EXECUTIVE COMMITTEE – 15 AUGUST 2005

PART I - DELEGATED

14.	UPDATE ON THE COMMUNITY SAFETY ACTION PLAN 2005/06 AND PROJECTS FUNDED BY THE SAFER STRONGER COMMUNTIES FUNDING (SSCF)

1.	Summary

1.1	To provide the Executive Committee with the Quarter 1 review of the Community Safety Action Plan for 2005/06 and the Stronger Safer Communities spend at the end of Quarter 1.

2.	Details

2.1	The Three Rivers Community Safety Action Plan 2005/06 was agreed by the Community Safety Partnership Board at its meeting on the 9th June 2005 and agreed by the Executive Committee on the 18th July 2005.  The plan contains 5 priority areas for action which are anti social behaviour, volume crime (including vehicle crime and burglary), violent crime (including domestic violence and hate crime), drugs and alcohol and cross cutting themes.

The action plan is monitored by the Community Safety Co-ordinating group on a quarterly basis and progress is reported up to the Community Safety Partnership Board.  Quarterly progress will also be reported back to the Leisure and Community Policy Panel.  The action plan helps the Community Safety Partnership to focus its efforts to where it has the greatest impact in preventing and reducing crime and disorder across the District.

The updated action plan is contained in Appendix A.

2.2	The Three Rivers Community Safety Partnership has been allocated £108,729 from the Home Office under the heading of Stronger Safer Communities Funding (SSCF) for 2005/06, 27% of which is capital funding.  The action plan highlights where a project has been funded through the Partnerships Home Office allocation.

3.	Options/Reasons for Recommendation

  - This report informs the Committee on the progress against the actions planned for 2005/06.  These actions will help work towards achieving the objectives and targets set in the 2005/08 Community Safety Strategy

4.	Policy/Budget Implications

4.1	The implementation of the action plan is in accordance with the priorities agreed within the Community Safety Strategy for 2005/2008 and within the allocated funding.

5.	Financial Implications

5.1	Departments have considered future revenue implications as part of their service and budget planning.

  - The total Home Office allocation for 2005/06 is £108,729

6.	Legal Implications

6.1	None specific.

7.	Staffing Implications

7.1	The implementation and monitoring of the plans involves significant staff resource but is currently contained within existing work programmes of the Community Partnerships Unit and the officers of the Community Safety Partnership Co-ordinating Group.  This will be reviewed for future years.

8.	Environmental Implications

8.1	The implementation of the action plan will have a positive impact on the local environment through such things as the removal of graffiti and abandoned vehicles.

9.	Community Safety Implications

9.1	The implementation of the action plan ensures that the strategy is translated into the work programmes of all partner agencies in order to achieve the targets laid down by the strategy.

10.	Customer Services Centre Implications

10.1	None specific

11.	Website Implications

11.1	None specific.

12.	Risk Management Implications

12.1	Without a monitored action plan the Government Office for the East of England (GO-East) will not release funds to Three Rivers District Council as the lead partnership agency.  Where actions fail to meet targets the co-ordination group will identify changes to ensure that the three year targets are met.

13.	Recommendation

13.1	That the Committee notes the Quarter 1 update of the Community Safety Action Plan 2005/06 and the progress against the different projects as detailed in Appendix A.

Background Papers

Community Safety Strategy 2005/08

Community Safety Action Plan 2005/06

Report prepared by:	Phillipa Scott, Community Safety Co-ordinator

The recommendations contained in this report DO NOT constitute a KEY DECISION.

APPENDICES / ATTACHMENTS

A – Updated Quarter 1 Action Plan report

UPDATED THREE RIVERS COMMUNITY SAFETY PARTNERSHIP ACTION PLAN 2005-06

THEME:	Anti Social Behaviour		  LEAD OFFICER:  Evelyn Mcwilliam – ASB Officer                    UPDATED: June 2005

| Link to Strategy | Owner and contact details | Project and short description | Performance measurement | Milestones | Status and date last updated | Partnership Funded 2005/06 (SSCF) | Invoices paid to date |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Reducing ASB | Evelyn McWilliam – ASB Officer TRDC 01923 727354 Evelyn.mcwilliam@threerivers.gov.uk | ASB Officer to work with the Police and other agencies to identify candidates for ASBO’s and ABC’s so to reduce the amount of ASB committed by persistent offenders within the District. | Monitor the number of ASBO’s and ABC’s in place. Reduction in the number of ASB incidents within the district. | ASBO’s and ABC’s are sought as and when needed. | We currently have 7 ASBO’s and 7 ABC’s in place within Three Rivers There were a total of 1,590 ASB incidents within Three Rivers during Quarter 1. | No | N/A |
| Reducing ASB | Alison Phin – Leisure Development Manager TRDC 01923 727143 Alison.phin@threerivers.gov.uk | To install a Youth Shelter at King George V Playing field. The project will form part of an overall refurbishment of a children's play area at King George V Playing Fields (KGV) in Mill End and compliment an outdoor basketball hoop and skateboarding area. Budgets of £18,000 for the Skateboarding area and £48,000 for the new children's play equipment have been set. | Number of ASB reports in the area of King George V playing fields reported to the Police to have reduced Number of young people using the shelter Young people’s reported fear of crime. Young people’s evaluation of service provision. | Shelter to be installed ready for use in the Summer. Usage of the shelter, number of ASB incidents recorded and surveys completed over the summer period ( by the end of September 2005) | A new youth shelter will be installed as part of the leisure refurbishment project at KGV playing fields, therefore the existing damaged youth shelter which is currently being stored at the depot is due to be repaired and installed at the Skateboarding area at West Hyde once Herts County Council give the go ahead. | £1,750 | - |
| Reducing ASB | Robin Barber – Maintenance and Environmental Services Area Manager - TRDC 01923 727026 Robin.barber@threerivers.gov.uk and Ian Parkhouse - Rickmansworth Station Manager 01923 481202 rickmansworthcmdr.a07@hertscc.gov.uk | To reduce the number of abandoned vehicles and fly tipping incidents across the district by carrying out Environmental Days (Operation Clean it days) | Reduction in the number of abandoned vehicles Number of vehicles removed/reported. Number of fly tips removed/reported. Reduction in deliberate and secondary fires in the targeted areas Number of EAD’s held | One EAD’ to be held every three months Quarterly review of deliberate and secondary fires one EAD’s have began taking place. | 125 abandoned vehicles were reported during the first quarter. 28 of these vehicles were collected and the remaining vehicles were either claimed, had valid tax or had been removed prior to being collected. There were 134 fly tips reported and removed during quarter 1. 1 Environmental Action Day was carried out during April. During Quarter 1 there were 15 deliberate fires compared to 26 deliberate fires last year within Three Rivers. | No | N/A |
| Reducing ASB | Community Inspector George Holland – Herts Police 01923 472127 George.holland@herts.pnn.police.uk | To police ASB hotspot areas. Implement Section 30 Orders in ASB hotspots at peak times of the year. | Reduction in the number of ASB incidents reported to the Police within specified locations and time span. Number of nuisance youth reports. Number of stop and account tickets issued to young people. | Section 30 Orders put in place as and when needed. | A Section 30 Order was re-instated within the South Oxhey area at the end of June 2005 During April – June 2005 there were 222 nuisance youth incidents reported within the South Oxhey Area. Figures for 2005/06 will be compared against 2004/05 figures from quarter 2) Awaiting data from the Police in relation to the number of stop and account tickets which have been issued. | No | N/A |
| Reducing ASB | Dave Corbett – HCC Youth Offending Team Manager 01923 229012 Dave.corbett@hertscc.gov.uk | To run a one week training programme, ‘Momentum on Two Wheels’, for young offenders and young people involved in Anti Social Behaviour | 6 month tracking on the young people taking part by the Youth Offending Team to monitor if their offending has reduced. Young people’s evaluation of service. | Programme to be run over the Summer. | The dates for 3 x week long courses have been set for August. The YOT will now begin to build a list of referrals to take part. | £2,500 | - |
| Reducing ASB | Alison Cameron-wood – Maintenance and Environmental Services Support Manager - TRDC 01923 727070 Alison.cameron-wood@threerivers.gov.uk | To install security doors at the flats in St Andrews Road South Oxhey to stop youths congregating in the hall ways and gaining access to the walkways above St Andrews Precinct and causing ASB | The number of ASB incidents at this location to reduce | Doors to be fitted within 4 – 6 weeks of doors being ordered | The leaseholders have now been notified of the plans to install security doors. They have to be given a months notice before prices are sought and then a further month to make any objections. An order can then be put in place; therefore doors should be installed in November. | £6,000 | - |
| Reducing ASB | Hannah Cornock – Leisure Project Support Officer -TRDC 01923 727144 Hannah.cornock@threerivers.gov.uk | Mill End Youth Project to run on a Friday night to offer young people (11 -19 year olds) in the area a range of diversionary activities. | Number of young people attending Young people’s evaluation of service. Reduction in ASB incidents in the area of Mill End | On-going | The Mill End Youth Project is running well and around 25 young people are attending each week. Currently the ages of the children attending are 11-14 years old. The project is now offering more activities than in previous years. Between April – June there was 50 nuisance youth incidents reported in the Penn area and 90 within the Maple Cross area. Figures for 2005/06 will be compared against 2004/05 figures from quarter 2) | No | N/A |
| Reducing ASB | Sue Topping – Leisure Play Development Officer - TRDC 01923 727151 Sue.topping@threerivers.gov.uk | The Shade summer project which offers young people (aged 10+) a range of diversionary activities over the summer holidays in various locations across the district | Number of young people attending Young people’s evaluation of service. Reduction in ASB incidents in the specified area | Activities to take place during the summer holidays | This project begins on the 25th July. | No | N/A |
| Reducing ASB | Chris Hope – Head of Leisure Services - TRDC 01923 727140 Chris.hope@threerivers.gov.uk | Free swimming sessions for young people at Sir James Altham Pool and William Penn Pool during the Summer Holidays. (During the day in the public swim sessions or the fun splash sessions) | Number of children attending the sessions Young people’s evaluation of service. Reduction in ASB incidents in the two locations specified during the specified times | Free sessions to take place during the summer holidays | This project begins on the 25th July and will offer free swimming sessions for children under 18 years old for the duration of the summer. | No | N/A |
| Reducing ASB | Spencer Edwards – Contracts Manager - TRC 0208 421 5215 Spencer.edwards@threerivers.gov.uk | To remove graffiti from privately owned buildings. Continue to remove racist or offensive graffiti within 3 hours of it being reported and all other graffiti within 24 hours of being reported | Number of reports/removals Removal deadlines made. Evaluation of service via minority race and faith forum. | Graffiti removal is on going Graffiti reports are collated at the end of each quarter | Graffiti removal is ongoing. During the first quarter there were 38 graffiti incidents on private property and £1713.65 was spent on removing graffiti from private property. | No | N/A |
| Reducing ASB | Ian Parkhouse - Rickmansworth Station Manager 01923 481202 rickmansworthcmdr.a07@hertscc.gov.uk | Action Against Arson: Areas identified through Risk Profiling will benefit from a targeted anti arson campaign. | Reduction in the number of arson incidents in the targeted areas | Areas such as South Oxhey and other Hot Spot wards will be targeted within 6 months; this will then be followed by further problem areas being identified through risk profiles. | Planned to be rolled out during August 2005 | No | N/A |

THEME:	Volume Crime		            LEAD OFFICER:  Inspector George Holland                   UPDATED: June 2005

| Link to Strategy | Owner and contact details | Project and short description | Performance Measurement | Milestones | Status and last updated | Partnership Funded | Invoices paid to date |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Reducing volume crime Prolific Offenders | Sgt James Goldsmith – PPO Manager – Herts Police 01923 472904 james.goldsmith@herts.pnn.police.uk | Targeting Prolific and other priority offenders Prevent and deter Catch and convict Rehabilitate and settle | Reduction in crime within Three Rivers Number of prolific offenders targeted Number of prolific offenders accessing treatment Young people’s evaluation of service | On going | PPO’s are monitored on a daily basis by the Police PPO Unit and action is taken should a PPO commit an offence. Regular updates are reported back to the Western Area’s Offender Management Group and the Three Rivers Co-ordinating Group. At the end of June there were 10 PPO’s being targeted within Three Rivers. Although there has been a decrease in some individual crime types Iquanta shows that when all crime types are measured as one “All Crime” Three Rivers has seen an increase in crime during quarter1. | No | N/A |
| Reducing volume crime Prolific Offenders | Godfrey Leak – SOVA Hertfordshire Probation Project 01727 867800 Sovaherts@talk21.com | Employment is the most significant factor in preventing re-offending. SOVA Herts is already involved in court work, mentoring and Basic Skills for offenders and wishes to expand its range of activities to include support in employment, training and education. Our support for the criminal justice system is by the involvement of local trained volunteers. The experience gained from citizen participation in community safety reduces the fear of crime and enables offenders the volunteers work with (including prolific and drug treatment and testing order) to access Education, training and employment on a personal level | Reduction in crime within Three Rivers Number of prolific offenders on the scheme. Offenders evaluation of service. | Existing volunteers to be mentoring from April 2005 onwards New volunteers to be trained in June 2005 New volunteers to be active by September 2005 Review meeting to take place with volunteers in March 2006 | 18 new volunteers have now been trained, 6 of these are from Three Rivers. A group of volunteers have also received training in relation to the Criminal Justice Act Where the Education, Training and Employment (ETE) initiative is a specified activity. 2 offenders are now on the ETE Project The awareness of the project has been raised with the Probation Service. | £4,000 | - |
| Reducing Burglary and distraction burglary | Gary Sibson – Crime Prevention Officer - Herts Police 01923 472020 Gary.sibson@herts.pnn.police.uk | A Doorstep Calendar to be produced in partnership with Three Valleys Water and Trading Standards containing awareness reminders about bogus callers. Calendars to be distributed to the elderly through out the district as a memoir aid for potential victims | Reduction in the number of distraction burglaries Evaluation of Calendar from customers. | Photographs to be arranged by August 2005 Distribution of calendar by the end of October 2005 | A working group for the production of the Countywide Calendar has been set up and the timetable is as follows: Artwork collected by 12/09/05 Studio images collated by 13/09/05 Proofs produced by 23/09/05 Final copy sent to printer by 30/09/05 Planned delivery date 1/11/05 | £750 | - |
| Reducing Burglary | Nicola Stageman – Manager of West Herts Against Crime (WHAC) 01923 801138 watrac@freenet.co.uk | To secure homes of vulnerable people within Three Rivers including those who have been victims of crime such as Burglary, Racial attacks and domestic violence attacks. WHAC offer a reactive and proactive service. | Reduction in Burglaries Customer satisfaction survey identifying demographics of race, age, disability, gender, sexual orientation and experience of domestic violence. | WHAC services are on going through out the year. Produce reports at the end of each quarter | WHAC have continued to install security devices free of charge to vulnerable people across the district. Vulnerable groups include victims of burglary, domestic violence, racist attacks, lone parents, the disabled and those over 60. This quarter WHAC Have dealt with both self referrals and referrals from the Police and up until 14th June 291 people from Three Rivers had benefited from the service (this was 27% up on the last quarter and 11% up on the same quarter last year). The total number of people who benefited from the Service during the whole of Quarter 1 was 362 people. | £10,000 | - |
| Reducing Burglary and vehicle crime | Geoff Carr – Chair of the Crime Prevention Panel 01923 665873 geoffcarruk@yahoo.co.uk | Contribution towards the Watford and Three Rivers Crime Prevention Panel to carry out such activities as property marking campaigns, purchase and fitting of shed bars and advice to car owners | Reduction in Burglaries and Car Crime Quarterly activity report | Events to take place through out the year | A wide range of activities have been carried out by the Crime Prevention Panel, including fitting shed bars, marking property and offering advice to local residents at fairs and safety awareness events. They have also visited ASDA to offer shoppers crime prevention advice when they entered or exited the store. Iquanta data for April – June 2005 shows domestic burglary has seen a downward trend and is well below the moving average for the Three Rivers area in relation to it historical trends. The Iquanta data also shows that vehicle crime has also continued to decrease within Three Rivers during quarter 1. (Figures from Inspector Holland shows that burglary is down 26% from last year) | £1,500 | - |
| Reducing Vehicle Crime | Community Inspector George Holland – Herts Police 01923 472127 George.holland@herts.pnn.police.uk | Targeted Patrols in Hotspot locations for car crimes such as car parks. Use of mobile bus stop style signs to raise awareness to members of the public about not leaving valuables in their cars. | Reduction in car crimes Quarterly activity report. | On going through out the year | The Police have continued to target their patrols in vehicle crime hotspot areas including Croxley Green, Chorleywood, Maple Cross, Mill End and South Oxhey. Operation Tarantula has continued and Operation Trench and Operation Tend have also started. As previously mentioned Iquanta data for April – June 2005 shows vehicle crime has seen a downward trend and is well below the moving average for the Three Rivers area in relation to it historical trends. | No | N/A |

THEME:  Violent crime including Hate Crime and DV          LEAD OFFICER: Inspector George Holland                   UPDATED: June 2005

Andy Stovold – Community Partnerships Manager

| Link to Strategy | Owner and contact details | Project and short description | Performance Measurement | Milestones | Status and last updated | Partnership Funded | Invoices paid to date |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Reducing violent crime Prolific Offenders | Sgt James Goldsmith – PPO Manager -Herts Police 01923 472904 james.goldsmith@herts.pnn.police.uk | Targeting Prolific and other priority offenders Prevent and deter Catch and convict Rehabilitate and settle | Reduction in crime within Three Rivers Number of prolific offenders targeted Number of prolific offenders accessing treatment Service user evaluation | On going | PPO’s are monitored on a daily basis by the Police PPO Unit and action is taken should a PPO commit an offence. Regular updates are reported back to the Western Area’s Offender Management Group and the Three Rivers Co-ordinating Group. At the end of June there were 10 PPO’s being targeted within Three Rivers. | No | N/A |
| Reducing violent crime | Verity Richards – DV Information line Co-ordinator Verity.richards@yahoo.co.uk | Domestic Violence Information Line | Number of calls to the line Publicity which has taken place | The DV Information line is ongoing throughout the year | Between Jan – March 2005 the DV line received 111 calls (2 of these could be identified as coming from the Three rivers area). There have been a further 44 calls during April and 61 calls during May. | No | N/A |
| Reducing Domestic Violence | Andy Stovold – Community Partnerships Manager TRDC 01923 727239 andy.stovold@threerivers.gov.uk | Develop Three Rivers multi agency Domestic Violence strategy and action plan in consultation with Domestic Violence Network. | Strategy produced by September. Action Plan quarterly reports. Number of reports of domestic violence Number of repeat victim reports | Strategy produced by September | Researched best practice standards from the Home Office. Meeting with an LGA Consultant has taken place During April - June 2005 there was 93 DV Offences recorded within Three Rivers. In relation to incidents there were 206 DV Incidents reported and 80 Repeat Incidents compared to 237 incidents and 91 repeat incidents reported last year between April and June. | No | N/A |
| Reduce Hate Crime | Evelyn Mcwilliam – ASB Officer TRDC 01923 727354 Evelyn.mcwilliam@threerivers.gov.uk | Develop Three Rivers multi agency race crime strategy and action plan. Develop Three Rivers multi agency homophobic crime strategy and action plan. | Strategy produced by October. Action Plan quarterly reports. Number of racist incidents reported. Strategy produced by November. Action Plan quarterly reports. Number of homophobic crime incidents reported. |  | Best Practice Research undertaken and a Corporate Policy has been drafted. We do not currently have the final number of Racial Incidents for April – June 2005 but in relation to Racially aggravated crime there were 50 incidents within Three Rivers compared to 53 for the same period last year although it is worth noting that criminal damage to a dwelling has risen and the biggest rise in this type of offence has occurred within the Northwick ward. We had 45 racial graffiti incidents within Three Rivers during quarter 1. In relation to Homophobic crime Best Practice is being researched. We currently do not have the final figure for the quarter in relation to Homophobic incidents. | No | N/A |

THEME: 	Drugs and Alcohol 	           LEAD OFFICER: Fiona Spence– DAT Project Officer	            UPDATED: June 2005

| Link to Strategy | Owner and contact details | Project and short description | Performance Measurement | Milestones | Status and last updated | Partnership Funded | Invoices paid to date |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Drugs and alcohol | David Gould – Funding and communications manager New Hope Trust 01923 210680 dgould@wnht.org | Contribution towards the costs of extending the opening hours of the New Hope Trust Day Care Centre and the Night Shelter so they other a dovetailed service ensuring vulnerable rough sleepers have some where to be. This will help to reduce the time these clients are left hanging around the streets and also reduce their drinking. | Reduction in complaints from the public Number of increased clients using the night shelter Number of increased clients using the day centre Progress in peoples lives | Project to run for a full year between April 2005 – March 2006 | Both the day centre and night shelter provided their extended opening hours throughout April – June 2005, providing their vulnerable clients with somewhere to go for an extra 6 hours a day. Approximately 70% of rough sleepers and night shelter clients took advantage of the new day centre hours and 100% of night shelter residents made use of the new night shelter hours. Many of the clients at the New Hope Trust are repeat offenders and / or suffer from drug and alcohol problems and their presence when hanging around the street is intimidating to the general public. Adhoc head counts carried out during quarter 1 showed the following April 21st – 47 people June 1st – 45 people June 24th – 59 people The Occupancy Of the 8 emergency beds at the night shelter are monitored more accurately and the occupancy rates for quarter1 were April - 98% May - 93% June - 93% | £2,500 | - |
| Drugs and alcohol | Vicki Read – DIP Manager - HCC 01992 588731 Vicki.read@hertscc.gov.uk | Switch / Drug Intervention Programme The Drugs Intervention Programme will work directly with drug misusing offenders, specifically those prolific and other priority offenders identified by the CDRP, to address substance misuse and offending behaviour with a view to reducing criminal activity. The programme will provide a through care and aftercare service which will co-ordinate and case manage drug misusing offenders through the criminal justice system, treatment and resettle offenders back into the community. The programme will work and deliver services in partnership with criminal justice agencies, and the voluntary and statutory sector to reduce drug related crime. The programme will be made up of a multi-agency team including drug treatment workers, a clinical intervention team, police officers, probation officers, non statutory treatment providers, prisons and local authorities. | Reduction in Crime within Three Rivers Reduction in drug related crime by PPO’s in Three Rivers Increase in the number of PPO’s retained in treatment in the Watford and Three Rivers area. Increase in the number of clients retained in treatment for 12 weeks in the Watford and Three Rivers area. 450 generic cases and 120 / 150 PPO DIP cases across Hertfordshire managed by March 2006 (at least 15 PPO’s to enter the DIP from Three Rivers) | April 2005: DIP will go live across the county with a full complement of staff to deliver the PPO element of DIP and the wider programme. July 2005: Marketing launch of DIP for all stake holders to open new premises and present first quarter figures September 2005: Mid year review report for the Home Office and National Treatment Agency March 2006: End of year report for the Home Office and National Treatment Agency | Although there has been a decrease in some individual crime types Iquanta shows that when all crime types are measured as one “All Crime” Three Rivers has seen an increase in crime during quarter1. During quarter 1 the drug intervention programme has been busy recruiting drug workers, clinical interventions teams, a probation service officer and police officers to work on the project. All PPO’s identified by CDRP’s and police intelligence have been approached by DIP and if they have agreed to take part in the programme they have been triage assessed. DIP has been holding clinics to offer offender management and clinical intervention at churches in Hertford, Stevenage, St Albans and Hemel Hempstead. At the moment PPO Officers do not have any admin staff and are therefore unable to provide data about drug related crime and as yet DIP have not been able to provide information about the number of PPO’s retained in treatment. At the end of June there were 10 PPO’s being targeted within Three Rivers. | £15,000 | £15,000 |
| Drugs and alcohol | Gary Ray – Project Manger - HCC 01992 588738 Gary.ray@hertscc.gov.uk | Drugs Paraphernalia Project 2005/06 | To have data and maps on held on MIDAS by October 20 plus frontline staff from Three Rivers to be trained in drug paraphernalia and harm reduction. | Data and maps to be held on MIDAS by the end October 2005 | 15 Frontline refuse workers from TRDC were trained during quarter 1. Possible training for other frontline workers and staff such as PCSO’s, Police, Neighbourhood representatives and school care takers to take place later in the year. A leaflet offering advice to residents about what to do if they find a discarded needle was distributed during April. No needles have been reported to TRDC during quarter 1 | No | N/A |
| Drugs and alcohol | Scott Cook – HCC Scott.cook@hertscc.gov.uk | Up to date and accessible information around alcohol for young people – to be provided by “Manic in Herts’ Website | Update of information on website | Manic newsletter to be produced on a monthly basis | The “it’s manic in Herts” newsletter has been produced on a monthly basis. The last one was sent out on 23rd June. Details of the summer activities due to run within the Three Rivers area have been sent to Scott Cook so they can be promoted on the website. | No | N/A |
| Drugs and alcohol | Hertfordshire Health Promotion Team Youth Service Resource Librarian Drug Education Forum | Focus on alcohol and tobacco by developing a range of alcohol resources and developing a range of tobacco resources. | Number of up-to-date resources available through Health Promotion + Youth Service Info Files. Number of alcohol focussed campaigns. Number of tobacco focussed campaigns. | April 2005 – March 2006 | No update has been given | No | N/A |
| Drugs and alcohol | Lead Officer to be identified if and when the Co-ordinating Group feel a visual audit is needed (will depend on what the visual audit will be focusing on) | Visual Audits to be carried out to gather information / evidence about the drug problems or other problems in an area. | Number of events held Information Collected | Visual Audits to be carried if and when they are needed. | None have been carried out so far this year | No | N/A |
| Drugs and alcohol | Debbie Lovelock – Health Development Manager of Herts Health Action with the Homeless 01707 251372 Debbie.lovelock@hyhg.org | The drugs and homelessness link project aims to provide support and access to appropriate treatment services homeless people with problematic substance misuse issues. There will be 2 drug link workers who will each serve 2 quadrants of Hertfordshire (North/East and South/West). They will intensively support individuals with engagement to services (including detox and rehab) as will helping to stabilise them. Both workers are acupuncture trained and they will also be able to advise clients on benefits and housing issues ensuring that a holistic approach is used. | Each client to be tracked on a data base to monitor their uptake of the service and the duration of their engagement. Monitoring the client’s levels of substance misuse to check decreases are achieved. Feedback from support agencies and clients about how effective the service is Evaluation forms and training sessions | April 2005 – June 2006 continue to engage clients, arrange a training programme and begin delivery. July 2005 – Sept 2005 continue client work and look at setting up acupuncture groups. Evaluate training. Oct 2005 – Dec 2005 arrange a second course of training and continue client work. Jan 2006 – Mar 2006 continue client work and evaluate training. | Since the HHAH project found out their bid had been successful during May the following work has been carried out. - Agencies in the area have been informed that clients from the Three Rivers area can now be referred. - The Druglink worker has been attending acupuncture training - 1 Client has been referred from Three Rivers and work started with him on the 1705/05. The client has now begun structured day care and has greatly reduced his drinking | £4,000 | - |
| Drugs and alcohol | Julia Bateson – Watford Football Club Learning Centre Manager 01923 496296 Julia.Bateson@watfordfc.com | Six groups of 14 Y5 and Y6 children (84 in total) will be given the opportunity to participate in a drug and alcohol education (including smoking) project at Watford Football Club. Each course will last 25 hours, and will be divided into two segments. Half of the time will be spent in the state-of-the-art Learning Centre, working on a multi-media project. This will include children creating a short film on drug/alcohol education, which they will have researched, scripted and filmed themselves. The other half of the project will involve the children in football coaching sessions, linked to leading and promoting a healthy lifestyle. The project will increase children’s knowledge about drugs, alcohol and smoking, and empower them to make healthy, informed choices. It will achieve this by working in partnership with the football club, and other agencies. | Children from each school will create a film; The film will be shown at Watford FC and at school, demonstrating key issues to peer groups, parents and invited guests; At the end of the football coaching, children will be given a fun quiz to test knowledge; Children’s evaluation forms. School evaluations and feedback. | Children from each school will create a film; The film will be shown at Watford FC and at school, demonstrating key issues to peer groups, parents and invited guests; At the end of the football coaching, children will be given a fun quiz to test knowledge; Children’s evaluation forms. School evaluations and feedback. | The Watford Football Club Learning Centre received confirmation of funding during June to carry out another course of the Football and Film Drugs Education project. This time children from schools in the Mill End and Maple Cross area were given first choice to attend the course. The following numbers of children were referred: St Mary’s C of E 4 Shepherds Primary School 6 St John’s RC 15 St Peter’s C of E 18 Arnett Hills 7 The remaining places have been advertised in the Watford Observer and letters have been sent out to other schools in the district to allow children form other areas of the district to take part in the project. So far additional children from St Paul’s C of E, Greenfield’s and Abbots Langley school have signed up for the summer project. | £14,721 | - |

THEME:   Cross Cutting Themes	     LEAD OFFICER: Phillipa Scott – Community Safety Co-ordinator               UPDATED: June 2005

| Link to Strategy | Owner and contact details | Project and short description | Performance Measurement | Milestones | Status and last updated | Partnership Funded | Invoices paid to date |
| --- | --- | --- | --- | --- | --- | --- | --- |
| All priorities | Chief Inspector Mick Fogarty – Herts Police 01438 757683 Mick.fogarty@herts.pnn.police.uk | Partnership Orientated Problem Solving Event to increase awareness and knowledge of best practice crime and disorder reduction initiatives amongst partners | Number of attendees Feedback forms completed by attendees | Date of conference is 16th November 2005 | The venue has been identified and booked and the event is now being publicised. Approached have also been made to keynote speakers. The event will be able to host 450 delegates and 20 places have been made available to the Three Rivers Community Safety Partnership. | £500 | £500 |
| All priorities | Chief Inspector David Moore – Herts Police 01707 638727 David.moore@herts.pnn.police.uk | MIDAS - The aim of MIDAS is to provide a central repository for all crime, disorder, drugs and alcohol and community safety data, accessible through an Internet based platform to all partners involved in Community Safety with the provision of standard analytical and mapping products. | Monitoring of the standard products supplied to partners Monitoring of bespoke products created for partners Seek feedback from partners on effectiveness and ease of use of system | March 2005: Invitation to Tender document sent out to Software houses. Selection to be made by end of Advertisement placed for System manager post April 2005: Contract for IT developmental work to be awarded and work to start Advertisements placed for remaining roles May /June 2005: System build and first products available focusing on Anti Social Behaviour and Violent Crime | Work on developing the MIDAS System is ongoing. The MIDAS System Manager has now been appointed and the GIS Product Officer has also been selected and will commence work during August / September, the part time Liaison Officer will then follow in October / November. Initial accommodation has been equipped with work stations and computers and work has begun on data gathering and the construction of IT architecture. | No | N/A |
| All priorities | Kevin Snow – Press Relations Manger -TRDC 01923 727255 Kevin.snow@threerivers.gov.uk | A year long community safety campaign promoting community safety initiatives and raising awareness to the residents of Three Rivers about simple ways they can keep themselves safe. | Number of media hits (i.e. articles / radio coverage) Number of enquires relating to the campaign | Campaign launched on the 1st April 2005 On going through out the year | The campaign was launched on the 1st April and was covered in the Watford Observer, The Watford Free, BBC Three Counties Radio and the Spring edition of Three Rivers Times. The Watford Observer has officially backed the campaign and the launch will be covered in the next edition of Herts Beat. A fact sheet on personal safety has been written ready to go on the website and safety leaflets were distributed at the canal festival. | No | N/A |
| All Priorities | Andy Stovold – Community Partnerships Manager - TRDC 01923 727239 Andy.stovold@threerivers.gov.uk | Improve community engagement and consultation by Locality Arrangements Carrying out Consultation Links with the DV Forum, Pensioners Forum, Youth Forum and Citizens Panel. Increasing representation of minority race and faith communities, lgbt communities and disabled people within the Citizens Panel and other structures. | Number of groups / forums set up Number of meetings held Number of consultation events carried out Recommendations of consultation events. | To be in place by March 2006 | Joint work with the Police has been carried out to set up an Independent Advisory Group (IAG) Police and TRDC Officers have attended the following local area forums: Croxley Green, Chorleywood and Watford Rural. A Consultation event was held with minority race and faith communities. | No | N/A |
| Youth | Andy Stovold – Community Partnerships Manager - TRDC 01923 727239 Andy.stovold@threerivers.gov.uk | To develop multi-agency strategies to address the needs of young people in relation to crime | Number agencies signed up to implement strategies. Views of young people. Quarterly update reports. | To be in place by March 2006 | Discussions with HCC and other agencies have taken place in response to every child matters and race crime. | No | N/A |
| Hotspots | Andy Stovold – Community Partnerships Manager - TRDC 01923 727239 Andy.stovold@threerivers.gov.uk | To develop targeted multi agency strategies for key hotspot locations. | Number of agencies signed up to each strategy. Views of local residents. External funding obtained. Quarterly update reports. | To be in place by March 2006 | There has been a joint response to ASB in Croxley Green, Chorleywood and South Oxhey | No | N/A |
| Community Safety | Ian Parkhouse - Rickmansworth Station Manager 01923 481202 rickmansworthcmdr.a07@hertscc.gov.uk | Smoke detector initiative: In conjunction with community health partners the Fire Service to fit smoke detectors in the homes of vulnerable residents in the Three Rivers area. | All identified vulnerable residents to have a smoke detector | All identified vulnerable residents to have a working smoke detector, a fire risk assessment and an escape plan by the end of March 2006 | This initiative is on going throughout the year. | No | N/A |
| Community Safety | Ian Parkhouse - Rickmansworth Station Manager 01923 481202 rickmansworthcmdr.a07@hertscc.gov.uk | Quick Strike: After all property fires, surrounding houses in the vicinity will be visited within 24 hours by fire crews to check detector (fitting one in necessary) and offering fire advice. | Quarterly review of the number of property fires, establishing whether a smoke detector was installed and whether the occupiers had an escape plan. | Campaign is ongoing | 5 quick strikes have been completed following property fires. Multiple properties have been visited and smoke detectors have been fitted where necessary | No | N/A |
| Community Safety | Ian Parkhouse - Rickmansworth Station Manager 01923 481202 rickmansworthcmdr.a07@hertscc.gov.uk | Home Risk Assessments: To carry out a risk based programme of home risk assessments in Three Rivers. | Quarterly review of the number of assessments carried out through the Performance management system | On going | 76 home risk assessments have been conducted | No | N/A |
| Community Safety | Ian Parkhouse - Rickmansworth Station Manager 01923 481202 rickmansworthcmdr.a07@hertscc.gov.uk | Canal Boat Safety: All canal boat residents to be identified and the occupiers to be offered fire safety advice and a smoke detector to be fitted where appropriate. | All residential canal boats in the Watford and Three Rivers area will have a smoke detector and the occupiers will be aware of fire safety issues relating to these vessels | Completed by the End of March 2006 | 90 information packs have been distributed to residential and pleasure boats within the Three Rivers area. | No | N/A |
| Community Safety | Ian Parkhouse - Rickmansworth Station Manager 01923 481202 rickmansworthcmdr.a07@hertscc.gov.uk | Smoke Free 3 Rivers: Campaign to reduce accidental property fires caused by smoking and smoking materials. Help reduce deliberate fires and arson caused by smoking materials. | Campaign to be measured against current benchmarks and standards | On going through out the year | This initiative is on going through out the year and dates have been planned in September and March to support the campaign | No | N/A |

Partnership Community Chest (Unallocated funds) - £45,508

Revenue - £35,508

Capital - £10,000