COMMUNITY SERVICES - ENVIRONMENTAL PROTECTION SERVICE PLAN

2018 - 2021

CONTENTS

| Section | Item | Page |
| --- | --- | --- |
|  | Introduction | 3 |
| 1 | Inputs | 3 |
| 1.1 | Budgets | 3 |
| 2 | Outputs and Outcomes | 4 |
| 2.1 | Performance management | 5 |
| 2.2 | Projects | 6 |
| 2.3 | Risk Management | 8 |
|  | Version Control | 14 |

INTRODUCTION

The progress of this service plan will be monitored in the following ways:

- Through regular discussion at departmental management team (DMT) and Section Heads meetings and logged in the version control section of this document

- Performance indicator monitoring by the Council’s Management Board on a quarterly basis

- By Committee reports twice a year (at the end of quarters two and four)

Service Plans will be formally updated on an annual basis, taking into account internal and external influences arising from monitoring arrangements throughout the year.

SECTION 1:	INPUTS

| 1.1 | Budgets |
| --- | --- |

|  | 2018/19 | 2019/20 | 2020/21 |
| --- | --- | --- | --- |
|  | Latest | Latest | Latest |
| Net Cost of Service (Direct Cost / Income only) | £ | £ | £ |
| Environmental Protection |  |  |  |

Further financial analysis can be found by using this link

SECTION 2:	OUTPUTS AND OUTCOMES

| 2.1 | Performance management |
| --- | --- |

2.1.1	Contribution to the Councils’ Strategic Aims and Objectives

| Strategic Plan Priority theme | Strategic Plan objective (inc. ref) | Measure (including the reference) | Target |
| --- | --- | --- | --- |
| Better Neighbourhoods | 1.3.1 Improve and facilitate access to leisure and recreational activities for adults 2.1.1 Maintain the number of accredited open spaces, parks and woodland areas. 2.1.2 Minimise waste and optimise recycling. 2.1.4 Maintain clean streets. | CP02 – Satisfaction with quality/provision of parks and open spaces LL34 – Maintain Green Flag Accreditation EP10 – Increase the percentage of household waste sent for reuse, recycling and composting. EP06 – Decrease the tonnage of household waste collected and sent to landfill CP03 – The percentage of respondents who are satisfied with refuse collection CP04 – The percentage of respondents who are satisfied with doorstep recycling CP01 – Satisfaction with ‘keeping public land clear of litter and refuse’ | 93% 3 60% <15,000 tonnes 76% 76% 78% |
| Healthier Communities | We will strive to improve and maintain service standards for all services | EH06 Respond to all requests for service within 14 days (animal control). EH07 – Respond to all requests for service within 10 days (pest control) EP11 – Percentage of collections made on the correct day | 98% 98% 95% |

The Environmental Protection department also provides data for and contributes to CP17 Reduce fly tipping across the district, which is reported by the Community Safety department.

2.1.2 	Performance indicators

Performance indicators are used to aid the decision making process as well as assess the efficiency and effectiveness of service delivery. The data that we use must be accurate, reliable and timely. To meet these requirements we have adopted the Audit Commission’s Standards for Better Data Quality. Further details of the Council’s commitment to data quality can be found in the Strategic Plan.

| Ref | Description | 2016/17 Actual | 2017/18 Target (Current year) | 2018/19 Target (Next year) | 2019/20 Target | 2020/21 Target |
| --- | --- | --- | --- | --- | --- | --- |
| EH06 | Respond to all requests for service within 24 hours (animal control) | 89.57% | 98.00% | 98% | 98% | 98% |
| EH07 | Respond to all requests for service within 10days (pest control) | 98.83% | 98.00% | 98% | 98% | 98% |
| EP01 | Percentage household waste recycled | 30.24% | 34.00% | 28% | 28% | 28% |
| EP03 | The kg of household waste collected per head per annum | 368.69 kgs | 390kgs | 390kgs | 390kgs | 390kgs |
| EP04 | The Percentage change in Kg per head from the previous year | -0.01% | 0.00% | 0% | 0% | 0% |
| EP06 | Tonnes of Household waste collected and sent to landfill | 12,883 tonnes | 15,000.00 | 15,000 tonnes | 15,000 tonnes | 15,000 tonnes |
| EP08 | Cost of Waste collection per household | £60.00 | £60.00 | £60.00 | £60.00 | £60.00 |
| EP 09 (NI 191) | Residual household waste per household | 346 kg | 400kgs | 400kg | 400kg | 400kg |
| EP 10 (NI 192) | Percentage of household waste sent for reuse, recycling and composting | 61.90% | 60.00% | 60% | 60% | 60% |
| EP11 | Percentage of collections made on the correct day (new indicator in 2017/18 to replace EP07) | N/A | New | 95% | 95% | 95% |
| EP12 | Percentage of eligible properties signed up to the Garden Waste scheme (new in 2017/18) | N/A | New for 2017-20 | 70% | 70% | 70% |
| EP13 | Manage the behaviour of dogs in our parks and open spaces (new in 2017/18) | N/A | New for 2017-20 | New – 5% reduction on YTD | New – 7% reduction on YTD | New – 9% reduction on YTD |
| CP01 | Satisfaction with ‘keeping public land clear of litter and refuse’ | 78% | 77.00% | 78% | 78% | 78% |
| CP02 | Satisfaction with parks and open spaces | 92% | 93.00% | 93% | 93% | 93% |
| CP03 | Satisfaction with refuse collection | 80% | 76.00% | 76% | 80% | 80% |
| CP04 | The percentage of respondents who are satisfied with doorstep recycling | 85% | 76.00% | 76% | 80% | 80% |

The Environmental Protection department also provides data for and contributes to CP17 Reduce fly tipping across the district, which is reported by the Community Safety department.

The Environmental Strategy Manager is responsible for the source data, data entry (assisted by a member of the Support team) and checking the data. The purpose of collating this data is to ensure that our services improve. It should be noted there will always be some variation between the figures reported on PDC and those recorded on Waste Data Flow. This is down to timescale of input and the way the calculations work i.e Waste Data Flow takes into account contamination whereas PDC is based on collected tonnages. It is Waste Data Flow figures that will be reported on nationally.

| 2.2 | Projects |
| --- | --- |

| Project details | Project timescales |
| --- | --- |
| Project title | Proposed outcome | 2018/19 | 2019/20 | 2020/21 |
| Reduction of Residual waste | Carry out a review of all the 240 litre bins to ensure only those eligible have one. Review collections in flat blocks to ensure capacity is in line with household collections. | TBC We intend to carry out a district wide review, after which reviews will be on-going on a regular basis. On-going | On-going | On-going |
| Cemetery carpark | To lay a new carpark at Woodcock Hill cemetery and layout the formal cemetery extension | On-going |  |  |
| Trade waste / recycling | Continue to expand the trade waste and recycling service offered by the Council. | On-going |  |  |
| Upgrade Batchworth Depot | New depot building. Property and Major Projects are leading. |  |  |  |
| Fly Tipping Promotions | To build on the project work carried out in 2017/18 | On-going |  |  |
| Review of assisted collection | Carry out a review of assisted collections to ensure only those eligible have one. | TBC We intend to carry out a district wide review, after which reviews will be on-going on a regular basis. | On-going | On-going |
| Digitisation | To continue to minimise the need for paper resource and get as much work as possible carried out electronically | On-going | On-going | On-going |

Note: TRDC is part Herts Waste Partnership (HWP) and officers from Environmental Protection are very much involved with the various groups as part of this including WasteAware, Heads of Waste, Directors and the Fly Tipping Group.  Officers are involved with projects from these groups on an on-going basis. TRDC is leading a county-wide fly tipping communications project during 2017/18 which will continue into 2018/19. The Environmental Strategy Manager is Vice Chair of the WasteAware group.

| 2.3 | Risk Management |
| --- | --- |

RISK REGISTER

| Service Plan: Environmental Protection 2018-21 |
| --- |
| Risk Ref | Risk | Impact | Impact Classification | Likelihood Classification | Reason for Assessment |  |  |
|  | Brief Description – Title of Risk | See Impact Table | See Impact Table | See Likelihood Table | Use this box to describe how the score has been derived |  |  |
| 1 | Insufficient staff | Service Disruption | II | E | If several key frontline staff were ill / injured for a period of time, the Council’s agency costs could rise substantially | Requires Treatment | No |
|  |  | Financial Loss | III |  |  | Last Review Date | 01/04/17 |
|  |  | Reputation | II |  |  | Next Milestone Date | 29/01/18 |
|  |  | Legal Implications | I |  |  | Next Review Date | 01/04/18 |
|  |  | People | I |  |  | Date Closed |  |
| 2 | Total failure of ICT systems | Service Disruption | III | E | Would affect office staff and missed bins etc, but operational staff could continue their work | Requires Treatment | No |
|  |  | Financial Loss | I |  |  | Last Review Date | 01/04/17 |
|  |  | Reputation | II |  |  | Next Milestone Date | 29/01/18 |
|  |  | Legal Implications | I |  |  | Next Review Date | 01/04/18 |
|  |  | People | I |  |  | Date Closed |  |
| 3 | Loss of accommodation | Service Disruption | II | E | Although it would be difficult for office based staff, the frontline service could still continue to operate. | Requires Treatment | No |
|  |  | Financial Loss | II |  |  | Last Review Date | 01/04/17 |
|  |  | Reputation | II |  |  | Next Milestone Date | 29/01/18 |
|  |  | Legal Implications | I |  |  | Next Review Date | 01/04/18 |
|  |  | People | I |  |  | Date Closed |  |
| 4 | Fraudulent activity | Service Disruption | I | E | Any fraudulent activity, including the collection of cash, is kept to a minimum by training and monitoring | Requires Treatment | No |
|  |  | Financial Loss | I |  |  | Last Review Date | 01/04/17 |
|  |  | Reputation | II |  |  | Next Milestone Date | 29/01/18 |
|  |  | Legal Implications | II |  |  | Next Review Date | 01/04/18 |
|  |  | People | I |  |  | Date Closed |  |

| Risk Ref | Risk | Impact | Impact Classification | Likelihood Classification | Reason for Assessment |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 5 | Whole fleet lost (accident / fire / theft). | Service Disruption | III | F | Cost of replacing fleet even if insured is high, as is the hire charge for prolonged time. However very unlikely for whole fleet to be lost | Requires Treatment | No |
|  |  | Financial Loss | IV |  |  | Last Review Date | 01/04/17 |
|  |  | Reputation | III |  |  | Next Milestone Date | 29/01/18 |
|  |  | Legal Implications | II |  |  | Next Review Date | 01/04/18 |
|  |  | People | I |  |  | Date Closed |  |
| 6 | Long period of Extreme weather / snow | Service Disruption | III | E | If extreme weather is prolonged then service could be disrupted for a long period of time. This is due to vehicles being very dangerous to drive on ice | Requires Treatment | No |
|  |  | Financial Loss | II |  |  | Last Review Date | 01/04/17 |
|  |  | Reputation | III |  |  | Next Milestone Date | 29/01/18 |
|  |  | Legal Implications | I |  |  | Next Review Date | 01/04/18 |
|  |  | People | II |  |  | Date Closed |  |
| 7 | Fuel shortage | Service Disruption | III | E | If there was a prolonged fuel shortage the Service continuity plan would be invoked, which would involve the dropping of some services on a temporary basis | Requires Treatment | No |
|  |  | Financial Loss | II |  |  | Last Review Date | 01/04/17 |
|  |  | Reputation | III |  |  | Next Milestone Date | 29/01/18 |
|  |  | Legal Implications | I |  |  | Next Review Date | 01/04/18 |
|  |  | People | I |  |  | Date Closed |  |
| 8 | H&S or DTP action | Service Disruption | III | F | H&S or DTP action could prevent services operating. Good training and procedures minimise the likelihood of this happening | Requires Treatment | No |
|  |  | Financial Loss | III |  |  | Last Review Date | 01/04/17 |
|  |  | Reputation | IV |  |  | Next Milestone Date | 29/01/18 |
|  |  | Legal Implications | IV |  |  | Next Review Date | 01/04/18 |
|  |  | People | I |  |  | Date Closed |  |
| 9 | Decrease in recycling rate | Service Disruption | I | E | The Council is hoping to maximise recycling, but this relies on other factors such as the financial climate. | Requires Treatment | No |
|  |  | Financial Loss | II |  |  | Last Review Date | 01/04/17 |
|  |  | Reputation | II |  |  | Next Milestone Date | 29/01/18 |
|  |  | Legal Implications | I |  |  | Next Review Date | 01/04/18 |
|  |  | People | I |  |  | Date Closed |  |
| 10 | Serious accident occurs due to vehicle movements at Batchworth Depot | Service Disruption | II | F | Stringent H&S procedures have minimised the likelihood of this occurring However if it were to happen then the impact could be catastrophic | Requires Treatment | Yes |
|  |  | Financial Loss | III |  |  | Last Review Date | 01/04/17 |
|  |  | Reputation | III |  |  | Next Milestone Date | 29/01/18 |
|  |  | Legal Implications | IV |  |  | Next Review Date | 01/04/18 |
|  |  | People | IV |  |  | Date Closed |  |

| Risk Ref | Risk | Impact | Impact Classification | Likelihood Classification | Reason for Assessment |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 11 | Serious accident due to staff operating machinery incorrectly | Service Disruption | II | F | The likelihood of this occurring has been mitigated by providing ongoing training and PPE. | Requires Treatment | No |
|  |  | Financial Loss | I |  |  | Last Review Date | 01/04/17 |
|  |  | Reputation | II |  |  | Next Milestone Date | 29/01/18 |
|  |  | Legal Implications | I |  |  | Next Review Date | 01/04/18 |
|  |  | People | III |  |  | Date Closed |  |
| 12 | Increased complaints | Service Disruption | II | E | The complaint monitoring procedures highlights repetitive complaints and enables officers to address the problem | Requires Treatment | No |
|  |  | Financial Loss | I |  |  | Last Review Date | 01/04/17 |
|  |  | Reputation | II |  |  | Next Milestone Date | 29/01/18 |
|  |  | Legal Implications | I |  |  | Next Review Date | 01/04/18 |
|  |  | People | I |  |  | Date Closed |  |
| 13 | Customers contaminate recycling bins in attempt to dispose of more general waste | Service Disruption | I | C | Officers try to prevent this by enforcing through the issuing of Fixed Penalty Notices | Requires Treatment | No |
|  |  | Financial Loss | II |  |  | Last Review Date | 01/04/17 |
|  |  | Reputation | II |  |  | Next Milestone Date | 29/01/18 |
|  |  | Legal Implications | II |  |  | Next Review Date | 01/04/18 |
|  |  | People | I |  |  | Date Closed |  |
| 14 | Increased fly tipping | Service Disruption | I | E | Effective enforcement should keep fly tipping to a minimum. | Requires Treatment | No |
|  |  | Financial Loss | II |  |  | Last Review Date | 01/04/17 |
|  |  | Reputation | II |  |  | Next Milestone Date | 29/01/18 |
|  |  | Legal Implications | II |  |  | Next Review Date | 01/04/18 |
|  |  | People | I |  |  | Date Closed |  |
| 15 | Commuted sum insufficient to cover future maintenance costs | Service Disruption | I | D | Officers make every effort to calculate correct commuted sum. | Requires Treatment | No |
|  |  | Financial Loss | II |  |  | Last Review Date | 01/04/17 |
|  |  | Reputation | I |  |  | Next Milestone Date | 29/01/18 |
|  |  | Legal Implications | I |  |  | Next Review Date | 01/04/18 |
|  |  | People | I |  |  | Date Closed |  |
| 16 | TRDC compelled not to act in its own interests by majority of Partnership. | Service Disruption | I | E | TRDC would always consider its own interests at any HWP meeting. | Requires Treatment | No |
|  |  | Financial Loss | II |  |  | Last Review Date | 01/04/17 |
|  |  | Reputation | II |  |  | Next Milestone Date | 29/01/18 |
|  |  | Legal Implications | I |  |  | Next Review Date | 01/04/18 |
|  |  | People | I |  |  | Date Closed |  |

| Risk Ref | Risk | Impact | Impact Classification | Likelihood Classification | Reason for Assessment |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 17 | Costs increase above budgets | Service Disruption | I | E | Careful budget monitoring should stop this from occurring. | Requires Treatment | No |
|  |  | Financial Loss | II |  |  | Last Review Date | 01/04/17 |
|  |  | Reputation | II |  |  | Next Milestone Date | 29/01/18 |
|  |  | Legal Implications | I |  |  | Next Review Date | 01/04/18 |
|  |  | People | I |  |  | Date Closed |  |
| 18 | Member of the public injured | Service Disruption | II | F | Stringent H&S checks minimise the likelihood of this happening | Requires Treatment | No |
|  |  | Financial Loss | III |  |  | Last Review Date | 01/04/17 |
|  |  | Reputation | III |  |  | Next Milestone Date | 29/01/18 |
|  |  | Legal Implications | III |  |  | Next Review Date | 01/04/18 |
|  |  | People | III |  |  | Date Closed |  |
| 19 | Maintenance falls below required standard | Service Disruption | I | E | Effective contract monitoring minimises the likelihood of this happening. | Requires Treatment | No |
|  |  | Financial Loss | I |  |  | Last Review Date | 01/04/17 |
|  |  | Reputation | III |  |  | Next Milestone Date | 29/01/18 |
|  |  | Legal Implications | II |  |  | Next Review Date | 01/04/18 |
|  |  | People | I |  |  | Date Closed |  |
| 20 | AFM withdrawn by HCC | Service Disruption | I | B | Linked into partnership agreement | Requires Treatment | yes |
|  |  | Financial Loss | IV |  |  | Last Review Date | 01/04/17 |
|  |  | Reputation | I |  |  | Next Milestone Date | 29/01/18 |
|  |  | Legal Implications | I |  |  | Next Review Date | 01/04/18 |
|  |  | People | I |  |  | Date Closed |  |
| 21 | Crews unable to complete work | Service Disruption | II | E | This is mitigated by running spare vehicles to shuttle when crews are working longer hours | Requires Treatment | No |
|  |  | Financial Loss | II |  |  | Last Review Date | 01/04/17 |
|  |  | Reputation | I |  |  | Next Milestone Date | 29/01/18 |
|  |  | Legal Implications | I |  |  | Next Review Date | 01/04/18 |
|  |  | People | I |  |  | Date Closed |  |
| 22 | Revenue for sale of materials decreases thereby not covering costs | Service Disruption | III | D | Long-term contracts and HWP procurement ensuring economies of scale. Budget monitor process allows us to check this throughout the year. | Requires Treatment | No |
|  |  | Financial Loss | II |  |  | Last Review Date | 01/04/17 |
|  |  | Reputation | III |  |  | Next Milestone Date | 29/01/18 |
|  |  | Legal Implications | II |  |  | Next Review Date | 01/04/18 |
|  |  | People | I |  |  | Date Closed |  |

| Risk Ref | Risk | Impact | Impact Classification | Likelihood Classification | Reason for Assessment |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 23 | Public satisfaction decreases | Service Disruption | III | D | Officers working in partnership with HWP to find optimum solution. We also have a procedure in place to monitor complaints. | Requires Treatment | No |
|  |  | Financial Loss | II |  |  | Last Review Date | 01/04/17 |
|  |  | Reputation | III |  |  | Next Milestone Date | 29/01/18 |
|  |  | Legal Implications | II |  |  | Next Review Date | 01/04/18 |
|  |  | People | I |  |  | Date Closed |  |
| 24 | Insufficient grit for prolonged period of time | Service Disruption | III | C | TRDC have entered into arrangement with HCC | Requires Treatment | Yes |
|  |  | Financial Loss | II |  |  | Last Review Date | 01/04/17 |
|  |  | Reputation | III |  |  | Next Milestone Date | 29/01/18 |
|  |  | Legal Implications | II |  |  | Next Review Date | 01/04/18 |
|  |  | People | I |  |  | Date Closed |  |
| 25 | Routine inspections of play equipment | Service Disruption | III | E | Failure to assess adequately could result in injury | Requires Treatment | Yes |
|  |  | Financial Loss | II |  |  | Last Review Date | 01/04/17 |
|  |  | Reputation | III |  |  | Next Milestone Date | 29/01/18 |
|  |  | Legal Implications | II |  |  | Next Review Date | 01/04/18 |
|  |  | People | I |  |  | Date Closed |  |
| 26 | Level of charges affects take up of service | Service Disruption | I | C | Without appropriate market testing a change to fees and charges could affect service take up | Requires Treatment | No |
|  |  | Financial Loss | II |  |  | Last Review Date | 01/04/17 |
|  |  | Reputation | I |  |  | Next Milestone Date | 29/01/18 |
|  |  | Legal Implications | I |  |  | Next Review Date | 01/04/18 |
|  |  | People | I |  |  | Date Closed |  |

| Likelihood | A |  |  |  |  |  | Impact | Likelihood |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | B |  |  | 20 |  |  | V = Catastrophic | A = ≥98% |
|  | C | 13, 26 | 24 |  |  |  | IV = Critical | B = 75% - 97% |
|  | D | 15 | 22, 23, |  |  |  | III = Significant | C = 50% - 74% |
|  | E | 4, 9,12, 16, 21, | 1, 2, 3, 6, 7,11, 14,17, 19, | 25 |  |  | II = Marginal | D = 25% - 49% |
|  | F |  |  | 5,8, 18 | 10 |  | I = Negligible | E = 3% - 24% |
|  |  | I | II | III | IV | V |  | F = ≤2% |
|  | Impact |

Version Control

Example

| Version No. | Date | Reason for Update / Significant Changes | Made By |
| --- | --- | --- | --- |
| 1.0 | 10.10.17 | Initial draft completed | JP/MC |
| 1.1 | 11.10.17 | Updates to most sections | JP |
| 1.2 | 12.10.17 | Updates to Risk, Performance and Projects sections | JP/GG |