Three Rivers District Council

Audit Committee Progress Report

28 March 2017

- Recommendation

- Members are recommended to:

- Note the Internal Audit Progress Report for the period to 10 March 2017

- Approve amendments to the Audit Plan as at 10 March 2017

- Agree removal of implemented audit recommendations (Appendices 3-10)

- Agree changes to the implementation dates for 16 audit recommendations (paragraph 2.5) for the reasons set out in Appendices 3 to 10

- Contents

1 		Introduction and Background

1.1 Purpose of Report

1.2 Background

2 	Audit Plan Update

2.1 Delivery of Audit Plan and Key Findings

2.3 All Priority Audit Recommendations

2.6 Proposed Audit Plan Amendments

2.7 Performance against Targets

- Appendices

- Progress against the 2016/17 Audit Plan

- 2016/17 Audit Plan Projected Start Dates

3-10 Progress against Outstanding Internal Audit Recommendations

1. Introduction and Background

- Purpose of Report

  - This report details:

  - Progress made by the Shared Internal Audit Service (SIAS) in delivering the Council’s annual audit plan for 2016/17 as at 10 March 2017.

  - Implementation status of all previously agreed audit recommendations from 2009/10 onwards.

  - An update on performance management information as at 10 March 2017.

- Background

  - The work of internal audit is required to be reported to a Member Body so that the Council has an opportunity to review and monitor an essential component of corporate governance and gain assurance that its internal audit provision is fulfilling its statutory obligations. It is considered good practice that progress reports also include proposed amendments to the agreed annual audit plan.

  - The 2016/17 Annual Audit Plan was approved by Audit Committee on 22 March 2016.

  - The Audit Committee receives periodic updates on progress against the Annual Audit Plan from SIAS, the most recent of which was brought to this Committee on 22 November 2016.

2. Audit Plan Update

- Delivery of Audit Plan and Key Audit Findings

2.1      As at 10 March 2017, 86% of the 2016/17 Audit Plan days had been delivered (calculation excludes unused contingency). Appendix A provides a status update on each individual deliverable within the audit plan.

2.2	Three 2016/17 audits providing assurance to the Audit Committee have been finalised since the November meeting of this Committee. All final audit reports are available to Members on request.

| Audit Title | Date of Issue | Assurance Level | Number and Priority of Recommendations |
| --- | --- | --- | --- |
| Office Services | Jan ‘17 | Substantial | Two medium Five merits attention |
| Green Waste Charging | Feb ‘17 | Substantial | Two medium One merits attention |
| Creditors | Mar ‘17 | Substantial | One medium |

- All Priority Audit Recommendations

- 2.3	Members will be aware that a Final Audit Report is issued when agreed by Management. This includes an agreement to implement the recommendations made.  It is SIAS’s responsibility to bring to Members’ attention the implementation status of recommendations; it is the responsibility of officers to implement the recommendations by the agreed date.

2.4     The table below summarises progress in implementation of all outstanding internal audit recommendations at March 2017, with full details given in appendices 3 to 10:

| Year | Recommendations made No. | Implemented | Not yet due | Outstanding & request made for extended time | Percentage implemented % |
| --- | --- | --- | --- | --- | --- |
| 2009/10 | 144 | 144 | 0 | 0 | 100% |
| 2010/11 | 180 | 179 | 0 | 1 | 99% |
| 2011/12 | 102 | 100 | 0 | 2 | 98% |
| 2012/13 | 36 | 36 | 0 | 0 | 100% |
| 2013/14 | 79 | 78 | 0 | 1 | 99% |
| 2014/15 | 67 | 59 | 1 | 7 | 88% |
| 2015/16 | 29 | 28 | 0 | 1 | 97% |
| 2016/17 | 14 | 6 | 4 | 4 | 43% |

  - Since November 2016 Audit Committee, extension to implementation dates have been requested by action owners for 16 recommendations as follows:

- One from the 2010/11 IT Remote Working audit,

- One from the 2011/12 IT Project Management audit,

- One from the 2011/12 IT Backup and Disaster Recovery audit,

- One from the 2013/14 Cyber risk audit,

- One from the 2014/15 NDR audit,

- One from the 2014/15 Asset Management audit;

- Two from the 2014./15 Enforcement audit,

- One from the 2014/15 Benefits audit,

- Two from the 2014/15 Disaster Recovery audit,

- One from the 2015/16 Contract Management audit,

- One from the 2016/17 Corporate Credit Cards audit, and

- Three from the 2016/17 Office Services audit.

Proposed 2016/17 Audit Plan Amendments

2.6		The following amendments to the 2016/17 Audit Plan have been agreed with officers of the Council and are detailed below for Audit Committee approval:

Additions / Deletions:

- Land Charges audit deferred until quarter 1 of 2017/18 as new software is currently being installed. 7.5 days returned to contingency (shared plan).

- Following officer requests and agreed with the Council’s Head of Finance, the ICT audit has been re-phased to the first quarter of 2017/18.  The 19.5 audit days freed up have been diverted to support an in depth assurance review of the shared payroll service as requested by the MD of WBC and Joint Management Board.  These have been added to the existing payroll review in the shared service audit plan.

Changes

- 2 days added to the Office Services audit (from Contingency – Shared Plan) to cover increased scope.

- 2 days added to the Contract Management audit (from Contingency – Shared Plan) to cover additional time required to collate multiple management responses to the audit recommendations.

Performance against Targets

Reporting of Audit Plan Delivery Progress

2.7	To help the Committee assess the current situation in terms of progress against the projects in the 2016/17 Audit Plan, an analysis of agreed start dates is shown at Appendix 2. Dates have been agreed with management and resources allocated accordingly. This is designed to facilitate smooth delivery of the audit plan through the year.

2.8	The 2016/17 Annual performance indicators and targets were approved by the SIAS Board in March 2016. Actual performance for Three Rivers District Council (including the Shared Services Plan) against the targets that are monitored in year is set out in the table below.

| Performance Indicator | Annual Target | Profiled Target to 10 March 2017 | Actual to 10 March 2017 |
| --- | --- | --- | --- |
| 1. Planned Days – percentage of actual billable days against planned chargeable days completed (excluding unused contingency) | 95% | 92% | 86% |
| 2. Planned Projects – percentage of actual completed projects to draft report stage against planned completed projects (excludes 2015/16 completion and ‘ongoing’ pieces) | 95% | 65% (15 out of 23 projects to draft) * see note below | 61% (14 out of 23 projects to draft) *see note below |
| 3. Client Satisfaction – percentage of client satisfaction questionnaires returned at ‘satisfactory’ level | 100% | 100% | 100% |
| 4. Number of High Priority Audit Recommendations agreed | 95% | 95% | N/A (none yet made) |

* Draft reports have not yet been issued for the Officer Expenses and Starters & Leavers audits. The fieldwork and quality review stages are complete, however, Management have instructed that issue of the draft reports should be timed to coincide with the completion of the Payroll Assurance Review which is currently underway. These audits are not therefore included in either the ‘profiled target’ or ‘actual’ statistics reported in performance indicator 1 above.

2.9	In addition, the performance targets listed below are annual in nature.  Performance against these targets will be reported in the 2016/17 Head of Assurance’s Annual Report:

- 5. External Auditors’ Satisfaction – the Annual Audit Letter should formally record whether or not the External Auditors are able to rely upon the range and the quality of SIAS’ work.

- 6. Annual Plan – prepared in time to present to the March meeting of each Audit Committee.  If there is no March meeting then the plan should be prepared for the first meeting of the civic year.

- 7. Head of Assurance’s Annual Report – presented at the Audit Committee’s first meeting of the civic year.

- 2016/17 SIAS Audit Plan

| AUDITABLE AREA | LEVEL OF ASSURANCE | RECS |  |  | AUDIT PLAN DAYS |  |  | LEAD AUDITOR ASSIGNED |  | BILLABLE DAYS COMPLETED | STATUS/COMMENT |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | H | M | MA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key Financial Systems |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Benefits (shared plan) |  |  |  |  | 14 |  | Yes |  |  | 13.5 | Draft report issued |  |  |  |  |  |  |  |
| Council Tax (shared plan) |  |  |  |  | 11 |  | Yes |  |  | 10.5 | Draft report issued |  |  |  |  |  |  |  |
| Creditors (shared plan) | Substantial | 0 | 1 | 0 | 9 |  | Yes |  |  | 9 | Final report issued |  |  |  |  |  |  |  |
| Debtors (shared plan) |  |  |  |  | 10 |  | Yes |  |  | 9.5 | Draft report issued |  |  |  |  |  |  |  |
| Main Accounting (shared plan) |  |  |  |  | 12 |  | Yes |  |  | 11.5 | Draft report issued |  |  |  |  |  |  |  |
| NDR (shared plan) | Full | 0 | 0 | 0 | 12 |  | Yes |  |  | 12 | Final report issued |  |  |  |  |  |  |  |
| Payroll (shared plan) |  |  |  |  | 31.5 |  | Yes |  |  | 22 | In fieldwork |  |  |  |  |  |  |  |
| Treasury Management (shared plan) |  |  |  |  | 10 |  | Yes |  |  | 5 | In fieldwork |  |  |  |  |  |  |  |
| Budget Monitoring (shared plan) |  |  |  |  | 8 |  | Yes |  |  | 7.5 | Draft report issued |  |  |  |  |  |  |  |
| Operational Audits |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Green Waste Charging | Substantial | 0 | 2 | 1 | 8 |  | Yes |  |  | 8 | Final report issued |  |  |  |  |  |  |  |
| HR Starters & Leavers (shared plan) |  |  |  |  | 16 |  | Yes |  |  | 15.5 | In quality review |  |  |  |  |  |  |  |
| Land Charges | - | - | - | - | 0.5 |  | N/A |  |  | 0.5 | Cancelled |  |  |  |  |  |  |  |
| Office Services | Substantial | 0 | 2 | 5 | 12 |  | Yes |  |  | 12 | Final report issued |  |  |  |  |  |  |  |
| Officer Expenses (shared plan) |  |  |  |  | 12 |  | Yes |  |  | 11.5 | In quality review |  |  |  |  |  |  |  |
| Corporate Credit Cards | Substantial | 0 | 2 | 1 | 8 |  | Yes |  |  | 8 | Final report issued |  |  |  |  |  |  |  |
| Revenues & Benefits Service – Enforcement Agents Contract (shared plan) |  |  |  |  | 10 |  | Yes |  |  | 7.5 | In fieldwork |  |  |  |  |  |  |  |
| Section 106 Agreements | Substantial | 0 | 1 | 0 | 11 |  | Yes |  |  | 11 | Final report issued |  |  |  |  |  |  |  |
| Beat the Killer Cold | Substantial | - | - | - | 6 |  | Yes |  |  | 6 | Final report issued |  |  |  |  |  |  |  |
| DFG Capital Grant Certification | N/A | - | - | - | 2 |  | Yes |  |  | 2 | Complete |  |  |  |  |  |  |  |
| Procurement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Fleet Management / Vehicle Maintenance Contract |  |  |  |  | 12 | Yes |  |  |  | 5 | In fieldwork |  |  |  |  |  |  |  |
| Contract Management |  |  |  |  | 12 | Yes |  |  |  | 11 | Draft report issued |  |  |  |  |  |  |  |
| Joint Reviews / Shared Learning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Shared Learning Newsletters and Summary Themed Reports |  |  |  |  | 2 | N/A |  |  |  | 1.5 | Complete |  |  |  |  |  |  |  |
| Audit Committee Workshop |  |  |  |  | 1 | N/A |  |  |  | 0 | Due quarter 4 |  |  |  |  |  |  |  |
| Joint Review - Benchmarking Workshop |  |  |  |  | 2 | N/A |  |  |  | 0 | Due quarter 4 |  |  |  |  |  |  |  |
| Joint Review – Local Authority Trading |  |  |  |  | 2.5 | BDO |  |  |  | 1 | In fieldwork |  |  |  |  |  |  |  |
| Joint Review – PREVENT |  |  |  |  | 2.5 | BDO |  |  |  | 1.5 | In fieldwork |  |  |  |  |  |  |  |
| Counter Fraud |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Review of Counter-Fraud Arrangements (shared plan) |  |  |  |  | 5 |  | Yes |  |  | 1 | In fieldwork |  |  |  |  |  |  |  |
| Risk Management and Governance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| No audits in the plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ad Hoc Advice |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ad Hoc Advice |  |  |  |  | 3 |  | - |  |  | 2.5 | Ongoing |  |  |  |  |  |  |  |
| IT Audits |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IT Audits – detail to be determined (shared plan) |  |  |  |  | 0.5 |  | N/A |  |  | 0.5 | Cancelled |  |  |  |  |  |  |  |
| Contingency |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Unused Contingency (shared plan) |  |  |  |  | 17.5 |  | - |  |  | 0 |  |  |  |  |  |  |  |  |
| Follow-Up Audits |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Follow-up of outstanding audit recommendations |  |  |  |  | 11 |  | N/A |  |  | 11 | Complete |  |  |  |  |  |  |  |
| Strategic Support |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Head of Internal Audit Opinion 2015/16 |  |  |  |  | 2 |  | N/A |  |  | 2 | Complete |  |  |  |  |  |  |  |
| External Audit Liaison |  |  |  |  | 1 |  | N/A |  |  | 1 | Complete |  |  |  |  |  |  |  |
| Audit Committee |  |  |  |  | 11 |  | N/A |  |  | 10 | Ongoing |  |  |  |  |  |  |  |
| Monitoring and Client Meetings |  |  |  |  | 12 |  | N/A |  |  | 11 | Ongoing |  |  |  |  |  |  |  |
| 2017/18 Audit Planning |  |  |  |  | 8 |  | N/A |  |  | 8 | Complete |  |  |  |  |  |  |  |
| SIAS Development |  |  |  |  | 3 |  | N/A |  |  | 3 | Complete |  |  |  |  |  |  |  |
| 2015/16 Projects Requiring Completion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2015/16 Projects Requiring Completion (5 days shared plan; 5 days TRDC) | Various |  |  |  | 10 |  |  |  | N/A | 10 | Complete |  |  |  |  |  |  |  |
| TRDC TOTAL |  |  |  |  | 137.5 |  |  |  |  | 121 |  |  |  |  |  |  |  |  |
| SHARED SERVICES TOTAL |  |  |  |  | 183.5 |  |  |  |  | 141.5 |  |  |  |  |  |  |  |  |
| COMBINED TOTAL |  |  |  |  | 321 |  |  |  |  | 262.5 |  |  |  |  |  |  |  |  |

Key to recommendation priority levels:

H = High

M = Medium

MA = Merits attention

| Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Revenues & Benefits Parameter Testing (shared plan)* Complete | Officer Expenses (shared plan)* In quality review |  | Corporate Credit Cards Final report issued | Contract Management Draft report issued | Green Waste Charging Final report issued | Council Tax (shared plan) Draft report issued | NDR (shared plan) Final report issued | Payroll (shared plan) In fieldwork | Treasury Management (shared plan)* In fieldwork | Budget Monitoring (shared plan) Draft report issued |  |
| Section 106 Agreements Final report issued | Beat the Killer Cold Final report issued |  |  | HR Starters & Leavers (shared plan)* In quality review | Office Services Final report issued | Debtors (shared plan) Draft report issued | Benefits (shared plan) Draft report issued | Creditors (shared plan)* Final report issued | Fleet Management / Vehicle Maintenance Contract* In fieldwork |  |  |
|  |  |  |  |  | Disabled Facilities Grants – Certification Complete | Enforcement Agents Contract – Revs & Bens Service (shared plan) In fieldwork |  | Main Accounting (shared plan)* Draft report issued |  |  |  |
|  |  |  |  |  |  |  |  | Review of Counter-Fraud Arrangements (shared plan) In fieldwork |  |  |  |

*Notes:

- Fleet Management / Vehicle Maintenance Contract audit deferred from May at Management’s request in view of staff changes / absence and priority given to the introduction of charging for green waste collection.

- Officer Expenses and Starters & Leavers audits – draft reports not yet issued. The fieldwork and quality review stages are complete, however, Management have instructed that issue of the draft reports should be timed to coincide with the completion of the Payroll Assurance Review which is currently underway.

- The following key financial audits have been moved slightly to accommodate external audit reporting requirements:

  - Creditors and Main Accounting audits moved from January to December

  - Treasury Management moved from December to January / February.