Appendix 2

COMMUNITY SERVICES – LEISURE AND LANDSCAPES SERVICE PLAN

2018 - 2021

CONTENTS

| Section | Item | Page |
| --- | --- | --- |
|  | Introduction | 3 |
| 1 | Inputs | 3 |
| 1.1 | Budgets | 3 |
| 2 | Outputs and Outcomes | 5 |
| 2.1 | Performance management | 5 |
| 2.2 | Projects | 8 |
| 2.3 | Risk Management | 9 |
|  | Version Control | 12 |

INTRODUCTION

The progress of this service plan will be monitored in the following ways:

- Through regular discussion at departmental management team (DMT) and Section Heads meetings and logged in the version control section of this document

- Performance indicator monitoring by the Council’s Management Board on a quarterly basis

- By Committee reports twice a year (at the end of quarters two and four)

Service Plans will be formally updated on an annual basis, taking into account internal and external influences arising from monitoring arrangements throughout the year.

Link to Strategic Plan, Service Plans and Performance Indicators Folder

SECTION 1:	INPUTS

| 1.1 | Budgets |
| --- | --- |

|  | 2017/18 Latest | 2018/19 Latest | 2019/20 Latest |
| --- | --- | --- | --- |
|  | £ | £ | £ |
| Net Cost of Service (Direct cost / Income Only) |  |  |  |

Further financial analysis can be found by using this link

SECTION 2:	OUTPUTS AND OUTCOMES

| 2.1 | Performance management |
| --- | --- |

2.1.1	Contribution to the Councils’ Strategic Aims and Objectives

| Strategic Plan Priority theme | Strategic Plan objective (inc. ref) | Measure (including the reference) | Target |
| --- | --- | --- | --- |
| Better Neighbourhoods | 1.1.2 Maintain the number of accredited open spaces, parks and woodland areas. | LL34 – To maintain accreditation for Green Flag LL32 – UK Woodlands Assurance Scheme (UKWAS) accreditation. | 3 Maintained |
| Healthier Communities | 2.5.1 Improve and facilitate access to leisure and recreational activities for adults 2.5.2 Contribute to partnership working to reduce health inequalities 2.5.3 Provide a range of supervised leisure activities and facilities for young people. | LL31 – Attendances by adults at leisure venues and activities. LL24 – Sheltered Housing Scheme: Percentage of older people reporting specific health benefits. CP02 – Satisfaction with parks and open spaces LL25 a&b – Exercise Referral Scheme: (a) Number of new customers, (b) Number of participants who complete a 12 week programme LL33 – Attendances by young people at leisure venues and activities. LL28 – Children's play activities will be termed as ‘Good’ by Ofsted LL29 – no. of attendances by children from low income families at Easter and summer play schemes LL30 – Vulnerable children's satisfaction with leisure projects | 408,298 90% 89% a) 140 b) 60 220,942 Good 1,090 90% |
| Values |  | CP05 – Satisfaction with Three Rivers District Council CO02 – Public perception of how well informed they feel about public services CP46 – The perception of value for money from Three Rivers District Council The percentage of people who agree that local public services: …promote the interests of local residents (CP09) …act on the concerns of local residents (CP10) …treat all types of people fairly (CP11) | 73% 74% 59% 67% 62% 81% |

2.1.2 	Performance indicators

Performance indicators are used to aid the decision making process as well as assess the efficiency and effectiveness of service delivery. The data that we use must be accurate, reliable and timely. To meet these requirements we have adopted the Audit Commission’s Standards for Better Data Quality. Further details of the Council’s commitment to data quality can be found in the Strategic Plan.

| Ref | Description | 2016/17 Actual | 2017/18 Target (Current year) | 2018/19 Target (Next year) | 2019/20 Target | 2020/21 Target |
| --- | --- | --- | --- | --- | --- | --- |
| LL34 | To maintain accreditation for Green Flag | 3 | 3 | 3 | 3 | 3 |
| LL32 | UK Woodlands Assurance Scheme (UKWAS) accreditation. | Maintained | Maintained | Maintained | Maintained | Maintained |
| LL31 | Attendances by adults at leisure venues and activities. | 399,653 | 408,298 | 409,298 | 410,300 | 411,300 |
| LL24 | Sheltered Housing Scheme: Percentage of older people reporting specific health benefits | 100% | 90% | 90% | 90% | 90% |
| CP02 | Satisfaction with parks and open spaces | 92% | 89% | 89% | 89% | 89% |
| LL25 a&b | Exercise Referral Scheme: (a) Number of new customers, (b) Number of participants who complete a 12 week programme | a) 193 b) 52 | a) 140 b) 60 | a) 140 b) 60 | a) 140 b) 60 | a) 140 b) 60 |
| LL33 | Attendances by young people at leisure venues and activities. | 201,654 | 220,942 | 221,942 | 223,000 | 224,000 |
| LL28 | Children's play activities will be termed as ‘Good’ by Ofsted | Outstanding | Good | Good | Good | Good |
| LL29 | no. of attendances by children from low income families at Easter and summer play schemes | 1,255 | 1,090 | 1,090 | 1,090 | 1,090 |
| LL30 | Vulnerable children's satisfaction with leisure projects | 83% | 90% | 90% | 90% | 90% |

The Head of Community Services is responsible for the source data, data entry and checking the data. The purpose of collating this data is to ensure that our services improve.

| 2.2 | Projects |
| --- | --- |

| Project details | Project timescales |
| --- | --- |
| Project title | Proposed outcome | 2018/19 | 2019/20 | 2020/21 |
| S106 – Abbots Langley Project | Development of offsite Leisure facilities at Manor House Grounds Sports Complex (tennis courts and MUGA) and Henderson Hub | Completion | N/A | N/A |
| S106 – Abbots Langley Project | Development of Manor House Grounds Skate Park | Setting up steering group of young people | Completion | N/A |
| Heritage Lottery Fund Application | Funding allocated for projects within Three Rivers District Council | Awaiting outcome of funding application |  |  |
| Heritage Lottery Fund Project | Subject to funding agreement, development and installation of projects as outlined in the funding application – to include park ranger and Heritage Wildlife Centre | Commencement | Completion |  |
| Heritage Trail | Completion of a large heritage trail in Leavesden Country Park | Commencement | Completion |  |
| Chorleywood Play Area | Installation of a new play area in Chorleywood | Commencement and Completion | Completion (should a public enquiry be required) | N/A |
| Skidmore Way Play Area | Refurbishment to Skidmore Way Play Area, Rickmansworth | Completion | N/A | N/A |
| Croxley Green Skate Park | Refurbishment of Croxley Green Skate park | Commencement and completion | N/A | N/A |
| Denham Way Play Area | Refurbishment of play area in Maple Cross |  | Commencement and completion | N/A |
| The Swillet Play Area | Refurbishment of play area in Chorleywood |  | Commencement and completion | N/A |
| Leavesden Country Park play area | Refurbishment of Leavesden Country Park play area |  |  | Commencement and completion |
| Redevelopment of Bury Lake Young Mariners (in conjunction with Major Projects team) | New facility to increase water based sports participation in line with the project business and development plan | Commencement of construction | Construction completed | N/A |
| Leisure Management Contract(s) | New Leisure Management Contract(s) for The Centre, William Penn Leisure Centre and Rickmansworth Golf Course | Commencement of Leisure Management Contract(s) – 1 April 2018 | N/A | N/A |
| Redevelopment of SJA Pool at The Centre In conjunction with Major Projects team | Provision of new pool for South Oxhey and updated Centre. (Sir James Altham Pool to remain open until new pool in place) | Construction of extension/refurbishment of The Centre | Completion | N/A |
| Leavesden Studios planning approval S106 agreement investment | Liaise with developers on the design of the proposed children’s play area Community consultation for the design of the public open space (Horsesfield site) Implementation of the outcomes of the consultation | Maintain and enhance The Horses’ Field in accordance with the Management Plan | Maintain and enhance The Horses’ Field in accordance with the Management Plan | Maintain and enhance The Horses’ Field in accordance with the Management Plan |
| Rickmansworth Hockey all weather pitch | To support the local hockey club with the building of a new all weather hockey pitch in Rickmansworth (Scotsbridge playing fields) | Completion of Rickmansworth Hockey all weather pitch | N/A | N/A |
| Scotsbridge project | Bankside and access improvements to the site part of the Chess Valley Walk | Completion of feasibility assessment in partnership with CMS and EA. | Implementation of project arising out of feasibility study and in partnership with EA. | N/A |
| Tree Survey (Eezytreev) | To improve consistency, effectiveness and efficiency of surveying taking into account the outcomes of Tree Survey Audit. | Year one of the second phase of the three year rolling survey of tree stock incorporating annual survey of high risk areas | Year two of the second phase of the three year rolling tree stock incorporating annual survey of high risk areas | Year three of the second phase of the three year rolling tree stock incorporating annual survey of high risk areas |
| YMCA | Support the YMCA with the building of a new Café at YMCA Woodlands | Completion of construction | N/A | N/A |
| Batchworth Lake footpath network improvements | Works to improve the footpath surface around Batchworth Lake with positively impact on the wider cyclepath/towpath and footpath network. This will include links to Rickmansworth Town Centre and Station, Watford and the Ebury Way, into the Colne Valley Regional Park and beyond | Second phase of project | Completion of Project linking into the wider cyclepath and footpath network. | N/A |
| Watersmeet – Refurbishment of dressing rooms | Replace the work surfaces and redecorate the 4 dressing rooms to improve the condition | Completion |  |  |
| Watersmeet – Refurbishment of upper foyer toilets | Works to replace and redesign the layout of the public toilets in the upper foyer to allow an additional cubicle in the ladies toilet | Commencement and Completion |  |  |
| Watersmeet – Replacement of cinema screen | Replace the fixed cinema screen with a roller screen that can be rigged down stage to allow films to be shown over the top of other events |  | Commencement and Completion |  |

| 2.3 | Risk Management |
| --- | --- |

RISK REGISTER

| Service Plan: Community Services (Leisure and Landscapes) 2018-2021 |
| --- |
| Risk Ref | Risk | Impact | Impact Classification | Likelihood Classification | Reason for Assessment |  |  |
|  | Brief Description – Title of Risk | See Impact Table | See Impact Table | See Likelihood Table | Use this box to describe how the score has been derived |  |  |
| 1 | Insufficient ‘casual’ staff – Leisure Development | Service Disruption | III | E | Needed for a range of activities including play schemes, Mill End Youth Club, play rangers | Requires Treatment | Yes |
|  |  | Financial Loss | III |  |  | Last Review Date | 22.09.17 |
|  |  | Reputation | IV |  |  | Next Milestone Date | 31.03.18 |
|  |  | Legal Implications | II |  |  | Next Review Date | 30.09.18 |
|  |  | People | III |  |  | Date Closed | Ongoing |
| 2 | Failure of ICT systems | Service Disruption | III | D | Key systems such as word, excel not supported and not being upgraded | Requires Treatment | Yes |
|  |  | Financial Loss | II |  |  | Last Review Date | 22.09.17 |
|  |  | Reputation | IV |  |  | Next Milestone Date | 31.03.18 |
|  |  | Legal Implications | - |  |  | Next Review Date | 30.09.18 |
|  |  | People |  |  |  | Date Closed | Ongoing |
| 3 | Loss of accommodation | Service Disruption | III | E | Includes loss of a major leisure venue, including closure due to bad weather. | Requires Treatment | Yes |
|  |  | Financial Loss | III |  |  | Last Review Date | 22.09.17 |
|  |  | Reputation | IV |  |  | Next Milestone Date | 31.03.18 |
|  |  | Legal Implications | - |  |  | Next Review Date | 30.09.18 |
|  |  | People | - |  |  | Date Closed | Ongoing |
| 4 | Fraudulent activity | Service Disruption | III | E | Income handling within service reduced as most venues now managed by contractor. Watersmeet procedures continue to be monitored | Requires Treatment | Yes |
|  |  | Financial Loss | III |  |  | Last Review Date | 22.09.17 |
|  |  | Reputation | IV |  |  | Next Milestone Date | 31.03.18 |
|  |  | Legal Implications | IV |  |  | Next Review Date | 30.09.18 |
|  |  | People | - |  |  | Date Closed | Ongoing |
| 5 | Temporary closure of venue or loss of service due to infectious disease | Service Disruption | IV | D | Includes swine flu, Ebola and legionella | Requires Treatment | Yes |
|  |  | Financial Loss | III |  |  | Last Review Date | 22.09.17 |
|  |  | Reputation | IV |  |  | Next Milestone Date | 31.03.18 |
|  |  | Legal Implications | IV |  |  | Next Review Date | 30.09.18 |
|  |  | People | II |  |  | Date Closed | Ongoing |
| 6 | Usage targets linked to Key Budget Indicators are not met | Service Disruption | - | D | Usage can vary and is prone to external market forces | Requires Treatment | Yes |
|  |  | Financial Loss | III |  |  | Last Review Date | 22.09.17 |
|  |  | Reputation | III |  |  | Next Milestone Date | 31.03.18 |
|  |  | Legal Implications | - |  |  | Next Review Date | 30.09.18 |
|  |  | People | - |  |  | Date Closed | Ongoing |
| 7 | Major capital project overruns or has unforeseen cost | Service Disruption | III | C | Few major projects anticipated. BLYM and redevelopment of The Centre are currently the two ongoing major capital projects | Requires Treatment | Yes |
|  |  | Financial Loss | IV |  |  | Last Review Date | 22.09.17 |
|  |  | Reputation | IV |  |  | Next Milestone Date | 31.03.18 |
|  |  | Legal Implications | IV |  |  | Next Review Date | 30.09.18 |
|  |  | People | - |  |  | Date Closed | Ongoing |
| 8 | Loss of partner or agreed partnership funding (revenue or capital) | Service Disruption | IV | D | Partnerships continue to be under financial pressure | Requires Treatment | Yes |
|  |  | Financial Loss | III |  |  | Last Review Date | 22.09.17 |
|  |  | Reputation | III |  |  | Next Milestone Date | 31.03.18 |
|  |  | Legal Implications | - |  |  | Next Review Date | 30.09.18 |
|  |  | People | - |  |  | Date Closed | Ongoing |
| b) Venues Risks |
| 9 | Council liable for fatality at leisure venue | Service Disruption | IV | E | H&S procedures monitored | Requires Treatment | Yes |
|  |  | Financial Loss | - |  |  | Last Review Date | 22.09.17 |
|  |  | Reputation | IV |  |  | Next Milestone Date | 31.03.18 |
|  |  | Legal Implications | IV |  |  | Next Review Date | 30.09.18 |
|  |  | People | V |  |  | Date Closed | Ongoing |
| 10 | Serious accident to venue customer or staff member | Service Disruption | IV | E | Thorough risk assessments in place for all dangerous activities. Actions from Watersmeet H&S audit in March 2015 have been completed and continue to be monitored | Requires Treatment | Yes |
|  |  | Financial Loss | - |  |  | Last Review Date | 22.09.17 |
|  |  | Reputation | IV |  |  | Next Milestone Date | 31.03.18 |
|  |  | Legal Implications | IV |  |  | Next Review Date | 30.09.18 |
|  |  | People | IV |  |  | Date Closed | Ongoing |
| 11 | Failure involving major plant or equipment at leisure venue | Service Disruption | IV | C | Planned preventative programme and monitoring in place at Leisure Centres. Reliant on support from Asset Management. Concern over M&E at SJA Pool and potential loss of income claim from Leisure Contractor | Requires Treatment | Yes |
|  |  | Financial Loss | III |  |  | Last Review Date | 22.09.17 |
|  |  | Reputation | IV |  |  | Next Milestone Date | 31.03.18 |
|  |  | Legal Implications | III |  |  | Next Review Date | 30.09.18 |
|  |  | People | - |  |  | Date Closed | Ongoing |

| 12 | Leisure Facilities Management: Operator fails to provide adequate service | Service Disruption | IV | E | Rating based on track record and contract monitoring procedures | Requires Treatment | Yes |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Financial Loss | III |  |  | Last Review Date | 22.09.17 |
|  |  | Reputation | IV |  |  | Next Milestone Date | 31.03.18 |
|  |  | Legal Implications | - |  |  | Next Review Date | 30.09.18 |
|  |  | People | - |  |  | Date Closed | Ongoing |
| 13 | Watersmeet: Failure to hit usage or income targets | Service Disruption | II | E | Relies on commercial trading and success of Pantomime | Requires Treatment | Yes |
|  |  | Financial Loss | III |  |  | Last Review Date | 22.09.17 |
|  |  | Reputation | III |  |  | Next Milestone Date | 31.03.18 |
|  |  | Legal Implications | - |  |  | Next Review Date | 30.09.18 |
|  |  | People | - |  |  | Date Closed | Ongoing |

| 14 | Watersmeet: Failure to retain casual or volunteer staff | Service Disruption | II | D | Reliance on volunteers. Campaign ongoing and training schedule in place | Requires Treatment | Yes |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Financial Loss | III |  |  | Last Review Date | 22.09.17 |
|  |  | Reputation | III |  |  | Next Milestone Date | 31.03.18 |
|  |  | Legal Implications | - |  |  | Next Review Date | 30.09.18 |
|  |  | People | - |  |  | Date Closed | Ongoing |
| 15 | New BLYM facility doesn’t realise growth in participation | Service Disruption Financial loss Reputation Legal Implications People | II l lll | E | Reliance of volunteers and no major drought. (Note, project still in early stages) | Requires Treatment Last Review Date Next Milestone Date Next Review Date Date Closed | Yes 18.08.17 31.03.18 30.09.18 |

| c) Leisure Development Risks |
| --- |
| 16 | The Council could fail to meet its legal obligations under the Children’s Act and the Care Act if it fails to Safeguard children and or adults at risk | Service Disruption | IV | D | Continues to be a high profile issue | Requires Treatment | Yes |
|  |  | Financial Loss | IV |  |  | Last Review Date | 22.09.17 |
|  |  | Reputation | V |  |  | Next Milestone Date | 31.03.18 |
|  |  | Legal Implications | V |  |  | Next Review Date | 30.09.18 |
|  |  | People | V |  |  | Date Closed | Ongoing |
| 17 | A child/children or adults at risk could be exposed to some form of abuse if Council fails to Safeguard | Service Disruption | IV | E | As above Continues to be a high profile issue | Requires Treatment | Yes |
|  |  | Financial Loss | IV |  |  | Last Review Date | 22.09.17 |
|  |  | Reputation | V |  |  | Next Milestone Date | 31.03.18 |
|  |  | Legal Implications | V |  |  | Next Review Date | 30.09.18 |
|  |  | People | V |  |  | Date Closed | Ongoing |

| 18 | Service fails to appoint playscheme staff with relevant and appropriate training qualifications to meet Ofsted requirements for Under 8s playscheme | Service Disruption | IV | D | Service will be unable to cater for children aged under 8 years of age, which is half of the play scheme service | Requires Treatment | Yes |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Financial Loss | II |  |  | Last Review Date | 22.09.17 |
|  |  | Reputation | III |  |  | Next Milestone Date | 31.03.18 |
|  |  | Legal Implications | I |  |  | Next Review Date | 30.09.18 |
|  |  | People | I |  |  | Date Closed | Ongoing |
| 19 | Newly installed/refurbished play/skate/gym areas fail to pass post installation inspection | Service Disruption | III | E | Play/skate/gym areas will remain closed until areas of failure remedied | Requires Treatment | Yes |
|  |  | Financial Loss | I |  |  | Last Review Date | 22.09.17 |
|  |  | Reputation | III |  |  | Next Milestone Date | 31.03.18 |
|  |  | Legal Implications | I |  |  | Next Review Date | 30.09.18 |
|  |  | People | I |  |  | Date Closed | Ongoing |
| 20 | Loss of S106 funding should projects not go ahead | Service Disruption | II | E | Legal implications and loss of funding for local residents. Poor community perception | Requires Treatment | Yes |
|  |  | Financial Loss | III |  |  | Last Review Date | 22.09.17 |
|  |  | Reputation | II |  |  | Next Milestone Date | 31.03.18 |
|  |  | Legal Implications | II |  |  | Next Review Date | 30.09.18 |
|  |  | People | I |  |  | Date Closed | Ongoing |
| 21 | Poor satisfaction by residents if agreed projects do not go ahead e.g. play area refurbishments | Service Disruption | II | D | Negative impact on the Council – poor satisfaction levels by the community and loss of trust | Requires Treatment | Yes |
|  |  | Financial Loss | I |  |  | Last Review Date | 22.09.17 |
|  |  | Reputation | II |  |  | Next Milestone Date | 31.03.18 |
|  |  | Legal Implications | I |  |  | Next Review Date | 30.09.18 |
|  |  | People | I |  |  | Date Closed | Ongoing |
| 22 | Accidents / Injuries to members of the public / employees should staff not complete appropriate health and safety checks on all projects | Service Disruption | III | E | Legal and financial implications. Heightened press and publicity of claims raises the profile of such incidents | Requires Treatment | Yes |
|  |  | Financial Loss | III |  |  | Last Review Date | 22.09.17 |
|  |  | Reputation | III |  |  | Next Milestone Date | 31.03.18 |
|  |  | Legal Implications | III |  |  | Next Review Date | 30.09.18 |
|  |  | People | III |  |  | Date Closed | Ongoing |

| d) Tree & Landscape Risks |
| --- |
| 23 | Tree failure causes damage to property rail accident/disaster, loss of life | Service Disruption | V | C | Proactive survey methods now in place which would minimise claims against the authority | Requires Treatment | Yes |
|  |  | Financial Loss | V |  |  | Last Review Date | 22.09.17 |
|  |  | Reputation | V |  |  | Next Milestone Date | 31.03.18 |
|  |  | Legal Implications | V |  |  | Next Review Date | 30.09.18 |
|  |  | People | V |  |  | Date Closed | Ongoing |

| 24 | Successful appeal to the High Court against a new TPO | Service Disruption | - | F | Adequate procedures in place to protect TRDC. | Requires Treatment | No |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Financial Loss | III |  |  | Last Review Date | 22.09.17 |
|  |  | Reputation | III |  |  | Next Milestone Date | 31.03.18 |
|  |  | Legal Implications | III |  |  | Next Review Date | 30.09.18 |
|  |  | People | - |  |  | Date Closed | Ongoing |
| 25 | Successful appeal to Lands Tribunal for compensation for refusal to permit works to trees | Service Disruption | - | D | Adequate procedures in place to reduce likelihood of successful claim | Requires Treatment | Yes |
|  |  | Financial Loss | III |  |  | Last Review Date | 22.09.17 |
|  |  | Reputation | III |  |  | Next Milestone Date | 31.03.18 |
|  |  | Legal Implications | III |  |  | Next Review Date | 30.09.18 |
|  |  | People | - |  |  | Date Closed | Ongoing |

| Likelihood | A |  |  |  |  |  | Impact | Likelihood |  | Enter Risk number in the profiling grid (left) against the highest impact classification for the risk and the appropriate likelihood classification taken from the table above. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | B |  |  |  |  |  | V = Catastrophic | A = ≥98% |  |  |
|  | C |  |  |  |  |  | IV = Critical | B = 75% - 97% |  |  |
|  | D |  |  |  |  |  | III = Significant | C = 50% - 74% |  |  |
|  | E |  |  |  |  |  | II = Marginal | D = 25% - 49% |  |  |
|  | F |  |  |  |  |  | I = Negligible | E = 3% - 24% |  |  |
|  |  | I | II | III | IV | V |  | F = ≤2% |  |  |
|  | Impact |  |  |  |  |

Version Control

| Version No. | Date | Reason for Update / Significant Changes | Made By |
| --- | --- | --- | --- |
| 1 | 22.09.17 | First Draft | CG |
| 2 | 22.09.17 | Watersmeet projects added | JS |
| 3 | 25.09.17 | Updated projects section | RF |
| 4 | 27.09.17 | Updated projects and performance indicators section | JH |