APPENDIX 1

Three Rivers District Council

Audit Committee Progress Report

22 March 2016

- Recommendation

- Members are recommended to:

- Note the Internal Audit Progress Report for the period to 4 March 2016

- Approve amendments to the Audit Plan as at 4 March 2016

- Agree removal of implemented audit recommendations (Appendices 3-9)

- Agree changes to the implementation dates for 5 audit recommendations (paragraph 2.5.1) for the reasons set out in Appendices 3 to 9

- Note the status of the 19 IT audit recommendations (paragraph 2.5.2)

- Contents

1 	Introduction and Background

1.1 Purpose of Report

1.2 Background

2 	Audit Plan Update

2.1 Delivery of Audit Plan and Key Findings

2.3 All Priority Audit Recommendations

2.6 Proposed Audit Plan Amendments

2.7 Performance against Targets

- Appendices

- Progress against the 2015/16 Audit Plan

- 2015/16 Audit Plan Projected Start Dates

3-9 Progress against Outstanding Internal Audit Recommendations

1. Introduction and Background

- Purpose of Report

  - This report details:

  - Progress made by the Shared Internal Audit Service (SIAS) in delivering the Council’s annual audit plan for 2015/16 as at 4 March 2016.

  - Implementation status of all previously agreed audit recommendations from 2009/10 onwards.

  - An update on performance management information as at 4 March 2016.

- Background

  - The work of internal audit is required to be reported to a Member Body so that the Council has an opportunity to review and monitor an essential component of corporate governance and gain assurance that its internal audit provision is fulfilling its statutory obligations. It is considered good practice that progress reports also include proposed amendments to the agreed annual audit plan.

  - The 2015/16 Annual Audit Plan was approved by Audit Committee on 17 March 2015.

  - The Audit Committee receives periodic updates on progress against the Annual Audit Plan from SIAS, the most recent of which was brought to this Committee on 26 November 2015.

2. Audit Plan Update

- Delivery of Audit Plan and Key Audit Findings

2.1    As at 4 March 2016, 93% of the 2015/16 Audit Plan days had been delivered (calculation excludes unused contingency). Appendix A provides a status update on each individual deliverable within the audit plan.

2.2	Nine 2015/16 audits providing assurance to the Audit Committee have been finalised since the November meeting of this Committee. All final audit reports are available to Members on request.

| Audit Title | Date of Issue | Assurance Level | Number and Priority of Recommendations |
| --- | --- | --- | --- |
| Business Continuity and Emergency Planning | Nov ‘15 | Full | None |
| Repair and Renew Grant | Dec ‘15 | N/A | N/A (review of grant payment processes) |
| Risk Management Benchmarking | Dec ‘15 | N/A | N/A (joint review with other SIAS clients) |
| Contract Management | Jan ‘16 | Substantial | One medium |
| Council Tax (shared plan) | Feb ‘16 | Substantial | Four medium Three merits attention |
| Treasury Management - CRSA Year 2 (shared plan) | Feb ‘16 | Substantial | None |
| Recruitment (shared plan) | Mar ‘16 | Full | None |
| Social Media | Mar ‘16 | Substantial | One medium Three merits attention |
| Corporate Governance* | Mar ‘16 | N/A | N/A |

- * - The Corporate Governance audit examined the transition from the Cabinet or Executive System to the Committee system at the Council  and sought to establish the successes and areas for improvement or amendment after 12 months of operating under the new governance arrangements.

- The nature of our work did not lend itself to the provision of an assurance opinion however the Council is encouraged to consider the themes and opportunities arising from the survey of Members and officers. The report is due to be considered by the next meeting of the Constitutional Working Party as part of their review of the committee governance arrangements.

- All Priority Audit Recommendations

- 2.3	Members will be aware that a Final Audit Report is issued when agreed by Management. This includes an agreement to implement the recommendations made.  It is SIAS’s responsibility to bring to Members’ attention the implementation status of recommendations; it is the responsibility of officers to implement the recommendations by the agreed date.

2.4    The table below summarises progress in implementation of all outstanding internal audit recommendations, with full details given in appendices 3 to 9:

| Year | Recommendations made No. | Implemented | Not yet due | Outstanding & request made for extended time | Percentage implemented % |
| --- | --- | --- | --- | --- | --- |
| 2009/10 | 144 | 141 | 0 | 3 | 98% |
| 2010/11 | 180 | 179 | 0 | 1 | 99% |
| 2011/12 | 102 | 99 | 0 | 3 | 97% |
| 2012/13 | 36 | 35 | 0 | 1 | 97% |
| 2013/14 | 79 | 76 | 0 | 3 | 96% |
| 2014/15 | 67 | 47 | 6 | 14 | 70% |
| 2015/16 | 16 | 12 | 3 | 1 | 75% |

  - The 26 recommendations in the ‘outstanding and request made for extended time’ column fall into 2 categories as per sections 2.5.1 and 2.5.2 below.

2.5.1	Extension to implementation dates have been requested for five recommendations as follows:

- One for Health & Safety,

- Two for Asset Management,

- One for Enforcement, and

- One for Diesel Usage.

In respect of two recommendations from the Benefits audit (target dates 30 Nov / 31 Dec 2015), no updates were provided for this committee.

    - For the nineteen outstanding IT audit recommendations, no specific updates have been provided and a generic comment has been added to each in appendices 3 to 9. The following management comment was provided by the Director of Finance:

‘These recommendations will be taken into consideration in the new arrangement for the ICT service from June 2016.'

The recommendations relate to the following audits:

- Three for Network Infrastructure,

- One for IT Remote Working,

- One for IT Project Management,

- Two for IT Back-Up and Disaster Recovery,

- One for Server Virtualisation,

- Two for Cyber Risk,

- Three for IT Change Management,

- Three for Disaster Recovery, and

- Three for IT Operations and Contract Management.

Proposed 2015/16 Audit Plan Amendments

2.6		Since November 2015 Audit Committee, the following amendments to the 2015/16 Audit Plan have been agreed with officers of the Council and are detailed below for Audit Committee approval:

Additions:

- Insurance – new audit added at the request of management. Five days taken from contingency.

- Social Media – new audit added at the request of management. Five days taken from contingency.

- Repair and Renew Grant – review end of scheme. Two and a half days taken from contingency.

- Community Infrastructure Levy – new audit added at the request of management. Five days taken from contingency.

- Corporate Governance – 5 additional days taken from contingency to cover extended scope.

Deletions:

- Office Services – existing audit cancelled as re-structuring underway. Seven and a half days returned to contingency.

- South Oxhey – existing audit cancelled as no value in work at this time. Twelve days returned to contingency.

- IT Contract Management – existing audit cancelled at client request to avoid demand at this time on IT resources that are required for the provision of current IT support and re-tendering of the IT contract. The intention is to share output with management.  Five days returned to contingency.

Performance against Targets

Reporting of Audit Plan Delivery Progress

2.7	To help the Committee assess the current situation in terms of progress against the projects in the 2015/16 Audit Plan, an analysis of agreed start dates is shown at Appendix 2. Dates have been agreed with management and resources allocated accordingly. This is designed to facilitate smooth delivery of the audit plan through the year.

2.8	The 2015/16 Annual performance indicators and targets were approved by the SIAS Board in March 2015. Actual performance for Three Rivers District Council against the targets that are monitored in year is set out in the table below.

| Performance Indicator | Annual Target | Profiled Target to 4 March 2016 | Actual to 4 March 2016 |
| --- | --- | --- | --- |
| 1. Planned Days – percentage of actual billable days against planned chargeable days completed (excluding unused contingency) | 95% | 92% | 94% |
| 2. Planned Projects – percentage of actual completed projects to draft report stage against planned completed projects (excludes 2014/15 completion and ‘ongoing’ pieces) | 95% | 86% (18 out of 21 projects to draft) | 86% (18 out of 21 projects to draft) |
| 3. Client Satisfaction – percentage of client satisfaction questionnaires returned at ‘satisfactory’ level | 100% | 100% | 100% |
| 4. Number of High Priority Audit Recommendations agreed | 95% | 95% | 100% |

2.9	In addition, the performance targets listed below are annual in nature.  Performance against these targets will be reported in the 2015/16 Head of Assurance’s Annual Report:

- 5. External Auditors’ Satisfaction – the Annual Audit Letter should formally record whether or not the External Auditors are able to rely upon the range and the quality of SIAS’ work.

- 6. Annual Plan – prepared in time to present to the March meeting of each Audit Committee.  If there is no March meeting then the plan should be prepared for the first meeting of the civic year.

- 7. Head of Assurance’s Annual Report – presented at the Audit Committee’s first meeting of the civic year.

- 2015/16 SIAS Audit Plan

| AUDITABLE AREA | LEVEL OF ASSURANCE | RECS |  |  | AUDIT PLAN DAYS |  |  | LEAD AUDITOR ASSIGNED |  | BILLABLE DAYS COMPLETED | STATUS/COMMENT |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | H | M | MA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key Financial Systems |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Benefits (shared plan) |  |  |  |  | 14 |  | Yes |  |  | 13.5 | Draft report issued |  |  |  |  |  |  |  |
| Council Tax (shared plan) | Substantial | 0 | 4 | 3 | 11 |  | Yes |  |  | 11 | Final report issued |  |  |  |  |  |  |  |
| Creditors (shared plan) |  |  |  |  | 9 |  | Yes |  |  | 6 | In fieldwork |  |  |  |  |  |  |  |
| Debtors (shared plan) |  |  |  |  | 10 |  | Yes |  |  | 9.5 | Draft report issued |  |  |  |  |  |  |  |
| Main Accounting CRSA Yr2 (shared plan) | Substantial | 0 | 0 | 0 | 10 |  | Yes |  |  | 10 | Final report issued |  |  |  |  |  |  |  |
| NDR (shared plan) |  |  |  |  | 11 |  | Yes |  |  | 10.5 | Draft report issued |  |  |  |  |  |  |  |
| Payroll including payroll contract (shared plan) |  |  |  |  | 15 |  | Yes |  |  | 14 | Draft report issued |  |  |  |  |  |  |  |
| Treasury Management CRSA Yr2 (shared plan) | Substantial | 0 | 0 | 0 | 8 |  | Yes |  |  | 8 | Final report issued |  |  |  |  |  |  |  |
| Budget Monitoring (shared plan) |  |  |  |  | 8 |  | Yes |  |  | 6 | In fieldwork |  |  |  |  |  |  |  |
| Operational Audits |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Anti-Social Behaviour & Safeguarding | Substantial | 0 | 0 | 3 | 14 |  | Yes |  |  | 14 | Final report issued |  |  |  |  |  |  |  |
| Business Continuity & Emergency Planning | Full | 0 | 0 | 0 | 12 |  | Yes |  |  | 12 | Final report issued |  |  |  |  |  |  |  |
| Data Protection | Substantial | 0 | 0 | 1 | 6 |  | Yes |  |  | 6 | Final report issued |  |  |  |  |  |  |  |
| Diesel Usage | Moderate | 1 | 1 | 1 | 6 |  | Yes |  |  | 6 | Final report issued |  |  |  |  |  |  |  |
| Disabled Facilities Grants | Full | 0 | 0 | 0 | 6 |  | Yes |  |  | 6 | Final report issued |  |  |  |  |  |  |  |
| Freedom of Information | Substantial | 0 | 0 | 1 | 6 |  | Yes |  |  | 6 | Final report issued |  |  |  |  |  |  |  |
| Office Services |  |  |  |  | 0.5 |  | N/A |  |  | 0.5 | Cancelled |  |  |  |  |  |  |  |
| Recruitment (shared plan) | Full | 0 | 0 | 0 | 10 |  | Yes |  |  | 10 | Final report issued |  |  |  |  |  |  |  |
| Insurance |  |  |  |  | 5 |  | Yes |  |  | 4 | In quality review |  |  |  |  |  |  |  |
| Social Media | Substantial | 0 | 1 | 3 | 5 |  | Yes |  |  | 5 | Final report issued |  |  |  |  |  |  |  |
| Community Infrastructure Levy |  |  |  |  | 5 |  | Yes |  |  | 0 | In planning |  |  |  |  |  |  |  |
| Repair & Renew Grant | N/A | - | - | - | 2.5 |  | Yes |  |  | 2.5 | Complete |  |  |  |  |  |  |  |
| Procurement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contract Management | Substantial | 0 | 1 | 0 | 10 | Yes |  |  |  | 10 | Final report issued |  |  |  |  |  |  |  |
| South Oxhey Initiative |  |  |  |  | 0 | N/A |  |  |  | 0 | Cancelled |  |  |  |  |  |  |  |
| SIAS Joint Work |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Shared Learning Newsletters and Summary Themed Reports |  |  |  |  | 2 | N/A |  |  |  | 2 | Complete |  |  |  |  |  |  |  |
| Audit Committee Workshop |  |  |  |  | 1 | N/A |  |  |  | 1 | Complete |  |  |  |  |  |  |  |
| Risk Management Benchmarking Workshop |  |  |  |  | 2 | N/A |  |  |  | 2 | Complete |  |  |  |  |  |  |  |
| Counter Fraud |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Review of Counter-Fraud Arrangements (shared plan) |  |  |  |  | 0 |  | No |  |  | 0 | Cancelled |  |  |  |  |  |  |  |
| Risk Management and Governance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Corporate Governance | N/A | - | - | - | 20 |  | Yes |  |  | 20 | Final report issued |  |  |  |  |  |  |  |
| Ad Hoc Advice |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ad Hoc Advice |  |  |  |  | 3 |  | N/A |  |  | 3 | Complete |  |  |  |  |  |  |  |
| IT Audits |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IT Managed Service Delivery (shared plan) |  |  |  |  | 0.5 |  | N/A |  |  | 0.5 | Cancelled |  |  |  |  |  |  |  |
| IT Contract Management (shared plan) |  |  |  |  | 10 |  | Yes |  |  | 10 | Cancelled |  |  |  |  |  |  |  |
| IT Disaster Recovery Extended Follow-Up (shared plan) |  |  |  |  | 0.5 |  | N/A |  |  | 0.5 | Cancelled |  |  |  |  |  |  |  |
| Contingency |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Unused Contingency (shared plan) |  |  |  |  | 18 |  | N/A |  |  | 0 | As required |  |  |  |  |  |  |  |
| Follow-Up Audits |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Follow-up of outstanding audit recommendations |  |  |  |  | 10 |  | N/A |  |  | 10 | Complete |  |  |  |  |  |  |  |
| Strategic Support |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Head of Internal Audit Opinion 2014/15 | N/A |  |  |  | 2 |  | N/A |  |  | 2 | Complete |  |  |  |  |  |  |  |
| External Audit Liaison | N/A |  |  |  | 1 |  | N/A |  |  | 1 | Complete |  |  |  |  |  |  |  |
| Audit Committee | N/A |  |  |  | 10 |  | N/A |  |  | 9 | On-going |  |  |  |  |  |  |  |
| Monitoring and Client Meetings | N/A |  |  |  | 12 |  | N/A |  |  | 11 | On-going |  |  |  |  |  |  |  |
| 2016/17 Audit Planning | N/A |  |  |  | 8 |  | N/A |  |  | 8 | Complete |  |  |  |  |  |  |  |
| SIAS Development | N/A |  |  |  | 3 |  | N/A |  |  | 3 | Complete |  |  |  |  |  |  |  |
| 2014/15 Projects Requiring Completion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2014/15 Projects Requiring Completion (5 days shared plan; 4 days TRDC) | Various |  |  |  | 9 |  |  |  | N/A | 9 | Complete |  |  |  |  |  |  |  |
| TRDC TOTAL |  |  |  |  | 156 |  |  |  |  | 145.5 |  |  |  |  |  |  |  |  |
| SHARED SERVICES TOTAL |  |  |  |  | 140 |  |  |  |  | 114.5 |  |  |  |  |  |  |  |  |
| COMBINED TOTAL |  |  |  |  | 296 |  |  |  |  | 260 |  |  |  |  |  |  |  |  |

Key to recommendation priority levels:

H = High

M = Medium

MA = Merits attention

Key to Assurance Levels:

N/A = Not applicable

| Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Diesel Usage Final report issued | ASB / Safeguarding Final report issued | Disabled Facilities Grants* Final report issued |  | Contract Management Final report issued | Corporate Governance Final report issued | Business Continuity and Emergency Planning Final report issued | Benefits (shared plan) Draft report issued | Risk Mgmt (Joint Review) Complete | Creditors (shared plan) In fieldwork | Budget Monitoring (shared plan) In fieldwork |  |
| Revenues & Benefits Parameter Testing (shared plan)* Complete | Data Protection Final report issued |  |  | Recruitment (shared plan)* Final report issued |  | Council Tax (shared plan) Final report issued | Payroll inc contract (shared plan) Draft report issued | NDR (shared plan) Draft report issued | Main Accounting (shared plan) Final report issued | Insurance Quality review |  |
|  | Freedom of Information Final report issued |  |  |  |  | Debtors (shared plan) Draft report issued | Treasury Mgmt (shared plan) Final report issued |  | Social Media Final report issued |  |  |