Appendix 2

REGULATORY SERVICES SERVICE PLAN

2018 - 2021

CONTENTS

| Section | Item | Page |
| --- | --- | --- |
|  | Introduction | 3 |
| 1 | Inputs | 3 |
| 1.1 | Budgets | 3 |
| 2 | Outputs and Outcomes | 5 |
| 2.1 | Performance management | 5 |
| 2.2 | Projects | 8 |
| 2.3 | Risk Management | 9 |
|  | Version Control | 12 |

INTRODUCTION

The progress of this service plan will be monitored in the following ways:

- Through regular discussion at departmental management team (DMT) and Section Heads meetings and logged in the version control section of this document

- Performance indicator monitoring by the Council’s Management Board on a quarterly basis

- By Committee reports twice a year (at the end of quarters two and four)

Service Plans will be formally updated on an annual basis, taking into account internal and external influences arising from monitoring arrangements throughout the year.

Link to Strategic Plan, Service Plans and Performance Indicators Folder

SECTION 1:	INPUTS

| 1.1 | Budgets |
| --- | --- |

|  | 2017/18 Latest | 2018/19 Latest | 2019/20 Latest |
| --- | --- | --- | --- |
|  | £ | £ | £ |
| Net Cost of Service (Direct cost / Income Only) |  |  |  |

Further financial analysis can be found by using this link

SECTION 2:	OUTPUTS AND OUTCOMES

| 2.1 | Performance management |
| --- | --- |

2.1.1	Contribution to the Councils’ Strategic Aims and Objectives

As identified in the draft Strategic Plan 2018-2021 (‘Lead Service’).  Measures and targets should be developed further.

| Strategic Plan Priority theme | Strategic Plan objective (inc. ref) | Measure (including the reference) | Contribution of Regulatory Services to the Strategic Plan objective/measure | Target |
| --- | --- | --- | --- | --- |
| Better Neighbourhoods | Maintain high quality local neighbourhoods and streets 1.1.3 Preserve the Green Belt 1.2.1 Encouragement for business | CP18 Reduce the level of pavement parking in the District CP20 Reduce the sale of cars on verges and highways ESD04 Percentage of new homes built on previously developed land. ESD06 Change in employment floorspace | Consideration and implementation of future policy and enforcement to reduce the level of pavement parking in the District. Officers from the Projects & Compliance Team to work with other Council departments to support measures to reduce car sales on verges and highways. Continue to carry out Council duties in relation to street naming and numbering DM01 – NI157a major planning applications (target period for decision is 13 weeks) DM02 – NI157b minor planning applications (target period for a decision is 8 weeks) Receipt of and consideration of specialist consultee comments and incorporation in all relevant planning application reports | Reduction in pavement parking in accordance with agreed targets. Reduction of vehicles for sale on verges and highways. Provision of a cost neutral service with a consensus agreement on street naming and numbering. 60% of major applications determined within 13 weeks 65% of minor applications determined in 8 weeks All consultee comments received are considered. |
| Healthier Communities | 2.1.1 Improve or facilitate access to housing. 2.4.1 Ensure the safety of people in the district. | ESD01 – Net additional homes provided. ESD02 – Number of affordable homes delivered (gross). PS04 – provide additional temporary accommodation in the district. NI184 – Percentage of food establishments in the area which are broadly compliant with food hygiene law EHC04 & EHC05 – All high risk and other food premises inspected | DM01 – NI157a major planning applications (target period for decision is 13 weeks) DM02 – NI157b minor planning applications (target period for a decision is 8 weeks) Receipt of and consideration of specialist consultee comments and incorporation in all relevant planning application reports Carry out planned inspections of food premises according to risk rating and inspect high risk establishments at least once per year. Respond appropriately to notifications of accidents, dangerous occurrences, notifications of infectious diseases and complaints of unsafe workplace conditions. | 60% of major applications determined within 13 weeks 65% of minor applications determined in 8 weeks All consultee comments received are considered. 100% of planned inspections of high risk premises. |

2.1.2 	Performance indicators

See Data Quality Strategy for further details

Performance indicators are used to aid the decision making process as well as assess the efficiency and effectiveness of service delivery. The data that we use must be accurate, reliable and timely. To meet these requirements we have adopted the Audit Commission’s Standards for Better Data Quality. Further details of the Council’s commitment to data quality can be found in the Strategic Plan.

| Ref | Description | 2016/17 Actual | 2017/18 Target (Current year) | 2018/19 Target (Next year) | 2019/20 Target | 2020/21 Target |
| --- | --- | --- | --- | --- | --- | --- |
| DM01 | Issue decisions for major planning applications within 13 week period | 100% | 60% | 60% | 60% | 60% |
| DM02 | Issue decisions for minor planning applications within 8 week period | 92.83% | 65% | 65% | 65% | 65% |
| DM03 | Issue decisions for other planning applications within 8 week period | 97.23% | 80% | 80% | 80% | 80% |
| DM08 | Percentage of planning application appeals allowed (by PINS) | 28.57% | 35% or lower | 35% or lower | 35% or lower | 35% or lower |
| SU01 | Land and Property Services – turn around all land and property searches within 5 working days | Not reported. | 70% | 70% | 70% | 70% |
| EHC03 | Respond to all requests for services within 24 hours (food inspection, disease control, notified accidents and related enquiries no.) | 98% | 95% | 95% | 95% | 95% |
| EHC04 | The % of food premises inspections due that were carried out for high risk premises | 100% | 95% | 95% | 95% | 95% |
| EHC05 | The % of food premises inspections due that were carried out for other risk premises | 99% | 95% | 95% | 95% | 95% |
| EHC10 | Respond to all requests for service within 24 hours (Health and Safety Enforcement) | 100% | 95% | 95% | 95% | 95% |
| NI184 | Food establishments in the area which are broadly compliant with food hygiene law. | 93% | 91.2% | 91.2% | 91.2% | 91.2% |
| New – CP18 | Reduce the level of pavement parking in the District | New in 2017/18 | N/A | 20% | TBC, once baseline year completed | TBC, once baseline year completed. |
| New – CP20 | Reduce the sale of cars on verges and highways | New in 2017/18 | N/A | 20% | TBC, once baseline year completed | TBC, once baseline year completed |

The Head of Regulatory Services is responsible for the source data, data entry and checking the data. The purpose of collating this data is to ensure that our services improve.

| 2.2 | Projects See the Project Management Framework for further details |
| --- | --- |

| Project details | Project timescales |
| --- | --- |
| Project title | Proposed outcome | 2018/19 | 2019/20 | 2020/21 |
| Review of Statutory Notices and associated costs (specifically DM but could contribute to wider review both in Regulatory Services and corporately) | Reduction in costs whilst maintaining legislative requirements | Ongoing until end of 2018/19 |  |  |
| Comprehensive DM Procedure Manual (recommendation of Autumn 2017 audit) | Ensure consistency in processes | April 2018 (reviewed bi-annually) |  |  |
| Review of DM Consultation Letters sent | Ensure most efficient processes followed/reduction in paper and electronic communication/increasing ‘self service’ | Ongoing until end of 2018/19 |  |  |
| Developing and establishing a licensing pre application service | Recovery of costs and redirection of resources | Ongoing until end of 2018/19 |  |  |
| Transfer of Licensing and Environmental Health – case management data from M3 Northgate to Uniform | Improved joined up working and increased efficiencies in working practices | Case management data transferred end of 2017 but continued efficiencies in working practices to be realised through 2018/19 |  |  |
| Review of Council Parking Services | Provision of a cost neutral service. | Ongoing |  |  |
| Contract agreed between HBC and 7 LA’s (HA7), giving LA1 delegated authority to manage HBC on behalf of HA7 | LA1 to manage the contract, ensuring HBC is adhering to agreed service levels. LA1 to be signing decision notices and completion certificates on behalf of HA7. | April 2018 to have contract agreed with ongoing implementation | Ongoing | Ongoing |
| Pavement parking in District | Reduction in pavement parking in District – agreed Policy. | Continued formation and implementation of project proposals with other departments (joint working) | Continued implementation of agreed actions | Continued implementation of agreed actions |
| Reduce the sale of cars on verges and highways | Reduction in sale of vehicles on verges and highways in District – agreed Policy. | Continued formation and implementation of project proposals with other departments (joint working) | Continued implementation of agreed actions | Continued implementation of agreed actions |
| Support the Land Registry in transferring part of the Local Land Charges service. | Smooth transition of Local Land Charges provision to new agency with minimal customer disruption and continued maintenance of the data |  |  | Ongoing |
| Review processes for Local Land Charges Searches | Service resilience and efficiencies | Ongoing until end of 2018 |  |  |
| Review of processes for Street Naming and Numbering | Electronic service, resilience and efficiencies | Ongoing until end of 2018 |  |  |
| Developing EH service to provide a commercial food service to new businesses, including continuing to offer Primary Authority arrangements for large or established businesses | New pre-application advice service launched May 2016. Minimal uptake (one enquiry). Approaches to offer Primary Authority Agreements with existing businesses will be made subject to the appropriate skillset becoming established within the EH Commercial Team. |  |  | Ongoing (will be affected by staff resources) |
| Explore alternative means of providing the Commercial Environmental Health Service, in terms of partnerships or shared service within the HCC family of authorities or with neighbouring District Authorities | Reduction in costs (bearing in mind service generates little income) whilst maintaining mandatory performance. | To be investigated in 2018/19 | Potential commencement of partnerships/collaborative working in specialist areas |  |
| As recommended by the 2016 Annual Status Report (accepted by Defra in May 2017) to carry out a detailed assessment of nitrogen dioxide levels at the M25 J18 AQMA to ascertain whether this AQMA is still required in its current form. | Outcome unknown at present. AQMA likely to be retained but if not the requirement to produce and deliver an AQAP is removed, so it is worth investigating. | Investigations commence | Assessment to be commissioned |  |
| To continue AQ monitoring along the A412 at Mill End to ascertain the need, or otherwise, for a new AQMA at this location. | Early data obtained from the vicinity of Belfry House indicates that a detailed assessment may be required for nitrogen dioxide at this location. Relevant residential exposure at houses that front directly onto the highway will be considered. |  | Cumulative results obtained by end May 2018 will inform the next step | Ongoing |

| 2.3 | Risk Management Risk Management Strategy and guidance |
| --- | --- |

RISK REGISTER

| Service Plan: Regulatory Services 2017-2020 |
| --- |
| Risk Ref | Risk | Impact | Impact Classification | Likelihood Classification | Reason for Assessment |  |  |
|  | Brief Description – Title of Risk | See Impact Table | See Impact Table | See Likelihood Table | Use this box to describe how the score has been derived |  |  |
| a) Common Risks - shared across the whole section |
| 1 | Insufficient staff | Service Disruption | III | C | Staff numbers have been reduced over last three years. New and existing corporate projects cannot all be supported without increased staff resources. | Requires Treatment | Yes |
|  |  | Financial Loss | III |  |  | Last Review Date | 01/10/17 |
|  |  | Reputation | II |  |  | Next Milestone Date |  |
|  |  | Legal Implications | I |  |  | Next Review Date | 31/03/18 |
|  |  | People | I |  |  | Date Closed | -- |
| 2 | Total failure of ICT systems | Service Disruption | III | D | Delays in implementation of new software resulting in inefficiencies and affecting service levels. | Requires Treatment | Yes |
|  |  | Financial Loss | III |  |  | Last Review Date | 01/10/17 |
|  |  | Reputation | III |  |  | Next Milestone Date |  |
|  |  | Legal Implications | III |  |  | Next Review Date | 31/03/18 |
|  |  | People | III |  |  | Date Closed | -- |
| 3 | Loss of accommodation | Service Disruption | III | E | Could impact on service provision | Requires Treatment | Yes |
|  |  | Financial Loss | III |  |  | Last Review Date | 01/10/17 |
|  |  | Reputation | III |  |  | Next Milestone Date |  |
|  |  | Legal Implications | III |  |  | Next Review Date | 31/03/18 |
|  |  | People | III |  |  | Date Closed | -- |
| 4 | Fraudulent activity | Service Disruption | III | E | Fraud by officers, relating either to income, expenditure or stock. Potential through misreporting of income | Requires Treatment | Yes |
|  |  | Financial Loss | III |  |  | Last Review Date | 01/10/17 |
|  |  | Reputation | III |  |  | Next Milestone Date |  |
|  |  | Legal Implications | III |  |  | Next Review Date | 31/03/18 |
|  |  | People | III |  |  | Date Closed | -- |

| b) Regulatory Service Risks |
| --- |
| 5 | The parking programme may not be completed in full, due to resourcing and the consultative and iterative nature of the legal process for introducing parking restrictions and limited resources within the Council. | Service Disruption | II | C | Difficulties in recruiting Traffic Engineer role. Staffing restructure and award/commencement of parking enforcement service (April 2018) to new provider may affect service provision. | Requires Treatment | Yes |
|  |  | Financial Loss | II |  |  | Last Review Date | 01/10/17 |
|  |  | Reputation | II |  |  | Next Milestone Date |  |
|  |  | Legal Implications | II |  |  | Next Review Date | 31/03/18 |
|  |  | People | II |  |  | Date Closed | -- |
| 6 | Increase in workloads/major planning applications submitted. | Service Disruption | III | B | Current indicators show a continued increase in major applications | Requires Treatment | Yes |
|  |  | Financial Loss | III |  |  | Last Review Date | 01/10/17 |
|  |  | Reputation | III |  |  | Next Milestone Date |  |
|  |  | Legal Implications | III |  |  | Next Review Date | 31/03/18 |
|  |  | People | III |  |  | Date Closed | -- |
| 7 | Local Planning Authority placed in special measures allowing applicants to submit applications directly to Secretary of State. | Service Disruption | II | E | Planning application performance is currently significantly above thresholds for designation. New thresholds introduced for appeal decisions | Requires Treatment | Yes |
|  |  | Financial Loss | III |  |  | Last Review Date | 01/10/17 |
|  |  | Reputation | III |  |  | Next Milestone Date |  |
|  |  | Legal Implications | II |  |  | Next Review Date | 31/03/18 |
|  |  | People | III |  |  | Date Closed | -- |
| 8 | Disruption to services during transfer of part of Local Land Charges functions to Land Registry. | Service Disruption | III | B |  | Requires Treatment | Yes |
|  |  | Financial Loss | III |  |  | Last Review Date | 01/10/17 |
|  |  | Reputation | III |  |  | Next Milestone Date |  |
|  |  | Legal Implications | III |  |  | Next Review Date | 31/03/18 |
|  |  | People | III |  |  | Date Closed | -- |
| 9 | Insufficient staff and inadequate skills set | Service Disruption | III | C | New and existing departmental projects cannot all be supported, and service levels maintained, without increased staff resources. Experiencing difficulties in recruiting appropriately trained staff across all areas of the Service. | Requires Treatment | Yes |
|  |  | Financial Loss | III |  |  | Last Review Date | 01/10/17 |
|  |  | Reputation | III |  |  | Next Milestone Date |  |
|  |  | Legal Implications | III |  |  | Next Review Date | 31/03/18 |
|  |  | People | III |  |  | Date Closed | -- |
| 10 | Inaccuracy of appropriate data/records | Service Disruption | III | D | Particularly affecting property information on Uniform and ArcMap software. In process of designating specialist Officer within Council to maintain mapping systems Inadequate skills/failing IT | Requires Treatment | Yes |
|  |  | Financial Loss | II |  |  | Last Review Date | 01/10/17 |
|  |  | Reputation | III |  |  | Next Milestone Date |  |
|  |  | Legal Implications | III |  |  | Next Review Date | 31/03/18 |
|  |  | People | II |  |  | Date Closed | -- |
| 11 | Failure to agree measures to meet the £180K parking deficit and future parking income forecasts | Service Disruption | IV | D | A Parking Services Review is currently being undertaken | Requires Treatment | Yes |
|  |  | Financial Loss | IV |  |  | Last Review Date | 01/10/17 |
|  |  | Reputation | III |  |  | Next Milestone Date |  |
|  |  | Legal Implications | II |  |  | Next Review Date | 31/03/18 |
|  |  | People | II |  |  | Date Closed | -- |
| 12 | Near term Air Quality Action Plans not progressed | Service Disruption | III | E |  | Requires Treatment | Yes |
|  |  | Financial Loss | III |  |  | Last Review Date | 01/10/17 |
|  |  | Reputation | III |  |  | Next Milestone Date |  |
|  |  | Legal Implications | III |  |  | Next Review Date | 31/03/18 |
|  |  | People | III |  |  | Date Closed | -- |
| 13 | Long term Air Quality Action Plans not progressed | Service Disruption | II | C |  | Requires Treatment | Yes |
|  |  | Financial Loss | II |  |  | Last Review Date | 01/10/17 |
|  |  | Reputation | II |  |  | Next Milestone Date |  |
|  |  | Legal Implications | II |  |  | Next Review Date | 31/03/18 |
|  |  | People | II |  |  | Date Closed | -- |
| 14 | Local Authority placed in special measures for Gazetteer should we fall constantly below Below National Standard. | Service Disruption | II | E | Performance is generally above threshold but some issues with areas of matching due to levels of resource and authority wide records. | Requires Treatment | Yes |
|  |  | Financial Loss | III |  |  | Last Review Date | 01/10/17 |
|  |  | Reputation | III |  |  | Next Milestone Date |  |
|  |  | Legal Implications | II |  |  | Next Review Date | 31/03/17 |
|  |  | People | III |  |  | Date Closed | -- |

| Likelihood | A |  |  |  |  |  | Impact | Likelihood |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | B |  |  | 6, 8 |  |  | V = Catastrophic | A = ≥98% |
|  | C |  | 5, 13 | 1, 9, 11 |  |  | IV = Critical | B = 75% - 97% |
|  | D |  |  | 2, 10 |  |  | III = Significant | C = 50% - 74% |
|  | E |  |  | 3, 4, 7, 12, 14 |  |  | II = Marginal | D = 25% - 49% |
|  | F |  |  |  |  |  | I = Negligible | E = 3% - 24% |
|  |  | I | II | III | IV | V |  | F = ≤2% |
|  | Impact |  |  |

Version Control

| Version No. | Date | Reason for Update / Significant Changes | Made By |
| --- | --- | --- | --- |
| 1.0 | 11/10/17 | Draft prepared for Committee cycle | KR |