LEISURE, WELLBEING AND HEALTH COMMITTEE -

16 MARCH 2016

PART I - DELEGATED

5.	GET ACTIVE ACTION PLAN 2016-18

(CED)

1.	Summary

1.1	This report presents the Get Active Action Plan 2016-18 for member comment and adoption to support the achievement of the Three Rivers Physical Activity Strategy 2015-18.

2.	Details

2.1	At its meeting on 3 June 2015 the Committee agreed the Three Rivers Physical Activity Strategy 2015-18 (minute LW08/15 refers) and requested that officers developed an action plan to support its implementation.

2.2	Officers were also requested to seek endorsement of the Physical Activity Strategy by the Local Strategic Partnership. The Local Strategic Partnership meeting on 8 July 2015 endorsed the strategy and committed to working in partnership to achieve its priorities and targets.

2.3	Officers have drafted an action plan and consulted on this internally, and with some key partner agencies, including the Schools Sports Partnership, South West Herts Partnership (schools) and Hertsmere Leisure. The draft action plan is attached at Appendix 1.

2.4	Actions are indentified under the three strategic priorities of active people, active places and active together. Where actions overlap, they have been placed in the strategic priority area covering the largest element of the action.  Lead departments have been identified for the actions along with timescales and targets. Resource implications have been identified and in the main fall within existing resources. Where resources have not yet been identified this is indicated and further information will be brought back to the Committee once options have been explored.

2.5	If adopted, the action plan will be used to report on progress to the committee alongside key performance data indicators from the Physical Activity Strategy.

3.	Options/Reasons for Recommendation

3.1	For members to consider and adopt the action plan to support the Three Rivers Physical Activity Strategy 15-18.

4.	Policy/Budget Reference and Implications

4.1	The recommendations in this report are within the Council’s agreed policy and budgets.  The relevant policies are entitled:

Three Rivers Community Strategy

Three Rivers Strategic Plan 2016-18

4.2	The recommendations in this report relate to the achievement of the following performance indicators:

1 – to achieve a year on year reduction in the level of physical in activity of adults in Three Rivers (less than 30 minutes per week)

2 – to achieve a year on year increase in the number of adults who are active to the recommended level (150 minutes per week)

3 – to achieve a year on year increase in the number of adults participating in sport for 30 minutes per week.

4.3	The impact of the recommendations on this/these performance indicator(s) is:

To put in place the actions necessary to achieve the indicators.

5.	Financial, Legal, Staffing, Environmental, Community Safety, Customer Services Centre, and Communications & Website  Implications

5.1	None specific.

6.	Equal Opportunities Implications

6.1	Relevance Test

| Has a relevance test been completed for Equality Impact? | Yes |
| --- | --- |
| Did the relevance test conclude a full impact assessment was required? | No |

6.2	Impact Assessment

What actions were identified to address any detrimental impact or unmet need?

The strategy which the action plan supports seeks to address health inequalities in the District and no detrimental impact is identified.

7.	Public Health implications

7.1	The action plan seeks to address the public health priority of physical activity, recognised in the Hertfordshire Physical Activity Framework. Nearly a third (29%) of the adult population of the District are categorised as inactive, lower than the national and Hertfordshire averages.

8.	Risk Management and Health & Safety Implications

8.1	The Council has agreed its risk management strategy which can be found on the website at http://www.threerivers.gov.uk.  In addition, the risks of the proposals in the report have also been assessed against the Council’s duties under Health and Safety legislation relating to employees, visitors and persons affected by our operations.  The risk management implications of this report are detailed below.

8.2	The subject of this report is covered by the Community Partnerships and Community Services service plans.  Any risks resulting from this report will be included in the risk register and, if necessary, managed within these plans.

8.3	There are no risks to the Council in agreeing the recommendation.

8.4		The following table gives the risks that would exist if the recommendation is rejected, together with a scored assessment of their impact and likelihood:

| Description of Risk | Impact | Likelihood |
| --- | --- | --- |
| 1 | The priorities of the Community Strategy are not achieved through the Local Strategic Partnership | III | D |

8.5	The risk above is already included in a service plan:

| Description of Risk | Service Plan |
| --- | --- |
| 1 | The priorities of the Community Strategy are not achieved through the Local Strategic Partnership | Community Partnerships |

8.6	The above risks are plotted on the matrix below depending on the scored assessments of impact and likelihood, detailed definitions of which are included in the risk management strategy. The Council has determined its aversion to risk and is prepared to tolerate risks where the combination of impact and likelihood are plotted in the shaded area of the matrix. The remaining risks require a treatment plan.

| Likelihood | A |  |  |  |  |  | Impact | Likelihood |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | B |  |  |  |  |  | V = Catastrophic | A = >98% |
|  | C |  |  |  |  |  | IV = Critical | B = 75% - 97% |
|  | D |  |  | 1 |  |  | III = Significant | C = 50% - 74% |
|  | E |  |  |  |  |  | II = Marginal | D = 25% - 49% |
|  | F |  |  |  |  |  | I = Negligible | E = 3% - 24% |
|  |  | I | II | III | IV | V |  | F = <2% |
|  | Impact |  |  |

8.7	The risk above is a strategic risk already. Progress against the treatment plans for strategic risks is reported to the Policy and Resources Committee quarterly.  The effectiveness of all treatment plans are reviewed by the Audit Committee annually.

9.	Recommendation

9.1               That the Committee agrees the Get Active Action Plan.

9.2               That officers provide an annual update on progress against the action plan.

Report prepared by:	Andy Stovold, Head of Partnerships

# Data Quality

Data sources:

Sport England, Active people survey 2014

Public Health Outcomes Framework (2014)

Data checked by: Karl Stonebank, Partnerships Officer

Data rating:

| 1 | Poor |  |
| --- | --- | --- |
| 2 | Sufficient | ( |
| 3 | High |  |

APPENDICES / ATTACHMENTS

Appendix 1 – Get Active Action Plan 2016-18

# Appendix 1 - Three Rivers Get Active Action Plan 2016-2018

## Vision:

## “To reduce the levels of inactivity, increase regular participation and contribute to a healthier, more active Three Rivers.”

### We have set three strategic priorities, these are: Active People, Active Places, and Active Together.

| Strategic Priority 1- Active People: Encourage residents in Three Rivers to be active and healthy by enabling sport and physical activities to become a habit of life. |
| --- |
| Key Action | How will this be delivered | Timescale (if applicable) | Cost | Lead Department/ Officer | Targets |
| 1.1 Increase opportunities to take part in physical activity. | Increase opportunities to participate in affordable sport and physical activity via the District offer and leisure development | March 2018 | Officer Time Resources already allocated | Leisure Development Team | A 1% increase in physical activity amongst adults per year. |
| 1.2 Utilise physical activity and sport to prevent physical and mental ill health | Expand the current Three Rivers physical activity referral programme Active for Life to include alternative activities than just gym based sessions. Collaborate with mental health provision for targeted activity sessions. Social Prescribing of Arts – explore potential to expand the Arts referral scheme Increase the number of targeted health walks running across areas of deprivation providing an opportunity to access free activity. Introduce England Athletics 3-2-1 marked running routes into Three Rivers parks and open spaces. Promote and deliver yearly inclusion workshops for providers of physical activity through the Get Set Learn programme. | April 2016 March 2017 March 2017 March 2017 June 2016 April 2016 to March 2018 | Resources allocated through district offer. Resources allocated to mental health through district offer. Officer time Resources allocated through district offer Resources already allocated Resources already allocated | Physical Activity Referral Scheme and Projects Coordinator Leisure Projects Officer Community Arts Development Officer Active Communities Officer Sports Development Officer Leisure Projects Officer | Further activities developed and in regular use. Further activities developed and in regular use. To be determined, dependent on scheme Launch of 3 new health walks in South Oxhey, Mill End. 3-2-1 Route to be installed at Rickmansworth Aquadrome Delivery of Inclusion workshops 2 x year. |
| 1.3 Communicate the benefits of physical activity and opportunities. | Develop a Get Active Communications strategy Including: Create a Get Active section on the Three Rivers website Promote national, regional and local Get Active campaigns Make use of data to target inactive people Encourage residents to take the pledge to become more physically active. Encourage more people to introduce everyday activity to daily lifestyles Promote the change for life brand and a range of technologies to encouraging residents to increase physical activity levels. Encourage walking, cycling and sustainable travel into everyday life Promote allotments Promote the Herts Park App to residents. Promote Parkrun at South Oxhey and identify potential additional sites. Monitoring and evaluation of Get Active sessions with an annual report | June 2016 December 2016 March 2018 March 2018 March 2018 March 2018 March 2018 March 2018 March 2018 March 2018 March 2018 | Start up costs for Web Page, Officer Time to keep update. Officer Time Officer Time Officer Time Officer Time Officer Time Officer Time Officer Time Officer Time Officer Time Officer Time | Head of Community Partnerships / Sports Development Officer Marketing Manager/ Communications Officer Sports Development/ Active Communities Sports Development/ Active Communities Sports Development Officer Physical Activity Referral Project Coordinator/ Leisure Development team Leisure Development team. Principal Landscape Officer Sports Development Officer Sports Development Officer Leisure Development team. | Produce clear Communications Strategy Measure Number website visits Measure take up of Get Active Data informs decision making Measure numbers of pledges Brand products used in Communications Links provided on website Measure increased demand Residents to download and use park app Increased average attendance at Parkrun to 75 week. Report produced. |

| Strategic Priority 2- Active Places: Promote the design, development and use of environments that make it easier for people to participate in physical activity encouraging residents to be more active in every aspect of their day to day lives. |
| --- |
| Key Action | How will this be delivered | Timescale (if applicable) | Cost | Lead Officer | Targets |
| 2.1 Maximise the use of Three Rivers indoors and outdoor facilities | Conduct a sports facilities audit to provide accurate information on current levels of provision of sports facilities | March 2018 | Additional Cost – To be confirmed | Sports Development Officer | Facility Audit completed |
| 2.2 Increase access to and use of current green space | Promote volunteering opportunities in Three Rivers parks and open spaces assisting Park Ranger and Friends of park groups. | June 2016 onwards | Resource Implications for Marketing | Principal Landscape Officer/ Park Ranger | New volunteers recruited |
| 2.3 Encourage sustainable and active travel choices of all residents of Three Rivers. | Create a community cycle hub in Three Rivers Develop a network of safe, well sign posted and affordable routes to workplaces, schools, community facilities and services. Provide access to cycle training such as ‘Bikeability’ schemes for all ages. Explore and support ‘Park and Stride’ schemes | March 2018 March 2018 March 2017 March 2017 | Resources allocated through district Offer. To be determined Resources allocated through district Offer. Marketing cost of Flyers/ posters/ signage | Physical Activity Project Coordinator Senior Planning Officer Active Communities Officer/ Sports Development Officer Sports Development Officer | To increase residents moderate physical activity levels towards 150+ minutes per week Increase in number of cyclists Support the delivery 3 beginner cycle courses More children taking sustainable transport to school |

| Strategic Priority 3- Active Together: Working in partnerships across all sectors to consolidate and expand Three Rivers sport and physical activity opportunities enabling sport and physical activity to become a habit of daily lives. |
| --- |
| Key Action | How will this be delivered | Timescale (if applicable) | Cost | Lead Officer | Targets |
| 3.1 Working with Three Rivers employers and volunteers to create workplace environments and policies to provide physical activity and sport infrastructure | Encourage Three Rivers’ employers and workplace health champions to promote the workplace challenge to their workforce Promote health awareness events and campaigns across Three Rivers workplaces. Continue to offer coaching bursary scheme to raise the standard of sports coaching and to supporting coaches/volunteers to enhance their skills needed to offer great coaching sessions. | March 2018 March 2018 March 2018 | Officer time/ Nominal cost marketing Officer time Resources already allocated | Sports Development Officer/ Active Communities Officer Partnerships Officer Sports Development Officer | Measurable increase of Three Rivers business signed up to Scheme/ tournament Monitor changes in healthy lifestyles 10 Coaches/volunteers access coaching bursary |
| 3.2 Work with Watford and Three Rivers School Sports Partnerships and South West Herts School Partnership | Work with schools to: Promote Park and Stride Target physical activity at less active children Measure physical activity through the health related behaviour survey | March 2018 March 2017 March 2018 | Officer time Officer time Officer time | Sports Development Officer Sports Development Officer Head of Community Partnerships | 1x Junior school and 1x Senior school take up of scheme. Deliver targeted scheme Data captured in future surveys of school age children |
| 3.3 Identify a new role for Three Rivers Community Sport Network (CSN) to help increase physical activity levels | Work with Three Rivers Community Sports Network (CSN) to increase awareness of physical activity in the district | March 2018 | Officer time | Sports Development Officer | Increase Clubs attending Sports Forum |
| 3.4 Identify development targets for partner agencies to increase participation rates | Leisure Services Provider(s) set clear Performance Indicators. | March 2018 | Officer time | Performance and Contracts Monitoring Officer | Increase in physical activity rates |