COMMUNITY SERVICES - ENVIRONMENTAL PROTECTION SERVICE PLAN

2017 - 2020

CONTENTS

| Section | Item | Page |
| --- | --- | --- |
|  | Introduction | 3 |
| 1 | Inputs | 3 |
| 1.1 | Budgets | 3 |
| 2 | Outputs and Outcomes | 4 |
| 2.1 | Performance management | 5 |
| 2.2 | Projects | 6 |
| 2.3 | Risk Management | 8 |
|  | Version Control | 14 |

INTRODUCTION

The progress of this service plan will be monitored in the following ways:

- Through regular discussion at departmental management team (DMT) and Section Heads meetings and logged in the version control section of this document

- Performance indicator monitoring by the Council’s Management Board on a quarterly basis

- By Committee reports twice a year (at the end of quarters two and four)

Service Plans will be formally updated on an annual basis, taking into account internal and external influences arising from monitoring arrangements throughout the year.

SECTION 1:	INPUTS

| 1.1 | Budgets |
| --- | --- |

|  | 2017/18 | 2018/19 | 2019/20 |
| --- | --- | --- | --- |
|  | Latest | Latest | Latest |
| Net Cost of Service (Direct Cost / Income only) | £ | £ | £ |
| Environmental Protection | 4,208,255 | 4,205,115 | 4,218,915 |

Further financial analysis can be found by using this link

SECTION 2:	OUTPUTS AND OUTCOMES

| 2.1 | Performance management |
| --- | --- |

2.1.1	Contribution to the Councils’ Strategic Aims and Objectives

| Strategic Plan Priority theme | Strategic Plan objective (inc. ref) | Measure (including the reference) | Target |
| --- | --- | --- | --- |
| Safety and Wellbeing | 1.3.1 Improve and facilitate access to leisure and recreational activities for adults | CP02 – Satisfaction with quality/provision of parks and open spaces | 93% |
| Clean and Green | 2.1.1 Maintain the number of accredited open spaces, parks and woodland areas. 2.1.2 Minimise waste and optimise recycling. 2.1.4 Maintain clean streets. | LL34 – Maintain Green Flag Accreditation EP10 – Increase the percentage of household waste sent for reuse, recycling and composting. EP06 – Decrease the tonnage of household waste collected and sent to landfill CP03 – The percentage of respondents who are satisfied with refuse collection CP04 – The percentage of respondents who are satisfied with doorstep recycling CP01 – Satisfaction with ‘keeping public land clear of litter and refuse’ | 3 60% <15,000 tonnes 76% 76% 78% |
| Customer Service | - We will strive to improve and maintain service standards for all services | EH06 Respond to all requests for service within 14 days (animal control). EH07 – Respond to all requests for service within 14 days (pest control) New indicator (to replace EP07) EP11 – Percentage of collections made on the correct day | 98% 98% 95% |

2.1.2 	Performance indicators

Performance indicators are used to aid the decision making process as well as assess the efficiency and effectiveness of service delivery. The data that we use must be accurate, reliable and timely. To meet these requirements we have adopted the Audit Commission’s Standards for Better Data Quality. Further details of the Council’s commitment to data quality can be found in the Strategic Plan.

| Ref | Description | 2015/16 actual Actual | 2016/17 Target (Current year) | 2017/18 Target (Next year) | 2018/19 Target | 2019/20 Target |
| --- | --- | --- | --- | --- | --- | --- |
| - EH06 | - Respond to all requests for service within 24 hours (animal control) | - 98% | - 98.00% | - 98% | - 98% | - 98% |
| - EH07 | Respond to all requests for service within 14 days (pest control) | 98% | - 98.00% | - 98% | - 98% | - 98% |
| EP01 | Percentage household waste recycled | 28.90% | 34.00% | 28% | 28% | 28% |
| EP02 | Percentage household waste composted To be deleted after 2016/17 | 26.97% | 26.00% | 26% | 26% | 26% |
| EP03 | The kg of household waste collected per head per annum | 325.79 | 390kgs | 390kgs | 390kgs | 390kgs |
| EP04 | The Percentage change in Kg per head from the previous year | 0.1% | 0.00% | 0% | 0% | 0% |
| EP06 | Tonnes of Household waste collected and sent to landfill | 12,648 tonnes | 15,000.00 | 15,000 tonnes | 15,000 tonnes | 15,000 tonnes |
| EP08 | Cost of Waste collection per household | £58.74 | £60.00 | £60.00 | £60.00 | £60.00 |
| EP 09 (NI 191) | Residual household waste per household | 364 kg | 400kgs | 400kg | 400kg | 400kg |
| EP 10 (NI 192) | Percentage of household waste sent for reuse, recycling and composting | 61.73% | 60.00% | 60% | 60% | 60% |
| EP11 | Percentage of collections made on the correct day (new indicator in 2017/18 to replace EP07) | N/A | New | 95% | 95% | 95% |
| EP12 | Percentage of eligible properties signed up to the Garden Waste scheme | N/A | New for 2017-20 | 70% | 70% | 70% |
| New - EP13 | Manage the behaviour of dogs in our parks and open spaces | N/A | New for 2017-20 | New – 5% reduction on YTD | New – 7% reduction on YTD | New – 9% reduction on YTD |
| CP01 | Satisfaction with ‘keeping public land clear of litter and refuse’ | 77% | 77.00% | 78% | 78% | 78% |
| CP02 | Satisfaction with parks and open spaces | 93% | 93.00% | 93% | 93% | 93% |
| CP03 | Satisfaction with refuse collection | 82% | 76.00% | 76% | 80% | 80% |
| CP04 | The percentage of respondents who are satisfied with doorstep recycling | 85% | 76.00% | 76% | 80% | 80% |

The Environmental Projects Officer is responsible for the source data, data entry and checking the data. The purpose of collating this data is to ensure that our services improve. It should be noted there will always be some variation between the figures reported on PDC and those recorded on Waste Data Flow. This is down to timescale of input and the way the calculations work i.e Waste Data Flow takes into account contamination whereas PDC is based on collected tonnages.

| 2.2 | Projects |
| --- | --- |

| - Project details |  | - Project timescales |  |  |
| --- | --- | --- | --- | --- |
| - Project title | - Proposed outcome | 2017/18 | 2018/19 | 2019/20 |
| Reduction of Residual waste | Gain Member approval to introduce a scheme to further reduce residual waste. | September 2017 |  |  |
| Cemetery carpark | To lay a new carpark at Woodcock Hill cemetery and layout the formal cemetery extension |  |  |  |
| In conjunction with other services (Council and External) to deliver on the new parking related enforcement objectives | To reduce pavement parking and the sales of vehicles on the Highway | TBD |  |  |
| Trade waste / recycling | Review the strategy on trade waste/recycling with a view to being competitive in the market place to increase and bring in new business. | On-going |  |  |
| Collective | Develop this software to increase efficiencies and reporting of the functions carried out by EP. | On-going |  |  |
| Direct Debits | To offer customers a more flexible and efficient way of doing business with us. | TBD |  |  |
| Vehicle maintenance tender | To ensure the fleet is maintained to safe working standards under the Vehicle Operating Licence | Jan 17 start |  |  |

Note: TRDC is part Herts Waste Partnership (HWP) and officers from Environmental Protection are very much involved with the various groups as part of this including WasteAware, Heads of Waste, Directors and the Fly Tipping Group.  Officers are involved with projects from these groups on an on-going basis.

| 2.3 | Risk Management |
| --- | --- |

RISK REGISTER

| Service Plan: Environmental Protection 2017-20 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Ref | Risk | Impact | Impact Classification | Likelihood Classification | Reason for Assessment |  |  |
|  | Brief Description – Title of Risk | See Impact Table | See Impact Table | See Likelihood Table | Use this box to describe how the score has been derived |  |  |
| 1 | Insufficient staff | Service Disruption | II | E | If several key frontline staff were ill / injured for a period of time, the Council’s agency costs could rise substantially | Requires Treatment | No |
|  |  | Financial Loss | III |  |  | Last Review Date | 01/04/16 |
|  |  | Reputation | II |  |  | Next Milestone Date | 09/03/17 |
|  |  | Legal Implications | I |  |  | Next Review Date | 01/04/17 |
|  |  | People | I |  |  | Date Closed |  |
| 2 | Total failure of ICT systems | Service Disruption | II | E | Would effect office staff and missed bins etc, but operational staff could continue with work | Requires Treatment | No |
|  |  | Financial Loss | I |  |  | Last Review Date | 01/04/16 |
|  |  | Reputation | II |  |  | Next Milestone Date | 09/03/17 |
|  |  | Legal Implications | I |  |  | Next Review Date | 01/04/17 |
|  |  | People | I |  |  | Date Closed |  |
| 3 | Loss of accommodation | Service Disruption | II | E | Although it would be difficult for office based staff, the frontline service could still continue. | Requires Treatment | No |
|  |  | Financial Loss | II |  |  | Last Review Date | 01/04/16 |
|  |  | Reputation | II |  |  | Next Milestone Date | 09/03/17 |
|  |  | Legal Implications | I |  |  | Next Review Date | 01/04/17 |
|  |  | People | I |  |  | Date Closed |  |
| 4 | Fraudulent activity | Service Disruption | I | E | Any fraudulent activity, such as the taking of money, to perform functions is kept to a minimum by training and monitoring | Requires Treatment | No |
|  |  | Financial Loss | I |  |  | Last Review Date | 01/04/16 |
|  |  | Reputation | II |  |  | Next Milestone Date | 09/03/17 |
|  |  | Legal Implications | II |  |  | Next Review Date | 01/04/17 |
|  |  | People | I |  |  | Date Closed |  |

| Risk Ref | Risk | Impact | Impact Classification | Likelihood Classification |  | Reason for Assessment |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5 | Whole fleet lost (accident / fire / theft). | Service Disruption | III | F |  | Cost of replacing fleet even if insured high, also hire charge for prolonged time, however very unlikely for whole fleet to be lost | Requires Treatment | No |  |
|  |  | Financial Loss | IV |  |  |  | Last Review Date | 01/04/16 |  |
|  |  | Reputation | III |  |  |  | Next Milestone Date | 09/03/17 |  |
|  |  | Legal Implications | II |  |  |  | Next Review Date | 01/04/17 |  |
|  |  | People | I |  |  |  | Date Closed |  |  |
| 6 | Long period of Extreme weather / snow | Service Disruption | III | E |  | If Extreme weather prolonged service could be disrupted for long period of time, as vehicles very dangerous to drive on ice | Requires Treatment | No |  |
|  |  | Financial Loss | II |  |  |  | Last Review Date | 01/12/16 |  |
|  |  | Reputation | III |  |  |  | Next Milestone Date | 09/03/17 |  |
|  |  | Legal Implications | I |  |  |  | Next Review Date | 01/12/17 |  |
|  |  | People | II |  |  |  | Date Closed |  |  |
| 7 | Fuel shortage | Service Disruption | III | E |  | If there was a prolonged fuel shortage the Service continuity plan would be invoked, which would involve the dropping of some services | Requires Treatment | No |  |
|  |  | Financial Loss | II |  |  |  | Last Review Date | 01/10/16 |  |
|  |  | Reputation | III |  |  |  | Next Milestone Date | 09/03/17 |  |
|  |  | Legal Implications | I |  |  |  | Next Review Date | 01/10/17 |  |
|  |  | People | I |  |  |  | Date Closed |  |  |
| 8 | H&S or DTP action | Service Disruption | III | F |  | H&S or DTP action could prevent services operating. Good training and procedures minimise the likelihood of this happening | Requires Treatment | No |  |
|  |  | Financial Loss | III |  |  |  | Last Review Date | 01/04/16 |  |
|  |  | Reputation | IV |  |  |  | Next Milestone Date | 09/03/17 |  |
|  |  | Legal Implications | IV |  |  |  | Next Review Date | 01/04/17 |  |
|  |  | People | I |  |  |  | Date Closed |  |  |
| 9 | Decrease in recycling rate | Service Disruption | I | E |  | The Council is hoping to maximise recycling, but tonnages have reduced within the current financial climate. | Requires Treatment | No |  |
|  |  | Financial Loss | II |  |  |  | Last Review Date | 01/10/16 |  |
|  |  | Reputation | II |  |  |  | Next Milestone Date | 09/03/17 |  |
|  |  | Legal Implications | I |  |  |  | Next Review Date | 01/10/17 |  |
|  |  | People | I |  |  |  | Date Closed |  |  |
| 10 | Serious accident occurs due to vehicle movements at Batchworth Depot | Service Disruption | II | F | Stringent H&S procedures have minimised the likelihood of this occurring, however if it were to the impact could be catastrophic |  | Requires Treatment | Yes |  |
|  |  | Financial Loss | III |  |  |  | Last Review Date | 01/04/16 |  |
|  |  | Reputation | III |  |  |  | Next Milestone Date | 09/03/17 |  |
|  |  | Legal Implications | IV |  |  |  | Next Review Date | 01/04/17 |  |
|  |  | People | IV |  |  |  | Date Closed |  |  |

| Risk Ref | Risk |  | Impact | Impact Classification | Likelihood Classification | Reason for Assessment |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 11 | Serious accident due to staff operating machinery incorrectly |  | Service Disruption | II | F | The likelihood of this occurring has been mitigated by providing training and PPE. | Requires Treatment | No |
|  |  |  | Financial Loss | I |  |  | Last Review Date | 01/10/16 |
|  |  |  | Reputation | II |  |  | Next Milestone Date | 09/03/17 |
|  |  |  | Legal Implications | I |  |  | Next Review Date | 01/04/17 |
|  |  |  | People | III |  |  | Date Closed |  |
| 12 | Increased complaints |  | Service Disruption | II | E | The complaint monitoring procedures highlights repetitive complaints and enables officers to address the problem | Requires Treatment | No |
|  |  |  | Financial Loss | I |  |  | Last Review Date | 01/04/16 |
|  |  |  | Reputation | II |  |  | Next Milestone Date | 09/03/17 |
|  |  |  | Legal Implications | I |  |  | Next Review Date | 01/04/17 |
|  |  |  | People | I |  |  | Date Closed |  |
| 13 | Customers contaminate recycling bins in attempt to dispose of more general waste | Service Disruption |  | III | B | Officers try to prevent this by enforcing through the issuing of Fixed Penalty Notices | Requires Treatment | Yes |
|  |  | Financial Loss |  | III |  |  | Last Review Date | 01/12/16 |
|  |  | Reputation |  | III |  |  | Next Milestone Date | 09/03/17 |
|  |  | Legal Implications |  | II |  |  | Next Review Date | 01/12/17 |
|  |  | People |  | I |  |  | Date Closed |  |
| 14 | Increased flytipping | Service Disruption |  | I | E | Effective enforcement should keep flytipping to a minimum. | Requires Treatment | No |
|  |  | Financial Loss |  | II |  |  | Last Review Date | 01/04/16 |
|  |  | Reputation |  | II |  |  | Next Milestone Date | 09/03/17 |
|  |  | Legal Implications |  | II |  |  | Next Review Date | 01/04/17 |
|  |  | People |  | I |  |  | Date Closed |  |
| 15 | Commuted sum insufficient to cover future maintenance costs | Service Disruption |  | I | D | Officers make every effort to calculate correct commuted sum. | Requires Treatment | No |
|  |  | Financial Loss |  | II |  |  | Last Review Date | 01/10/16 |
|  |  | Reputation |  | I |  |  | Next Milestone Date | 09/03/17 |
|  |  | Legal Implications |  | I |  |  | Next Review Date | 01/10/17 |
|  |  | People |  | I |  |  | Date Closed |  |
| 16 | TRDC compelled not to act in its own interests by majority of Partnership. |  | Service Disruption | I | E | TRDC would always consider its own interests at any HWP meeting. | Requires Treatment | No |
|  |  |  | Financial Loss | II |  |  | Last Review Date | 01/10/16 |
|  |  |  | Reputation | II |  |  | Next Milestone Date | 09/03/17 |
|  |  |  | Legal Implications | I |  |  | Next Review Date | 01/10/17 |
|  |  |  | People | I |  |  | Date Closed |  |

| Risk Ref | Risk |  | Impact |  | Impact Classification |  | Likelihood Classification | Reason for Assessment |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 17 | Costs increase above budgets |  | Service Disruption |  | I |  | E | Careful budget monitoring should stop this from occurring. | Requires Treatment | No |  |
|  |  |  | Financial Loss |  | II |  |  |  | Last Review Date | 01/12/15 |  |
|  |  |  | Reputation |  | II |  |  |  | Next Milestone Date | 09/03/17 |  |
|  |  |  | Legal Implications |  | I |  |  |  | Next Review Date | 01/12/17 |  |
|  |  |  | People |  | I |  |  |  | Date Closed |  |  |
| 18 | Member of the public injured |  | Service Disruption |  | II |  | F | Stringent H&S checks minimise the likelihood of this happening | Requires Treatment | No |  |
|  |  |  | Financial Loss |  | III |  |  |  | Last Review Date | 01/04/16 |  |
|  |  |  | Reputation |  | III |  |  |  | Next Milestone Date | 09/03/17 |  |
|  |  |  | Legal Implications |  | III |  |  |  | Next Review Date | 01/04/17 |  |
|  |  |  | People |  | III |  |  |  | Date Closed |  |  |
| 19 | Maintenance falls below required standard |  | Service Disruption |  | I |  | E | Effective contract monitoring minimises the likelihood of this happening. | Requires Treatment | No |  |
|  |  |  | Financial Loss |  | I |  |  |  | Last Review Date | 01/04/16 |  |
|  |  |  | Reputation |  | III |  |  |  | Next Milestone Date | 09/03/17 |  |
|  |  |  | Legal Implications |  | II |  |  |  | Next Review Date | 01/04/17 |  |
|  |  |  | People |  | I |  |  |  | Date Closed |  |  |
| 20 | AFM withdrawn by HCC |  | Service Disruption |  | I |  | F | Linked into partnership agreement | Requires Treatment | No |  |
|  |  |  | Financial Loss |  | III |  |  |  | Last Review Date | 01/04/16 |  |
|  |  |  | Reputation |  | I |  |  |  | Next Milestone Date | 09/03/17 |  |
|  |  |  | Legal Implications |  | I |  |  |  | Next Review Date | 01/04/17 |  |
|  |  |  | People |  | I |  |  |  | Date Closed |  |  |
| 21 | Crews unable to complete Work |  | Service Disruption |  | II |  | E | This is mitigated by running spare vehicles to shuttle when crews are working longer hours | Requires Treatment |  | No |
|  |  |  | Financial Loss |  | II |  |  |  | Last Review Date |  | 01/04/16 |
|  |  |  | Reputation |  | I |  |  |  | Next Milestone Date |  | 09/03/17 |
|  |  |  | Legal Implications |  | I |  |  |  | Next Review Date |  | 01/04/17 |
|  |  |  | People |  | I |  |  |  | Date Closed |  |  |
| 22 | Revenue for sale of materials decreases thereby not covering costs | Service Disruption |  | III |  | D |  | Long-term Contracts and HWP procurement ensuring economies of scale | Requires Treatment |  | No |
|  |  | Financial Loss |  | II |  |  |  |  | Last Review Date |  | 01/05/16 |
|  |  | Reputation |  | III |  |  |  |  | Next Milestone Date |  | 09/03/17 |
|  |  | Legal Implications |  | II |  |  |  |  | Next Review Date |  | 01/05/17 |
|  |  | People |  | I |  |  |  |  | Date Closed |  |  |

| Risk Ref | Risk |  | Impact |  | Impact Classification |  | Likelihood Classification | Reason for Assessment |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 23 | Public satisfaction decreases | Service Disruption |  | III |  | D |  | Officers working in partnership with HWP to find optimum solution | Requires Treatment | No |
|  |  | Financial Loss |  | II |  |  |  |  | Last Review Date | 01/10/16 |
|  |  | Reputation |  | III |  |  |  |  | Next Milestone Date | 09/03/17 |
|  |  | Legal Implications |  | II |  |  |  |  | Next Review Date | 01/10/17 |
|  |  | People |  | I |  |  |  |  | Date Closed |  |
| 24 | Insufficient grit for prolonged period of time | Service Disruption |  | III |  | C |  | TRDC have entered into arrangement with HCC | Requires Treatment | Yes |
|  |  | Financial Loss |  | II |  |  |  |  | Last Review Date | 01/12/16 |
|  |  | Reputation |  | III |  |  |  |  | Next Milestone Date | 09/03/17 |
|  |  | Legal Implications |  | II |  |  |  |  | Next Review Date | 01/12/17 |
|  |  | People |  | I |  |  |  |  | Date Closed |  |
| 25 | Routine inspections of play equipment | Service Disruption |  | III |  | E |  | Failure to assess adequately could result in injury | Requires Treatment | No |
|  |  | Financial Loss |  | II |  |  |  |  | Last Review Date | 01/01/16 |
|  |  | Reputation |  | III |  |  |  |  | Next Milestone Date | 09/03/17 |
|  |  | Legal Implications |  | II |  |  |  |  | Next Review Date | 01/01/17 |
|  |  | People |  | I |  |  |  |  | Date Closed |  |
| 26 | Level of charges affects take up of service | Service Disruption |  | I |  | C |  | Without appropriate market testing a change to fees and charges could affect service take up | Requires Treatment | No |
|  |  | Financial Loss |  | II |  |  |  |  | Last Review Date | 01/01/16 |
|  |  | Reputation |  | I |  |  |  |  | Next Milestone Date | 09/03/17 |
|  |  | Legal Implications |  | I |  |  |  |  | Next Review Date | 01/01/17 |
|  |  | People |  | I |  |  |  |  | Date Closed |  |

| Likelihood | A |  |  |  |  |  | Impact | Likelihood |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | B |  | 13 |  |  |  | V = Catastrophic | A = ≥98% |
|  | C | 26 | 24 |  |  |  | IV = Critical | B = 75% - 97% |
|  | D | 15 | 22, 23, |  |  |  | III = Significant | C = 50% - 74% |
|  | E | 2,4, 9,12, 16, 21, | 1, 3, 6, 7,14,17, 19, 25, |  |  |  | II = Marginal | D = 25% - 49% |
|  | F |  | 11, 20 | 5,8, 18 | 10 |  | I = Negligible | E = 3% - 24% |
|  |  | I | II | III | IV | V |  | F = ≤2% |
|  | Impact |  |  |  |  |  |  |  |

Version Control

Example

| Version No. | Date | Reason for Update / Significant Changes | Made By |
| --- | --- | --- | --- |
| 0.1 | 09/10/15 | Initial draft completed | GG/AP |
| 1.3 | 29/09/2016 | Amendments to most sections | JP/GG |
| 1.4 | 3/10/16 | Updated a number of risks | JP |
| 1.5 | 04/09/2016 | Added current year targets to PIs | GG |
| 1.6 | 11/10/16 | Updated risk register and impact/likelihood table | JP |
| 1.7 | 12/10/06 | Update to projects | JP |
| 1.8 | 13/10/16 | Update to projects | JP |
| 1.9 | 09/02/2017 | Added budget info | GG |