Agenda Item 12a

COMMUNITY PARTNERSHIPS SERVICE PLAN

2016 - 2019

CONTENTS

| Section | Item | Page |
| --- | --- | --- |
|  | Introduction | 3 |
| 1 | Inputs | 3 |
| 1.1 | Budgets | 3 |
| 2 | Outputs and Outcomes | 5 |
| 2.1 | Performance management | 5 |
| 2.2 | Projects | 8 |
| 2.3 | Risk Management | 9 |
|  | Version Control | 12 |

INTRODUCTION

The progress of this service plan will be monitored in the following ways:

- Through regular discussion at departmental management team (DMT) and Section Heads meetings and logged in the version control section of this document

- Performance indicator monitoring by the Council’s Management Board on a quarterly basis

- By Committee reports twice a year (at the end of quarters two and four)

Service Plans will be formally updated on an annual basis, taking into account internal and external influences arising from monitoring arrangements throughout the year.

SECTION 1:	INPUTS

| 1.1 | Budgets |
| --- | --- |

|  | 2016/17 Latest | 2017/18 Latest | 2018/19 Latest |
| --- | --- | --- | --- |
|  | £ | £ | £ |
| Net Cost of Service (Direct cost / Income Only) | 747,510 | 751,160 | 754,230 |

Further financial analysis can be found by using this link

SECTION 2:	OUTPUTS AND OUTCOMES

| 2.1 | Performance management |
| --- | --- |

2.1.1	Contribution to the Councils’ Strategic Aims and Objectives

| Strategic Plan Priority theme | Strategic Plan objective (inc. ref) | Measure (including the reference) | Target |
| --- | --- | --- | --- |
| Safety and Wellbeing | 1.1.1 Reduce anti-social behaviour and crime | CP45 Customer Satisfaction with Anti Social Behaviour Service CP16 – No. of new families supported by Thriving Families in Three Rivers. CP14 – No. of ASB incidents (reported to the Police) | 80.00% 29 TBC by Community Safety Partnership |
|  | 1.2.1 Ensure the safety of people in the district. | CP07 The percentage of people who agree that local public services are working to make the area safer | 85.00% |
|  | 1.3.1 Improve and facilitate access to leisure and recreational activities for adults. | CP02 Satisfaction with quality/provision of parks and open spaces | 93.00% |
|  | 1.3.5 Work with the Community and Voluntary sector to meet the needs of local communities | CP26 Funding to the community and voluntary sector, through leverage, officer advice, match funding and external grants | £50,000 |
| Clean and Green | 2.1.2 Minimise waste and optimise recycling. | CP03 – The percentage of respondents who are satisfied with refuse collection CP04 – The percentage of respondents who are satisfied with doorstep recycling | 82.00% 86.00% |
|  | 2.1.4 Maintain Clean Streets | CP01 – Satisfaction with ‘keeping public land clear of litter and refuse’ | 79.00% |
| Economic Prosperity | 3.2.1 Improve access to benefits | CP27 – No. of clients supported by the CAB service in Three Rivers. | 9,000 |
| Customer Service | 4.1.2 We will strive to improve and monitor customer satisfaction | CP05 – Perception of satisfaction with Three Rivers District Council | 73.00% |
|  | 4.2.1 We will manage our financial resources to deliver value for money | The percentage of people who agree that local public services: …promote the interests of local residents (CP09) …act on the concerns of local residents (CP10) …treat all types of people fairly (CP11) CP46 The extent to which local people agree the Council provides value for money | 68.00% 70.00% 90.00% 56.00% |

2.1.2 	Performance indicators

See Data Quality Strategy for further details

Performance indicators are used to aid the decision making process as well as assess the efficiency and effectiveness of service delivery. The data that we use must be accurate, reliable and timely. To meet these requirements we have adopted the Audit Commission’s Standards for Better Data Quality. Further details of the Council’s commitment to data quality can be found in the Strategic Plan.

| Ref | Description | 2014/15 Actual | 2015/16 Target (Current year) | 2016/17 Target (Next year) | 2017/18 Target | 2018/189 Target |
| --- | --- | --- | --- | --- | --- | --- |
| CP01 | Satisfaction with keeping public land clear of litter and refuse | 77.00% | 78.00% | 79.00% | 79.00% | 79.00% |
| CP02 | Satisfaction with quality/provision of parks and open spaces | 93.00% | 93.00% | 93.00% | 93.00% | 93.00% |
| CP03 | Satisfaction with refuse collection | 82.00% | 82.00% | 82.00% | 83.00% | 83.00% |
| CP04 | Satisfaction with doorstep recycling | 85.00% | 86.00% | 86.00% | 87.00% | 87.00% |
| CP05 | Perception of satisfaction with Three Rivers District Council | 78.00% | 73.00% | 73.00% | 74.00% | 74.00% |
| CP07 | The percentage of people who agree that local public services are working to make the area safer | 84.00% | 85.00% | 85.00% | 85.00% | 85.00% |
| CP09 | The percentage of people who agree that local public services promote the interests of local residents | 72.00% | 68.00% | 68.00% | 68.00% | 68.00% |
| CP10 | The percentage of people who agree that local public services act on the concerns of local residents | 71.00% | 70.00% | 70.00% | 70.00% | 70.00% |
| CP11 | The percentage of people who agree that local public services treat all types of people fairly | 92.00% | 90.00% | 90.00% | 90.000% | 90.00% |
| CP14 | No. of ASB incidents (reported to the Police) | Q1 429 Q2 427 Q3 365 Q4 326 | Q1 420 Q2 418 Q3 358 Q4 320 | TBC | TBC | TBC |
| CP16 | No of new families supported by Thriving Families | 19 | 30 | 30 | 30 | 30 |
| CP22 | Satisfaction with sports and leisure facilities | 90.00% | 88.00% | 89.00% | 90.00% | 90.00% |
| CP26 | Funding to the Community and Voluntary Sector, through leverage, match funding and grants | £83,720 | £50,000 | £50,000 | £50,000 | £50,000 |
| CP39 | Customer satisfaction with Community Partnerships Unit | 90.00% | 90.00% | 90.00% | 90.00% | 90.00% |
| CP45 | Customer satisfaction with Anti Social Behaviour Service | 94.25% | 80.00% | 80.00% | 80.00% | 80.00% |
| CP46 | The perception of value for money from Three Rivers Council | 59.00% | 56.00% | 56.00% | 56.00% | 56.00% |
| CP27 | No. of clients supported by the CAB service in Three Rivers. | N/A – new in 2015/16 | 9000 | 9000 | 9000 | 9000 |

The Head of Community Partnerships is responsible for the source data, data entry and checking the data. The purpose of collating this data is to ensure that our services improve.

| 2.2 | Projects See the Project Management Framework for further details |
| --- | --- |

| Project details | Project timescales |
| --- | --- |
| Project title | Proposed outcome | 2016/17 | 2017/18 | 2018/19 |
| Adults with Complex Needs | Delivery of pilot in Three Rivers of an intensive support service for Adults with complex needs to reduce footprint on existing service use patterns and costs. | Project started April 2015 | Project Ends March 2017 |  |
| Public Health Offer | Delivery of projects and performance monitoring data on the Public Health District Offier Programme. | Project Started September 2014 and ends September 2016 |  |  |

| 2.3 | Risk Management |
| --- | --- |

RISK REGISTER

| Service Plan: Community Partnerships 2016-2019 |
| --- |
| Risk Ref | Risk | Impact | Impact Classification | Likelihood Classification | Reason for Assessment |  |  |
|  | Brief Description – Title of Risk | See Impact Table | See Impact Table | See Likelihood Table | Use this box to describe how the score has been derived |  |  |
| a) Common Risks - shared across the whole section |
| 1 | Insufficient staff | Service Disruption | II | E | Staff numbers have been reduced over last two years. New corporate projects cannot all be supported without temporary staff. | Requires Treatment | No |
|  |  | Financial Loss | II |  |  | Last Review Date | 05/10/15 |
|  |  | Reputation | II |  |  | Next Milestone Date | 1/3/16 |
|  |  | Legal Implications | - |  |  | Next Review Date | 31/03/16 |
|  |  | People | II |  |  | Date Closed |  |
| 2 | Total failure of ICT systems | Service Disruption | III | E | Critical systems SafetyNet for ASB | Requires Treatment | Yes |
|  |  | Financial Loss |  |  |  | Last Review Date | 05/10/15 |
|  |  | Reputation | II |  |  | Next Milestone Date | 1/3/16 |
|  |  | Legal Implications |  |  |  | Next Review Date | 31/03/16 |
|  |  | People | III |  |  | Date Closed |  |
| 3 | Loss of accommodation | Service Disruption | III | E | Could impact on service to high risk families. | Requires Treatment | Yes |
|  |  | Financial Loss | I |  |  | Last Review Date | 05/10/15 |
|  |  | Reputation | II |  |  | Next Milestone Date | 1/3/16 |
|  |  | Legal Implications | I |  |  | Next Review Date | 31/03/16 |
|  |  | People | III |  |  | Date Closed |  |
| 4 | Fraudulent activity | Service Disruption | III | E | No income managed. Grants managed and some petty cash for family casework. | Requires Treatment | Yes |
|  |  | Financial Loss | III |  |  | Last Review Date | 05/10/15 |
|  |  | Reputation | IV |  |  | Next Milestone Date | 1/3/16 |
|  |  | Legal Implications | IV |  |  | Next Review Date | 31/03/16 |
|  |  | People | - |  |  | Date Closed |  |

| 5 | Loss of partner or agreed partnership funding (revenue or capital) | Service Disruption | IV | E | Partnerships are under financial pressure | Requires Treatment | Yes |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Financial Loss | II |  |  | Last Review Date | 05/10/15 |
|  |  | Reputation | III |  |  | Next Milestone Date | 1/3/16 |
|  |  | Legal Implications | - |  |  | Next Review Date | 31/03/16 |
|  |  | People | - |  |  | Date Closed |  |
| b) Community Partnerships Service Risks |
| 6 | Failure to achieve Community Safety targets Strategic Risk No. 5 | Service Disruption | II | F | Strategy continues to meet majority of targets. Individual targets not met are being addressed by local action plans. Reducing funding increases likelihood | Requires Treatment | Yes |
|  |  | Financial Loss | I |  |  | Last Review Date | 05/10/15 |
|  |  | Reputation | III |  |  | Next Milestone Date | 31/3/16 |
|  |  | Legal Implications | I |  |  | Next Review Date | 31/03/16 |
|  |  | People | I |  |  | Date Closed |  |
| 7 | Failure to achieve the priorities of the Community Strategy through the Local Strategic Partnership Strategic Risk No 6 | Service Disruption | I | D | Performance Reward Grant largely allocated. No further income anticipated | Requires Treatment | Yes |
|  |  | Financial Loss | I |  |  | Last Review Date | 05/10/15 |
|  |  | Reputation | III |  |  | Next Milestone Date | 31/03/16 |
|  |  | Legal Implications | I |  |  | Next Review Date | 31/03/16 |
|  |  | People | I |  |  | Date Closed |  |
| 8 | Community consultation work fails to improve contact with hard to reach groups resulting in lack of clear evidence base for strategic plan. | Service Disruption | I | E | Reduced resources for consultation work alleviated by increased inter agency work. | Requires Treatment | No |
|  |  | Financial Loss | I |  |  | Last Review Date | 05/10/15 |
|  |  | Reputation | II |  |  | Next Milestone Date | 1/3/16 |
|  |  | Legal Implications | I |  |  | Next Review Date | 31/03/16 |
|  |  | People | I |  |  | Date Closed |  |
| 9 | The Council fails to maintain its legal duties for equality and risks legal challenge | Service Disruption | I | F | Information Publication has been achieved. Equality Impact assessment process in place. | Requires Treatment | No |
|  |  | Financial Loss | I |  |  | Last Review Date | 05/10/15 |
|  |  | Reputation | III |  |  | Next Milestone Date | 1/3/16 |
|  |  | Legal Implications | I |  |  | Next Review Date | 31/03/16 |
|  |  | People | I |  |  | Date Closed |  |
| 10 | Targets in the Strategic Plan are not performance managed and fail to be achieved. | Service Disruption | I | F | Risk that data fails to be captured due to decrease in resources and outcomes cannot be demonstrated to residents or members. | Requires Treatment | No |
|  |  | Financial Loss | I |  |  | Last Review Date | 05/10/15 |
|  |  | Reputation | III |  |  | Next Milestone Date | 1/3/16 |
|  |  | Legal Implications | I |  |  | Next Review Date | 31/03/16 |
|  |  | People | I |  |  | Date Closed |  |
| 11 | Failure to engage the community in the Strategic Plan Strategic Risk No. 4 | Service Disruption | I | E | Evidence held on successful consultations and high customer satisfaction data. | Requires Treatment | Yes |
|  |  | Financial Loss |  |  |  | Last Review Date | 05/10/15 |
|  |  | Reputation | III |  |  | Next Milestone Date | 31/3/16 |
|  |  | Legal Implications |  |  |  | Next Review Date | 31/03/16 |
|  |  | People |  |  |  | Date Closed |  |
| 12 | Failure to secure improvements to services Strategic Risk No. 1 | Service Disruption | III | F | Additional public perception surveys introduced. Improvement in performance of Revenues and Benefits. | Requires Treatment | No |
|  |  | Financial Loss |  |  |  | Last Review Date | 05/10/15 |
|  |  | Reputation | III |  |  | Next Milestone Date | 31/03/16 |
|  |  | Legal Implications |  |  |  | Next Review Date | 31/03/16 |
|  |  | People |  |  |  | Date Closed |  |
| 14 | Grants budget oversubscribed leading to poor publicity | Service Disruption | - | E | Popularity of scheme should allow for more effective funding | Requires Treatment | No |
|  |  | Financial Loss |  |  |  | Last Review Date | 05/10/15 |
|  |  | Reputation | II |  |  | Next Milestone Date | 31/03/16 |
|  |  | Legal Implications |  |  |  | Next Review Date | 31/03/16 |
|  |  | People |  |  |  | Date Closed |  |

| Likelihood | A |  |  |  |  |  | Impact | Likelihood |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | B |  |  |  |  |  | V = Catastrophic | A = ≥98% |
|  | C |  |  |  |  |  | IV = Critical | B = 75% - 97% |
|  | D |  |  | 7 |  |  | III = Significant | C = 50% - 74% |
|  | E |  | 1, 8, 14 | 2, 3, 11 | 4, 5, 13 |  | II = Marginal | D = 25% - 49% |
|  | F |  |  | 6, 9, 10, 12 |  |  | I = Negligible | E = 3% - 24% |
|  |  | I | II | III | IV | V |  | F = ≤2% |
|  | Impact |  |  |