## Summary (hidden)
Summary

## Reset
Recovery Impact Assessment, workplan and programme management
Strand - Reset. Lead Geof Muggeridge
Cell | Cell Lead | Sub Group | Sub Group Lead | Objectives of Sub Group | Actions to achieve Objectives | Delivery Date | Progress of Actions | Remedial Actions | Milestones | RAG Status of Action
Housing and Homelessness | Kimberley Grout |  |  | Identify the needs and develop housing pathways for customers provided with temporary accommodation as part of the Government response to the Covid-19 outbreak. | Complete a tracker for each customer in temporary accommodation placed under C19 | 11 June 2020 | Completed |  | Completed
|  |  |  | Identify the customer groups from who it is reasonable to expect an increase in demand on the housing advice and homelessness services. | Joint working with Community Partnerships, CAB, Partnership working through the Recovery Accommodation Cell | August 2020
|  |  |  | Identify what resources will be needed to meet this increased in demand. | Joint working with Community Partnerships, CAB, Partnership working through the Recovery Accommodation Cell | September 2020 | Recruitment underway to ensure team at full establishment
|  |  |  | Ensure that sufficient temporary accommodation is provided by the Council to meet an immediate and projected longer term increase in demand on the housing advice and homelessness services. | Identify customer groups for who we can expect an increase in demand on the service (see above). Identify additional temporary accommodation if current stock is insufficient | Autumn 2020 | Temporary accommodation sites at Bowring Green and Ashridge Drive (12 units) due to be completed in October 2020. Customers currently in nightly let temporary accommodation being moved back into district
|  |  |  | Make sure rough sleepers are aware of their options and ensure there are no rough sleepers in Three Rivers | Rough sleeping protocol to be developed | Autumn 2020 | Protocol was due in March 2020, however has been delayed until autumn
|  |  |  | Better understanding of rough sleeping in the district | Rough sleeping hotspots and trends to be identified | Autumn 2020 | monitoring is underway
|  |  |  | All tenants of Registered Providers (RPs) threatened with eviction are prevented from homelessness wherever possible | Joint working with RPs to provide advice and housing options to tenants. This includes liaison meetings and hosting the Homelessnesss Prevention Forum | Autumn 2020 | HPF to be arranged, date to be confirmed. Discussed a County-wide protocol through the Strategic Partnership Accommodation Board
Strand - Reset. Lead Geof Muggeridge
Cell | Cell Lead | Sub Group | Sub Group Lead | Objectives of Sub Group | Actions to achieve Objectives | Delivery Date | Progress of Actions | Remedial Actions | Milestones | RAG Status of Action
Service Restoration | Ray Figg | Service Restoration | Ray Figg Jennie Probert Josh Sills Kimberley Grout Kelly Barnard Billy Hall Tracy Langley Nigel Pollard Kimberley Rowley Charlotte Gomes | To identify, within an action plan, on the priority order and how all services will return to normal delivery over the short, medium and long term | 1. All HoS to identify service area priorities and rate them level 1-5 through Service Restoration Priority ratings form. 2. Priorities to be complied into one document under sub categories: Services currently running, New services running as a result of Covid, Service not currently running and needing to be restored 3. Senior Management and Members to agree service priority ratings 4. Senior Management to allocate Council resources and set time line for all services to be restored | TBC | Actions 1 & 2 complete |  | 1. Service Priority forms completed by HoS. 2. Master document of Service priority ratings complied 3.Covid-19 Recovery Committee on 21 July 2020 - to approve service priority ratings 4. Resources and priorities alloacted 5. All Services restored
|  |  |  | To cross reference the action plan against the other work streams | Share detail with Recovery Group Cell Leads | TBC | Ongoing
|  |  |  | To consider staff working within the office, working from home, site visits and interfacing with the public including interviews under caution and working with key stakeholders | All HoS to identify aspects of service delivery that cannot be carried out from home through Service Restoration Priority ratings form |  | Complete |  | 1. Return to office working 2. Return to on site visits 3. Return to public interfacing e.g. face to face interviews
|  |  |  | To communicate and liaise with the Lead Member and appropriate Lead Members with restoring services | All HoS to ensure Service Restoration is an agenda item in their respective Lead Member briefings and updates within the MIB in at least the short term | TBC | Ongoing
|  |  |  | To communicate with customers and local residents and to update the Customer Experience Strategy to reflect new ways of working | Once decisions have been taken, service areas to communicate directly with their customers and local residents via usual channels e.g. email, website, social media etc. General service update to go in Three Rivers Times and All Aboard (internal customers) | TBC | Ongoing |  | 1. Individual services have all areas operating business as usual 2. All services are back to business as usual
|  |  |  | To identify resources required to enable service restoration within the action plan over the short, medium and long term. | All HoS to identify resources required through Service Restoration Priority ratings form |  | Complete |  | 1. Service Priority forms completed by HoS. 2. Master document of Service priority ratings complied
|  |  |  | To work in partnership with key stakeholders to restore services, for example CAB, MIND, Friends of Groups, YMCA and SLM | All HoS to maintain dialogue with their services' respective groups, and seek input where necessary | TBC | Ongoing
Strand - Reset. Lead Geof Muggeridge
Cell | Cell Lead | Sub Group | Sub Group Lead | Objectives of Sub Group | Actions to achieve Objectives | Delivery Date | Progress of Actions | Remedial Actions | Milestones | RAG Status of Action
Finance | Nigel Pollard | Finance | Nigel Pollard / Temi Opeyemi | Support the Covid 19 reset strand | Will depend on which services are restored either as BAU or partially. | Weekly | Weekly Meetings
|  |  |  | Support the Covid 19 response sub- committee |  | As and when | None yet
|  |  |  | To ensure all financial implicating are considered in the road to recovery. |  | Fortnightly financial update on budget position to CMT | Interim Budget monitoring report to P&R 20 July | Recommend to Council that DOF is authorised to make the necessary budget adjustments arising from the impact of Covid 19 | Approved by P&R on 20 July and the next Council meeting
To review existing budgets with services to establish deletion or deferment.
Strand - Reset. Lead Geof Muggeridge
Cell | Cell Lead | Sub Group | Sub Group Lead | Objectives of Sub Group | Actions to achieve Objectives | Delivery Date | Progress of Actions | Remedial Actions | Milestones | RAG Status of Action
Risk | Phil King |  |  | Identify risks associated with objectives of the Corportae Framework 2020/23 | Score each risk | 2020-07-01 | Completed |  | To be agreed by Covid-19 Sub-Committee on 21 July | Amber
Strand - Reset. Lead Geof Muggeridge
Cell | Cell Lead | Sub Group | Sub Group Lead | Objectives of Sub Group | Actions to achieve Objectives | Delivery Date | Progress of Actions | Remedial Actions | Milestones | RAG Status of Action
Democracy & Governance | Anne Morgan |  |  | Support the Covid 19 reset strand | Will depend on which services are restored either as BAU or partially. | Weekly | Weekly Meetings
|  |  |  | Support the Covid 19 response sub- committee by providing all necessary legal and administrative support |  | As and when | None yet
|  |  |  | To ensure all Legal and governance implicating are considered in the road to recovery. |  | As and when | Supporting reports to Sub-Committee as and when | Recommendations to Council with any consitutional amendments necessay, arising from the impact of Covid 19 | Milestones will depend on actions from the Covid 19 Sub-Committee
Strand - Reset. Lead Geof Muggeridge
Cell | Cell Lead | Sub Group | Sub Group Lead | Objectives of Sub Group | Actions to achieve Objectives | Delivery Date | Progress of Actions | Remedial Actions | Milestones | RAG Status of Action
Policy | Andy Stovold |  |  | Review Coprorate Framework as a result of recovery impact work and covid-19. | Outcomes of recovery work to be considered. Evidence from impact surverys and conultations gathered and inform revised corporate objectives and consideration on this taken by Council. | 2020-12-01
|  |  |  | Review of Council Policy and Strategy Register | Undertake review in conultation with services. Draft to be completed by September | 2020-09-01
|  |  |  | Cyclical review of all policies | Map out timeline for review of policies. | 2020-12-01

## Reassure
Recovery Impact Assessment, workplan and programme management
Strand - Reassure. Lead Andy Stovold
Cell | Cell Lead | Sub Group | Sub Group Lead | Objectives of Sub Group | Actions to achieve Objectives | Delivery Date | Progress of Actions | Remedial Actions | Milestones | RAG Status of Action
Community Engagement | Rebecca Young | Community Engagement (Vol Sector) | Rebecca Young | To understand the impact on the many varied community groups, organisations and charities affected by COVID19 | Community Strategy LSP Impact Assessment Action Plan New- Review impact of Covid-19 on Community Groups and Voluntary sector. (Already started) | 01/09/2020 August 2020 | LSP Sub groups – Adults with Complex Needs, Community Safety Partnership, 11-19 Strategy group, Families First Partnership
|  |  |  | To set out how we will respond to the needs of the community. | New - Set up the LSP Community Interest Company | September 2020 | LSP received report on CIC and agreed some of the board members.
|  |  |  | To monitor the impact of the emergency on local needs | Regular partnership meetings, data anaylsis work and consultation | Autumn 2020
|  |  |  | To manage operation sustain | Existing - Engagement with county wide structures and Covid -19 response moving to Operation Sustain from Operation Shield. | July 2020 | Paper on Herts Community Help Network to be agreed at CECG meeting to support Operation Sustain as a partnership across Hertfordshire
|  |  |  | To fund W3RT and develop recovery focussed pathways in conjunction with the local voluntary sector. | Review and extend W3RT offer for community infrastructure support. | September 2020 | Extension of telephone support work undertaken in response to Covid-19. CVS support available until September 2020.
|  |  |  | To undertake specific consultation on the impact of the emergency within the local community including local businesses. | Consultation on new Corporate Plan to meet emerging needs. Hertfordshire Ominbus Survey including Covid-19. | Autumn 2020 | 1st results of omnibus surrvey received.
Strand - Reassure
Cell | Cell Lead | Sub Group | Sub Group Lead | Objectives of Sub Group | Actions to achieve Objectives | Delivery Date | Progress of Actions | Remedial Actions | Milestones | RAG Status of Action
Community Protection | Andy Stovold | Mental Health | Alison Mirpuri | Residents are supported to live independently and maintain their tenancies and homes | Existing - Establishment of Three Rivers CIC as a funding vehicle to support the delivery of the Community Strategy and its recovery plan. New – Development of project proposals to address the above needs New – Develop donation system for the CIC to obtain funds to deliver above projects and market this to local residents and businesses | August 2020 September 2020 August 2020 | Report taken to LSP June 2020
|  |  |  | We work together to make our residents safe in their accommodation | Existing - Covid 19 Impact Assessment on the Community Strategy and agreement of the recovery action plan | August 2020 | Impact assessment shared with LSP. Needs identified and partnership action plans are being developed.
|  |  |  | Residents are able to manage their own health, social care and support | Obtain data on the extent of adverse impact on physical health including food poverty, abuse, trauma/mental wellbeing through county-wide and national surveys and performance data of existing services to identify the needs of different community groups. | September 2020 | HCC surveyr results on healthy hub impact on partners completed.
|  |  |  | Residents have the life skills and access to the resources they need to live independently and cope with challenges to sustain their independence | Adults with complex Needs group to investigate further | October 2020 | CCG Grant funding available for charities to support this work in the community.
|  |  |  | Residents live in supportive communities | Existing – 11-19 Strategy Group – improve offer of services for young people with anxiety | Ongoing | Draft action plan has been produced by 11-19 group. Mental wellbeing can be addressed through Better Choices expansion.
|  |  |  | Residents have opportunities to be physically and mentally healthy | Herts Mind Network Community Support Service – expand capacity of service to support recover through funding a 1.0 FTE additional worker for 12 months using Brexit Funding | August 2020 | Recruitment carried out, and offer made. HMN are undergoing checks & DBS
[5 empty] | Existing – Adults with Complex Needs Group – improve the offer of services for adults with complex needs with mental health issues during recovery | Ongoing | Meetings are ongoing, currently increased to monthly and inputting on development of community strategy covid action plan.
|  |  |  | Residents have access to health and social care, especially the vulnerable | Existing – Families First Partnership – assess increase in referrals to all partners and additional resources requirement to address capacity | Ongoing
|  |  |  | Residents are safe from crime and antisocial behaviour | Existing – Community Safety Partnership – increase the capacity of ASB service at TRDC to address increasing demands of mental health related ASB complaints | Ongoing
|  |  |  | Residents are safe from abuse, neglect, violence, bullying, discrimination and exploitation | Existing – Community Safety Partnership Action Plans | Ongoing
|  |  |  | Neighbourhoods are safe for people to live, work and socialise in | Existing – Community Safety Partnership Action Plans | Ongoing
Community Protection | Andy Stovold | Physical Health | Rebecca Young | Residents are supported to live independently and maintain their tenancies and homes | Existing - Establishment of Three Rivers CIC as a funding vehicle to support the delivery of the Community Strategy and its recovery plan. | August 2020 | All directors have been nominated except TRDC's suggestion.
[5 empty] | New – Development of project proposals to address the above needs | September 2020 | Action plan development underway for the Community Strategy
[5 empty] | New – Develop donation system for the CIC to obtain funds to deliver above projects and market this to local residents and businesses | August 2020
[5 empty] | New- poverty Foodhub – deliver food to those impacted by the financial impact of the emergency including child food poverty and vulnerable adult food poverty | June-Oct | Food Hub has supported over 2,100 people with approx. 44,500 meals. | A review of the Food Hub will be completed by the end of July 2020 | Review of food hub - July 2020
|  |  |  | We work together to make our residents safe in their accommodation | Existing - Covid 19 Impact Assessment on the Community Strategy and agreement of the recovery action plan | August 2020 | Action plan development underway for the Community Strategy
|  |  |  | Residents are able to manage their own health, social care and support | Obtain data on the extent of adverse impact on physical health including food poverty, abuse, trauma/mental wellbeing through county-wide and national surveys and performance data of existing services to identify the needs of different community groups. | September 2020
Residents have the life skills and access to the resources they need to live independently and cope with challenges to sustain their independence
|  |  |  | Residents live in supportive communities | Existing – 11-19 Strategy Group – improve offer of services for young people with anxiety and facing trauma | Ongoing | Draft action plan has been produced by 11-19 group. Mental wellbeing can be addressed through Better Choices expansion - this will not cover trauma as that requires specialist support.
|  |  |  | Residents have opportunities to be physically and mentally healthy | Herts Mind Network Community Support Service – expand capacity of service to support recover through funding a 1.0 FTE additional worker for 12 months using Brexit Funding Existing – Adults with Complex Needs Group – improve the offer of services for adults with complex needs with mental health issues during recovery Existing – Three Rivers Healthy Hub – need to redesign service deliver during social distancing | August 2020 Ongoing Ongoing | CSS have been out to recruit and offer made, currently undergoing checks. Agreement in AWCN Group that Mind will attend local food banks to signpost people who's mental health is impacted by covid/unemployment to mental health services Healthy Hub HMN worker out to recruit, plans for them to be attached to foodbanks once in place
|  |  |  | Residents have access to health and social care, especially the vulnerable | Existing – Families First Partnership – assess increase in referrals to all partners and additional resources requirement to address capacity | Ongoing
|  |  |  | Residents are safe from abuse, neglect, violence, bullying, discrimination and exploitation | New – safeguarding – ensure all VCS structures understand the processes for safeguarding referrals. | July 2020 - March 2021
Neighbourhoods are safe for people to live, work and socialise in
Community Protection | Andy Stovold | Domestic Abuse | Alison Mirpuri | Residents are supported to live independently and maintain their tenancies and homes | Existing - Establishment of Three Rivers CIC as a funding vehicle to support the delivery of the Community Strategy and its recovery plan. New – Development of project proposals to address the above needs New – Develop donation system for the CIC to obtain funds to deliver above projects and market this to local residents and businesses | August 2020 September 2020 August 2020
|  |  |  | We work together to make our residents safe in their accommodation | Existing - Covid 19 Impact Assessment on the Community Strategy and agreement of the recovery action plan | September 2020 | Communtiy Strategy Action plan is being developed
|  |  |  | Residents are able to manage their own health, social care and support | Obtain data on the extent of adverse impact on physical health including food poverty, abuse, trauma/mental wellbeing through county-wide and national surveys and performance data of existing services to identify the needs of different community groups. | September 2020
Residents have the life skills and access to the resources they need to live independently and cope with challenges to sustain their independence
|  |  |  | Residents live in supportive communities | Existing – 11-19 Strategy Group – improve offer of services for young people with anxiety and facing trauma | Ongoing | Draft action plan has been produced by 11-19 group. Mental wellbeing can be addressed through Better Choices expansion.
|  |  |  | Residents have opportunities to be physically and mentally healthy | Herts Mind Network Community Support Service – expand capacity of service to support recover through funding a 1.0 FTE additional worker for 12 months using Brexit Funding Existing – Adults with Complex Needs Group – improve the offer of services for adults with complex needs with mental health issues during recovery | August 2020 Ongoing | CSS have been out to recruit and offer made, currently undergoing checks. Agreement in AWCN Group that Mind will attend local food banks to signpost people who's mental health is impacted by covid/unemployment to mental health services Healthy Hub HMN worker out to recruit, plans for them to be attached to foodbanks once in place
|  |  |  | Residents have access to health and social care, especially the vulnerable | Existing – Families First Partnership – assess increase in referrals to all partners and additional resources requirement to address capacity | Ongoing
|  |  |  | Residents are safe from abuse, neglect, violence, bullying, discrimination and exploitation | Existing – Community Safety Partnership – increase the capacity of ASB service at TRDC to address increasing demands of mental health related ASB complaints | Ongoing | Ongoing
Neighbourhoods are safe for people to live, work and socialise in
Community Protection | Andy Stovold | Child and vulnerable adult abuse | Andy Stovold | Residents are supported to live independently and maintain their tenancies and homes | Existing - Establishment of Three Rivers CIC as a funding vehicle to support the delivery of the Community Strategy and its recovery plan. New – Development of project proposals to address the above needs New – Develop donation system for the CIC to obtain funds to deliver above projects and market this to local residents and businesses | August 2020 September 2020 August 2020
|  |  |  | We work together to make our residents safe in their accommodation | Existing - Covid 19 Impact Assessment on the Community Strategy and agreement of the recovery action plan | September 2020 | Communtiy Strategy Action plan is being developed
|  |  |  | Residents are able to manage their own health, social care and support | Obtain data on the extent of adverse impact on physical health including food poverty, abuse, trauma/mental wellbeing through county-wide and national surveys and performance data of existing services to identify the needs of different community groups. | September 2020
Residents have the life skills and access to the resources they need to live independently and cope with challenges to sustain their independence
|  |  |  | Residents live in supportive communities | Existing – 11-19 Strategy Group – improve offer of services for young people with anxiety and facing trauma | Ongoing | Draft action plan has been produced by 11-19 group. Mental wellbeing can be addressed through Better Choices expansion - this will not cover trauma as that requires specialist support.
|  |  |  | Residents have opportunities to be physically and mentally healthy | Herts Mind Network Community Support Service – expand capacity of service to support recover through funding a 1.0 FTE additional worker for 12 months using Brexit Funding Existing – Adults with Complex Needs Group – improve the offer of services for adults with complex needs with mental health issues during recovery | August 2020 Ongoing | CSS have been out to recruit and offer made, currently undergoing checks. Agreement in AWCN Group that Mind will attend local food banks to signpost people who's mental health is impacted by covid/unemployment to mental health services Healthy Hub HMN worker out to recruit, plans for them to be attached to foodbanks once in place
|  |  |  | Residents have access to health and social care, especially the vulnerable | Existing – Families First Partnership – assess increase in referrals to all partners and additional resources requirement to address capacity | Ongoing
|  |  |  | Residents are safe from crime and antisocial behaviour | Existing – Community Safety Partnership – increase the capacity of ASB service at TRDC to address increasing demands of mental health related ASB complaints | Ongoing | ongoing
Neighbourhoods are safe for people to live, work and socialise in
Community Protection | Andy Stovold | Housing | Kimberley Grout | Residents are able to manage their own health, social care and support | Obtain data on the extent of adverse impact on physical health including food poverty, abuse, trauma/mental wellbeing through county-wide and national surveys and performance data of existing services to identify the needs of different community groups. | September 2020
|  |  |  | We work together to make our residents safe in their accommodation | Existing - Covid 19 Impact Assessment on the Community Strategy and agreement of the recovery action plan New – Increase the capacity of Citizens Advice to cope with additional poverty related workload | September 2020 September | Action plan development underway for the Community Strategy. CAB workload is currently managable
Residents have the life skills and access to the resources they need to live independently and cope with challenges to sustain their independence
|  |  |  | Residents live in supportive communities | Existing – 11-19 Strategy Group – improve offer of services for young people with anxiety and facing trauma | Ongoing | Draft action plan has been produced by 11-19 group. Mental wellbeing can be addressed through Better Choices expansion.
[5 empty] | Existing - Establishment of Three Rivers CIC as a funding vehicle to support the delivery of the Community Strategy and its recovery plan. | September 2020
[5 empty] | New – Development of project proposals to address the above needs | September 2020 | Communtiy Strategy Action plan is being developed
[5 empty] | New – Develop donation system for the CIC to obtain funds to deliver above projects and market this to local residents and businesses | July
|  |  |  | Residents have opportunities to be physically and mentally healthy | Herts Mind Network Community Support Service – expand capacity of service to support recover through funding a 1.0 FTE additional worker for 12 months using Brexit Funding Existing – Adults with Complex Needs Group – improve the offer of services for adults with complex needs with mental health issues during recovery | August 2020 Ongoing | CSS have been out to recruit and offer made, currently undergoing checks. Agreement in AWCN Group that Mind will attend local food banks to signpost people who's mental health is impacted by covid/unemployment to mental health services Healthy Hub HMN worker out to recruit, plans for them to be attached to foodbanks once in place
|  |  |  | Residents are safe from abuse, neglect, violence, bullying, discrimination and exploitation | Existing – Community Safety Partnership – increase the capacity of ASB service at TRDC to address increasing demands of drug related crime and disorder | Ongoing | ongoing
Neighbourhoods are safe for people to live, work and socialise in
Community Protection | Andy Stovold | Drug and Alcohol misuse | Shivani Davé | Residents are supported to live independently and maintain their tenancies and homes | Existing - Establishment of Three Rivers CIC as a funding vehicle to support the delivery of the Community Strategy and its recovery plan. New – Development of project proposals to address the above needs New – Develop donation system for the CIC to obtain funds to deliver above projects and market this to local residents and businesses | August 2020 September 2020 August 2020
|  |  |  | We work together to make our residents safe in their accommodation | Existing - Covid 19 Impact Assessment on the Community Strategy and agreement of the recovery action plan | September 2020 | Communtiy Strategy Action plan is being developed
|  |  |  | Residents are able to manage their own health, social care and support | Obtain data on the extent of adverse impact on physical health including food poverty, abuse, trauma/mental wellbeing through county-wide and national surveys and performance data of existing services to identify the needs of different community groups. | September 2020
Residents have the life skills and access to the resources they need to live independently and cope with challenges to sustain their independence
|  |  |  | Residents live in supportive communities | Existing – 11-19 Strategy Group – improve offer of services for young people with anxiety and facing trauma | Ongoing | Draft action plan has been produced by 11-19 group. Mental wellbeing can be addressed through Better Choices expansion.
|  |  |  | Residents have opportunities to be physically and mentally healthy | Herts Mind Network Community Support Service – expand capacity of service to support recover through funding a 1.0 FTE additional worker for 12 months using Brexit Funding Existing – Adults with Complex Needs Group – improve the offer of services for adults with complex needs with mental health issues during recovery | August 2020 Ongoing | CSS have been out to recruit and offer made, currently undergoing checks. Agreement in AWCN Group that Mind will attend local food banks to signpost people who's mental health is impacted by covid/unemployment to mental health services Healthy Hub HMN worker out to recruit, plans for them to be attached to foodbanks once in place
|  |  |  | Residents have access to health and social care, especially the vulnerable | Existing – Families First Partnership – assess increase in referrals to all partners and additional resources requirement to address capacity | Ongoing
|  |  |  | Residents are safe from abuse, neglect, violence, bullying, discrimination and exploitation | Existing – Community Safety Partnership – increase the capacity of ASB service at TRDC to address increasing demands of drug and alcohol misuse related ASB complaints | Ongoing | ongoing
|  |  |  | Neighbourhoods are safe for people to live, work and socialise in | New – explore touch points with video screens to enable business meetings. | End of August
Community Protection | Andy Stovold | Poverty | Rebecca Young | Residents are supported to live independently and maintain their tenancies and homes | Existing - Establishment of Three Rivers CIC as a funding vehicle to support the delivery of the Community Strategy and its recovery plan. | September 2020
[5 empty] | New – Development of project proposals to address the above needs | September 2020 | Communtiy Strategy Action plan is being developed
[5 empty] | New – Develop donation system for the CIC to obtain funds to deliver above projects and market this to local residents and businesses | August 2020
[5 empty] | Foodhub – establish the role of this beyond the end of June 2020 and options for helping to feed those affected | June-Oct | Food Hub has supported over 2,100 people with approx. 44,500 meals. | A review of the Food Hub will be completed by the end of July 2020 | Review of food hub - July 2020
|  |  |  | Residents are able to manage their own health, social care and support | Obtain data on the extent of adverse impact on physical health including food poverty, abuse, trauma/mental wellbeing through county-wide and national surveys and performance data of existing services to identify the needs of different community groups. | September 2020
|  |  |  | Residents have the life skills and access to the resources they need to live independently and cope with challenges to sustain their independence | Existing – Families First Partnership – assess increase in referrals to all partners and additional resources requirement to address capacity | Ongoing
|  |  |  | Residents live in supportive communities | Herts Mind Network Community Support Service – expand capacity of service to support recover through funding a 1.0 FTE additional worker for 12 months using Brexit Funding Existing – Families First Partnership – assess increase in referrals to all partners and additional resources requirement to address capacity Existing – Adults with Complex Needs Group – improve the offer of services for adults with complex needs with poverty as a presenting issue Existing – 11-19 Strategy Group – improve offer of services for young people with money worries. | September 2020 Ongoing Ongoing Ongoing | CSS have been out to recruit and offer made, currently undergoing checks. Agreement in AWCN Group that Mind will attend local food banks to signpost people who's mental health is impacted by covid/unemployment to mental health services Healthy Hub HMN worker out to recruit, plans for them to be attached to foodbanks once in place. Better choices expansion on mental and emotional wellbeing could address this. Requires funding
|  |  |  | Residents are safe from abuse, neglect, violence, bullying, discrimination and exploitation | Existing - Covid 19 Impact Assessment on the Community Strategy and agreement of the recovery action plan | August 2020 | Communtiy Strategy Action plan is being developed
Strand - Reassure. Lead Andy Stovold
Cell | Cell Lead | Sub Group | Sub Group Lead | Objectives of Sub Group | Actions to achieve Objectives | Delivery Date | Progress of Actions | Remedial Actions | Milestones | RAG Status of Action
Communications | Phil King |  |  | To produce, agree and implement a Communications Action Plan for the COVID-19 recovery – residents and businesses | Provide clear, relevant, accurate and timely information | Ongoing | Draft Action Plan being developed | Agree communications action plan when priorities agreed |  | Amber
|  |  |  | To review and contribute to partners’ communications. | Action plans will be developed as the project progresses and as required | To be agreed as the project progresses |  |  |  | Amber
|  |  |  | To agree internal communications methodology. | Action plans will be developed as the project progresses and as required | To be agreed as the project progresses |  |  |  | Amber
Strand - Reassure. Lead Andy Stovold
Cell | Cell Lead | Sub Group | Sub Group Lead | Objectives of Sub Group | Actions to achieve Objectives | Delivery Date | Progress of Actions | Remedial Actions | Milestones | RAG Status of Action
Staff Welfare | Terry Baldwin |  | Claire Smith | Ensure employees get the right Health and Wellbeing information at the right time. | Risk assessments completed; on-going assessment of health and wellbeing needs, particularly relevant if another spike occurs. | 2020-07-31 | on track. Discussions taking place with managers re risk assessments and plans to mitigate. Review monthly and amend plans if another lock down is imposed. |  | end July for risk assessments. End October for review of health and wellbeing of employees (if a 2nd spike occurs) | G
|  |  |  | Ensuring Health and Wellbeing information is up to date and appropriate for the circumstances at that time. | Information on website reviewed regularly and updated; newsletters produced monthly; regular wellbeing meetings with MHFA's undertaken. | Ongoing | 1st newsletter completed and sent out; intranet updated. |  | Monthly newsletters | G
|  |  |  | Link with the work being undertaken to identify those that want to come in to the office, those that are fearful, those with underlying medical conditions or living with someone with underlying conditions, caring responsibilities. | As above re risk assessments | end of July | Risk assessments completed for majority of staff. HRBP's discussing action plans with amangers |  | end July for risk assessments. End October for review of health and wellbeing of employees (if a 2nd spike occurs) | G
|  |  |  | Communicate the information and support available through the intranet, Three Rivers Health and You | Update intranet; produce monthl;y health and wellbing newsletter | on-going monthly | 1st newsletter produced |  | on-going monthly | G
Strand - Reassure. Lead Andy Stovold
Cell | Cell Lead | Sub Group | Sub Group Lead | Objectives of Sub Group | Actions to achieve Objectives | Delivery Date | Progress of Actions | Remedial Actions | Milestones | RAG Status of Action
Celebration | Terry Baldwin |  |  | After the end of the current lockdown, and return to "The New Normal", set up a “Thank You to Staff" event, hosted by the senior team | N – Celebration event planning, design and delivery | Date for event to be agreed
Strand - Reassure. Lead Andy Stovold
Cell | Cell Lead | Sub Group | Sub Group Lead | Objectives of Sub Group | Actions to achieve Objectives | Delivery Date | Progress of Actions | Remedial Actions | Milestones | RAG Status of Action
Capacity | Terry Baldwin |  |  | Ensure resources are in the right place to deliver services for residents in the short, medium and longer term. | identify priority services to return and resource requirements for those services. If there arwe shortfalls, put in place the various methods outlined to fill the gaps. Budget issues to be discussed with Finance/CMT at the ealriest opportunity. | 31/08/2020 for initial assessment; 31 December for longer term impacts. | Service prioritisation taking place |  |  | G
Ensure recovery projects have adequate resources to deliver their objectives.
Consider how to move resources if required – secondments, temporary or permanent reallocation of staff.
Any budget issues regarding staff movement or additional staff requirements to be raised as early as possible and resolved before action is taken.
Communicate any opportunities for development to staff.
Utilise a flexible matrix management approach to staff being redeployed on a temporary basis.

## Renew
Recovery Impact Assessment, workplan and programme management
Strand - Renew. Lead Alison Scott
Cell | Cell Lead | Sub Group | Sub Group Lead | Objectives of Sub Group | Actions to achieve Objectives | Delivery Date | Progress of Actions | Remedial Actions | Milestones | RAG Status of Action
Economic Recovery | Clare May |  |  | The RCG has set up an Economic Resilience Cell which will take the lead in this area at a county wide level and this includes involvement with the Hertfordshire Local Enterprise Partnership (LEP). The objective is to tie in with this Cell but also understand in greater depth the impact on the Three Rivers area. The work stream should consider any locally based interventions which will support the local economy and major anchor businesses and SMEs. | Existing - Hertfordshire Growth Board to ensure that the district is adequately represented. | Ongoing - | Chief Exec and Lead Member are Members of the Herts Growth Board action will follow. |  | HGB Meetings | A
[5 empty] | New Reopening High Street Safety Fund Temporary measures to ensure social distancing on high streets for shops reopening, communication campaign to advise residents of these measures and a communication campaign to advise businesses and retailers of these measures and to provide advice on how to get premises suitable for opening. Suggestion is that money is spent on additional resources for Environmental Heath Team to advise retailers and businesses of what measure need to be taken. | Initial July 2020 for Ricky High Street. August 2020 for other parades | Postars and signage already in Rickmansworth High Street. • We have introduced signage on various Retail Parades to encourage people to keep a safe distance when queuing for shops (Bedmond parade and South Oxhey still outstanding – additional signage needs to be ordered for SO as over half the precinct is open). • We have supported HCC by undertaking surveys asking about the effects of the barriers to widen footways in Rickmansworth town centre • We have asked for views on possible further options to protect people walking, queueing and cycling in the High Street. • The Lead Member has agreed that in line with HCC Highways guidance we consider offering local shops a service to mark out queuing areas on pavements in front of their shops. The intention is that we speak to shopkeepers in our own retail parades and take forward as requested. With regard to the public highway we only progress speaking to shopkeepers if EH intelligence has raised concerns. |  | July 2020 for Ricky High Street August for other parades and 31 March 2021 end date for temporary measures. | G
[5 empty] | New Local Authority Small Business Discretionary Grant | July 2020 | Funding is currently £572,000. We have spent £98,727 as of July 2020. New policy to be agreed by group leaders before we review the claims already paid and then open a second application window. Date to be decided |  | Date for second window of grants yet to be decided | A
[5 empty] | New – Herts LEP undertaking small business survey. Use the results from Three Rivers participants of the Herts LEP survey to gather information on the situation to inform actions | August 2020 | Head of Planning Policy has set up regular meetings with Adam Wood of Herts LEP to keep up to date on progress of their work. As of 14 July 2020 the business survey is still open and the results will be available by end of August. |  | Monthly Meetings (next in August 2020) and the results of their business survey due August 2020 | A
[5 empty] | New Instigate a Key Account system for major businesses in the area | August 2020 | An initial List of key business to be drawn up and Chief Executive, Directors and other Senior Officers to build relationships for intellegence gathering. |  |  | R
[5 empty] | New Hert LEP undertaking a study on the retail and leisure industries specifically later this year (November) Information to be provided to assist | May 2020 (TRDC to provide information) November 2020 (anticipated date for completion of study) | Our Retail and Leisure Study has been passed to Herts LEP to help inform their study (May 2020). Consultants have been appointed (July 2020) |  | Monthly Meetings (next in August 2020) with representative of Herts LEP | A
[5 empty] | New - Review impact of Covid-19 on the High Street and local shopping centres. (Annual Shop Survey September 2020 and again in June 2021) (To inform Economic Recovery Strategy?) | September 2020 June 2021 | None. Annual Shop Survery undertaken for the Annual Monitoring Report to be done in September 2020. |  | September 2020 ad June 2021 | R
[5 empty] | New - Review the impact of Covid-19 on longer term requirements of businesses within the District. To be informed by the Herts LEPs Economic Review which looks at the impacts of COVID19. (To feed into TRDC Economic Strategy?) | August 2020 (Herts LEP appointment of consultants) December 2020 (anticipated completion of study) January 2021 (TRDCs consideration of findings) | Herts LEP preparing tender brief for Economic Study (July 2020) |  | Monthly Meetings (next in August 2020) with representative of Herts LEP | A
[5 empty] | New Review employment opportunities and skills (to feed in to the Economic Recovery Strategy?) | December 2020 | None |  |  | R
[5 empty] | New Economic Recovery Strategy: Strategy can only be written when things are back to normal and should be in alignment with the Hertfordshire LEP Economic Recovery Strategy. | March 2021 | None |  | Appointent of Economic Officer | R
Strand - Renew. Lead Alison Scott
Cell | Cell Lead | Sub Group | Sub Group Lead | Objectives of Sub Group | Actions to achieve Objectives | Delivery Date | Progress of Actions | Remedial Actions | Milestones | RAG Status of Action
Regeneration | Alison Scott | Regeneration | Alison Scott | To support high quality neighbourhoods, including businesses and the local economy and access to good quality housing. This cell will work with developers and other partners to help minimise the impact of Covid 19, facilitate the continuing development of housing and business opportunities within the district and react to market failures within specific areas and sectors. This cell focuses on infrastructure and the built environment whilst the Economic Recovery Cell focuses on businesses and the labour market. | Existing - Review impact of Covid-19 on local plan. | Full Council approve Local Plan for consultation 18 December 2020. Dec 2020 – Feb 2021 – Consultation on Publication Version of Local Plan July—Aug 2021 - Full Council to approve Local plan for submission to Secretary of State for examination August 2021 – Feb 2022 - Examination of Local Plan March 2022 - Adoption of Local Plan | On Target |  | Full Council approve Local Plan for consultation 18 December 2020. Dec 2020 – Feb 2021 – Consultation on Publication Version of Local Plan Full Council July 2021 to approve Local plan for submission to Secretary of State for examination August 2021 – Feb 2022 - Examination of Local Plan March 2022 - Adoption of Local Plan
[5 empty] | Existing - Hertfordshire Growth Board to ensure that the district is adequately represented. | Ongoing | On Target
[5 empty] | New - Work with major developers in relation to major development sites to facilitate their continued development. | Pre-Application activity projected to start end of 2020. | On Target
Strand - Renew. Lead Alison Scott
Cell | Cell Lead | Sub Group | Sub Group Lead | Objectives of Sub Group | Actions to achieve Objectives | Delivery Date | Progress of Actions | Remedial Actions | Milestones | RAG Status of Action
Future Policy | Jane Walker |  |  | To review the council’s customer experience strategy to deliver all services in the most effective way, while still enabling vulnerable groups to access services. | Customer Experience Strategy: i) Review of all reports as to how customers are accessing services ii) online survey for customers regarding use of online services plus questions at end of call with CSC iii) Review service processes and re-design for all channels to ensure fit for purpose (and that self-help is available & promoted to residents & businesses where possible) – digital by default | September 2020 November 2020 May 2021 | i) work has commenced on the review of all reports and is on track for completion by September 2020. Once completed work will start on the survey.
|  |  |  | To promote self-help where possible and manage the reintroduction of face to face service delivery in line with new ways of working. | Return to the Office enabling works | Complete by end of June 2020 – see detailed plan attached | The only outstanding piece of this work is perspex screens. We are atill waiting on delivery |  | Extend the delivery date to mid Aug 2020.
|  |  |  | Ensure new ways of working are embedded into the values and behaviours for Three Rivers, reflected in performance appraisals and all staff are fully engaged. | Review of staff working requirements – able to work flexibly, agile and potentially for some roles, from any location. Review office space requirements – to link with projects from other areas but to also include days required to be in the office (specify days or complete flexibility) and use (or not) of zones within Three Rivers House. Review contracts and policies to ensure they are up to date and reflect new ways of working Develop new leadership and management programmes to support new ways of working Batchworth depot new building, ensure this is compliant with the new guidelines and in accordance with new ways of working | Immediate requirements by end of October; longer term plans by 31 March 2021 Immediate requirements by end of September; longer term plans by 31 March 2021 To be updated as new agreements are reached. By 31 March 2021 March 2021 | The review has commenced.
|  |  |  | Manage the transition to the new ways of working for all staff, including those returning to the office. | Review of printing and post arrangements, including new MFD (printers) Review of HR Policies in relation to new ways of working. Review of Office Accommodation Requirements in the longer term, including space required, opening hours, access etc. Review contracts and policies to ensure they are up to date and reflect new ways of working | March 2021 31 December 2020 31 December 2020 To be updated as new agreements are reached.
Strand - Renew. Lead Alison Scott
Cell | Cell Lead | Sub Group | Sub Group Lead | Objectives of Sub Group | Actions to achieve Objectives | Delivery Date | Progress of Actions | Remedial Actions | Milestones | RAG Status of Action
New Ways of Working | Kimberley Grout |  |  | To decide and agree a phased return to the office in the short-term.
To decide and agree the long term office and working from home arrangements.
To decide and agree working practices and office space and building arrangements for the ‘new normal’.
To incorporate the views and concerns of staff and any identified risks from the Return to Office: Coronavirus Risk Assessments where practical and possible.
Strand - Renew. Lead Alison Scott
Cell | Cell Lead | Sub Group | Sub Group Lead | Objectives of Sub Group | Actions to achieve Objectives | Delivery Date | Progress of Actions | Remedial Actions | Milestones | RAG Status of Action
Values & Behaviours | Terry Baldwin | Simon Ralton; Sheela Popat; Other representatives (to be identified) from service areas. | Simon Ralton | Ensure new ways of working are embedded into the values and behaviours for Three Rivers | Identify the 'new ways of working'; Obtain approval for the changes; organise workshops or facilitated meetings with Members; senior managers, and staff at all levels to discuss and agree the new values and behaviours as a result of the new ways of working; roll out to organisation and include within i-perform check-ins and annual appraisal system. Develop new leadership and management programmes to support new ways of working | by 31 March 2021, ready for appraisal year 2021/22 | Early stage discussions only at this point. New ways of working to be developed fruther before values and behaviours can start to be considered and agreed. | N/A |  | G
Engage with staff to ensure they are part of our new values and behaviours;
Present and agree values and behaviours with members.
Embed the new values and behaviours into the review process for staff (i-perform);
Strand - Renew. Lead Alison Scott
Cell | Cell Lead | Sub Group | Sub Group Lead | Objectives of Sub Group | Actions to achieve Objectives | Delivery Date | Progress of Actions | Remedial Actions | Milestones | RAG Status of Action
Remobilistaion of staff | Terry Baldwin |  | Tracy Langley | • Ensure the priority phasing of staff returning to office working; | Link to service prioritisation work | Initial work to be completed by end of September 2020 re return to TRH; other areas by end of March 2021 | Review office space requirements – to link with projects from other areas but to also include days required to be in the office (specify days or complete flexibility) and use (or not) of zones within Three Rivers House. |  | 30 Sept 2020 - initial assessment of priority staff to return to TRH | G
• Consider how to safely introduce staff back to an office environment;
• Ensure polices are updated to reflect new ways of working;
• Review how annual Leave is to be managed during this time by considering how to prioritise requests; deal with carry-over of leave and TOIL to ensure we can still run services.
• Ensure outcomes of the risk assessments regarding return to work are considered and taken into account when planning for staff to return to office working.