COMMUNITY SERVICES (HOUSING)

SERVICE PLAN

2016 - 2019

CONTENTS

| Section | Item | Page |
| --- | --- | --- |
|  | Introduction | 3 |
| 1 | Inputs | 3 |
| 1.1 | Budgets | 3 |
| 2 | Outputs and Outcomes | 5 |
| 2.1 | Performance management | 5 |
| 2.2 | Projects | 8 |
| 2.3 | Risk Management | 9 |
|  | Version Control | 12 |

INTRODUCTION

The progress of this service plan will be monitored in the following ways:

- Through regular discussion at departmental management team (DMT) and Section Heads meetings and logged in the version control section of this document

- Performance indicator monitoring by the Council’s Management Board on a quarterly basis

- By Committee reports twice a year (at the end of quarters two and four)

Service Plans will be formally updated on an annual basis, taking into account internal and external influences arising from monitoring arrangements throughout the year.

SECTION 1:	INPUTS

| 1.1 | Budgets |
| --- | --- |

|  | 2016/17 Latest | 2017/18 Latest | 2018/19 Latest |
| --- | --- | --- | --- |
|  | £ | £ | £ |
| Net Cost of Service (Direct Cost / Income only) | 443,800 | 451,580 | 459,510 |

Further financial analysis can be found by using this link

SECTION 2:	OUTPUTS AND OUTCOMES

| 2.1 | Performance management |
| --- | --- |

2.1.1	Contribution to the Councils’ Strategic Aims and Objectives

As identified in the draft Strategic Plan 2015-2018 (‘Lead Service’).  Measures and targets should be developed further.

| Strategic Plan Priority theme | Strategic Plan objective (inc. ref) | Measure (including the reference) | Target |
| --- | --- | --- | --- |
| Safety and Wellbeing |  |  |  |
| Clean and Green |  |  |  |
| Economic Prosperity | 3.2.2 Improve or facilitate access to housing. | HN06 – Promote access to private sector lettings with use of the Council Rent Deposit Guarantee Scheme | 14 per year |
| Customer Service | 4.1.1 We will strive to improve and maintain service standards for all services. | HN07 – Housing application registration time | 95% within 5 days |

2.1.2 	Performance indicators

Performance indicators are used to aid the decision making process as well as assess the efficiency and effectiveness of service delivery. The data that we use must be accurate, reliable and timely. To meet these requirements we have adopted the Audit Commission’s Standards for Better Data Quality. Further details of the Council’s commitment to data quality can be found in the Strategic Plan.

| Ref | Description | 2014/15 Actual | 2015/16 Target (Current year) | 2016/17 Target (Next year) | 2017/18 Target | 2018/19 Target |
| --- | --- | --- | --- | --- | --- | --- |
| HN01 | Maximum number of households living in temporary accommodation (snapshot) | 95* | 30 | 50 | 48 | 45 |
| HN02 | Maximum number of families in Bed & Breakfast# | 5 | 0 | 0 | 0 | 0 |
| HN03 | Maximum number of households in temporary accommodation throughout the year | New PI | New PI | 240 | 230 | 220 |
| HN06 | Promote access to private sector lettings through RDGS (and Easy Let - removed) | 18 | 20 | 16 | 16 | 16 |
| HN07 | Process housing applications within 5 working days once all supporting information has been received from the applicant | 94.68% | 95% | 95% | 96% | 97% |
| HN08 | Housing applications received online rather than paper forms | 88.52% | 90% | 92% | 94% | 96% |
| HN09 | Homeless application decisions within 33 working days | 82.30% | 90% | 80% | 85% | 90% |

* Consisted of adding up four quarters but this was a snapshot figure and so could have included double counting, procedure note amended for 2015/16 for the target to be the same as the end of quarter four and also now inline with Government returns.

# This relates to the detail contained within the PI which counts the number of families in B&B over 6 weeks without a move on plan. This is different to the legal definition. Full details of this in the Committee Report dated 11 November regarding temporary accommodation.

The Housing Services Manager is responsible for the source data, data entry and checking the data. The purpose of collating this data is to ensure that our services improve.

| 2.2 | Projects |
| --- | --- |

| Project details | Project timescales |
| --- | --- |
| Project title | Proposed outcome | 2016/17 | 2017/18 | 2018/19 |
| Gold Standard peer review | To be reviewed by two local authority housing teams (supported by National Practitioner Support Service) and achieve at least 60% (pass rate) | To start Mar 2016 and end Oct 2016 |  |  |
| Gold Standard Challenges | Following peer review begin the 10 challenges, working through 1 challenge at a time to ultimately achieve gold status | To start Nov 2016 | To achieve bronze status by Apr 2017 | To finish approx Jul 2018 |
| Housing allocations policy review | To review current policy and implement recommendations for improvements and updates | To start Jan 2016 and end Jul 2016 |  |  |
| Scope and progress provision of additional temporary accommodation (building/buying) | To increase provision of temporary accommodation for homeless households reducing the need of Bed & Breakfast | Started Oct 2015 | End Jul 2017 |  |

| 2.3 | Risk Management |
| --- | --- |

RISK REGISTER

| Service Plan: Community Partnerships 2015-2018 |
| --- |
| Risk Ref | Risk | Impact | Impact Classification | Likelihood Classification | Reason for Assessment |  |  |
|  | Brief Description – Title of Risk | See Impact Table | See Impact Table | See Likelihood Table | Use this box to describe how the score has been derived |  |  |
| a) Common Risks - shared across the whole section |
| 1 | Insufficient staff | Service Disruption | III | E | Potential use of agency staff if required but service is a statutory function so required to provide a minimum level of service | Requires Treatment | Yes |
|  |  | Financial Loss | II |  |  | Last Review Date | 13/10/15 |
|  |  | Reputation | III |  |  | Next Milestone Date | 01/03/16 |
|  |  | Legal Implications | III |  |  | Next Review Date | 31/10/15 |
|  |  | People | II |  |  | Date Closed |  |
| 2 | Total failure of ICT systems | Service Disruption | III | E | Customers records held on web based system. Also responsible for consortium of 5 LA and many RP’s. Staff could deliver if web service available elsewhere | Requires Treatment | Yes |
|  |  | Financial Loss | II |  |  | Last Review Date | 13/10/15 |
|  |  | Reputation | II |  |  | Next Milestone Date | 01/03/16 |
|  |  | Legal Implications | I |  |  | Next Review Date | 31/10/15 |
|  |  | People | II |  |  | Date Closed |  |
| 3 | Loss of accommodation | Service Disruption | III | E | Remote working possible for some staff. Web based computer system. Service could be delivered from a satellite location – must have access for public | Requires Treatment | Yes |
|  |  | Financial Loss | I |  |  | Last Review Date | 13/10/15 |
|  |  | Reputation | III |  |  | Next Milestone Date | 01/03/16 |
|  |  | Legal Implications | II |  |  | Next Review Date | 31/10/15 |
|  |  | People | III |  |  | Date Closed |  |
| 4 | Fraudulent activity | Service Disruption | II | E | Web based system has an audit facility to monitor staff usage. Risk of fraud by the public | Requires Treatment | Yes |
|  |  | Financial Loss | II |  |  | Last Review Date | 13/10/13 |
|  |  | Reputation | III |  |  | Next Milestone Date | 01/03/16 |
|  |  | Legal Implications | II |  |  | Next Review Date | 31/10/15 |
|  |  | People | - |  |  | Date Closed |  |

| 5 | Loss of partner or agreed partnership funding (revenue or capital) | Service Disruption | III | E | Partnerships are under financial pressure | Requires Treatment | Yes |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Financial Loss | II |  |  | Last Review Date | 13/10/15 |
|  |  | Reputation | III |  |  | Next Milestone Date | 01/03/16 |
|  |  | Legal Implications | - |  |  | Next Review Date | 31/10/15 |
|  |  | People | - |  |  | Date Closed |  |
| b) Housing Service Risks |
| 6 | Loss of temporary accommodation provider (Lincoln Drive) | Service Disruption | III | E | Would result in higher dependency on B&B at higher cost to the Council. Working on new SLA with other providers and sought alternative hostel accommodation in Herts | Requires Treatment | Yes |
|  |  | Financial Loss | III |  |  | Last Review Date | 13/10/15 |
|  |  | Reputation | III |  |  | Next Milestone Date | 01/03/16 |
|  |  | Legal Implications | II |  |  | Next Review Date | 31/10/15 |
|  |  | People | - |  |  | Date Closed |  |

| Likelihood | A |  |  |  |  |  | Impact | Likelihood |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | B |  |  |  |  |  | V = Catastrophic | A = ≥98% |
|  | C |  |  |  |  |  | IV = Critical | B = 75% - 97% |
|  | D |  |  |  |  |  | III = Significant | C = 50% - 74% |
|  | E |  |  | 1, 2, 3, 4, 5, 6 |  |  | II = Marginal | D = 25% - 49% |
|  | F |  |  |  |  |  | I = Negligible | E = 3% - 24% |
|  |  | I | II | III | IV | V |  | F = ≤2% |
|  | Impact |  |  |