COMMUNITY SERVICES (HOUSING)

SERVICE PLAN

2017 - 2020

CONTENTS

| Section | Item | Page |
| --- | --- | --- |
|  | Introduction | 3 |
| 1 | Inputs | 3 |
| 1.1 | Budgets | 3 |
| 2 | Outputs and Outcomes | 5 |
| 2.1 | Performance management | 5 |
| 2.2 | Projects | 8 |
| 2.3 | Risk Management | 9 |
|  | Version Control | 12 |

INTRODUCTION

The progress of this service plan will be monitored in the following ways:

- Through regular discussion at departmental management team (DMT) and Section Heads meetings and logged in the version control section of this document

- Performance indicator monitoring by the Council’s Management Board on a quarterly basis

- By Committee reports twice a year (at the end of quarters two and four)

Service Plans will be formally updated on an annual basis, taking into account internal and external influences arising from monitoring arrangements throughout the year.

SECTION 1:	INPUTS

| 1.1 | Budgets |
| --- | --- |

|  | 2017/18 Latest | 2018/19 Latest | 2019/20 Latest |
| --- | --- | --- | --- |
|  | £ | £ | £ |
| Net Cost of Service (Direct Cost / Income only) | 1,689,230 | 1,222,140 | 1,437,950 |

Further financial analysis can be found by using this link

SECTION 2:	OUTPUTS AND OUTCOMES

| 2.1 | Performance management |
| --- | --- |

2.1.1	Contribution to the Councils’ Strategic Aims and Objectives

| Strategic Plan Priority theme | Strategic Plan objective (inc. ref) | Measure (including the reference) | Target |
| --- | --- | --- | --- |
| Better Neighbourhoods |  |  |  |
| Healthier Communities | 2.1.1. Improve or facilitate access to housing | HN06 – Promote access to private sector lettings with use of the Council Rent Deposit Guarantee Scheme New – provide additional temporary accommodation in the district New – measure time taken to make a decision on DFG following receipt of referral | 16 |

2.1.2 	Performance indicators

Performance indicators are used to aid the decision making process as well as assess the efficiency and effectiveness of service delivery. The data that we use must be accurate, reliable and timely. To meet these requirements we have adopted the Audit Commission’s Standards for Better Data Quality. Further details of the Council’s commitment to data quality can be found in the Strategic Plan.

| Ref | Description | 2015/16 Actual | 2016/17 Target (Current year) | 2017/18 Target (Next year) | 2018/19 Target | 2019/20 Target |
| --- | --- | --- | --- | --- | --- | --- |
| EH01 | Respond to pollution requests for service within 24 hours (Residential Environmental Health) | 99% | 94% | 95% | 95% | 96% |
| EH02 | NEW PI – Issue decision on DFG grant within 26 weeks following receipt of referral | New PI | New PI | 70% | 72% | 74% |
| HN01 | Maximum number of households living in temporary accommodation on the last day of the quarter (snapshot) | 53 | 50 | 120 | 155 | 185 |
| HN02 | Maximum number of families in Bed & Breakfast for more than six weeks # | 0 | 0 | 0 | 0 | 0 |
| HN03 | Maximum number of households in temporary accommodation throughout the year | New PI | 240 | 290 | 350 | 440 |
| HN06 | Promote access to private sector lettings through RDGS | 16 | 18 | 14 | 16 | 18 |
| HN07 | Process housing applications within 5 working days once all supporting information has been received from the applicant | 95.85% | 95% | 96% | 97% | 98% |
| HN08 | Housing applications received online rather than paper forms | 99% | 92% | 95% | 97% | 99% |
| HN09 | Homeless application decisions within 33 working days | 70.75% | 80% | 75% | 75% | 75% |
| HN10 | NEW PI - Number of households prevented from becoming homeless | New PI | New PI | 28 | 30 | 32 |

The Housing Services Manager is responsible for the source data, data entry and checking the data. The purpose of collating this data is to ensure that our services improve.

| 2.2 | Projects |
| --- | --- |

| Project details | Project timescales |
| --- | --- |
| Project title | Proposed outcome | 2017/18 | 2018/19 | 2019/20 |
| Gold Standard Challenges | Following peer review begin the 10 challenges, working through 1 challenge at a time to ultimately achieve gold status | Start Jan 2017 and achieve bronze by Jun 2017 | To achieve silver status by Jul 2018 | To finish approx Jul 2019 |
| Housing allocations policy review | To review current policy and implement recommendations for improvements and updates | Started Sep 2016 and end May 2017 |  |  |
| Progress provision of additional temporary accommodation (building/buying) | To increase provision of temporary accommodation for homeless households reducing the need of expensive private temporary accommodation | Started Oct 2015 | End Jul 2018 |  |
| Scope alternative models for procuring private rented for RDGS | To explore innovative means of sourcing private rented sector property and attracting landlords to the Council’s existing Rent Deposit Guarantee Scheme in an increasingly expensive and competitive market. | Start Apr 2017 and end Oct 2017 |  |  |
| Stock condition survey or similar | Stock condition survey required as seven years since the previous one and unclear true number of HMO’s within the district | Start Apr 2017 and end Oct 2017 |  |  |

| 2.3 | Risk Management |
| --- | --- |

RISK REGISTER

| Service Plan: Community Services (Housing) 2017-2020 |
| --- |
| Risk Ref | Risk | Impact | Impact Classification | Likelihood Classification | Reason for Assessment |  |  |
|  | Brief Description – Title of Risk | See Impact Table | See Impact Table | See Likelihood Table | Use this box to describe how the score has been derived |  |  |
| 1 | Insufficient staff | Service Disruption | III | E | Significant service disruption and failing of statutory duty would occur if there were insufficient staff. Priority services are identified in the Service Continuity Plan. | Requires Treatment | Yes |
|  |  | Financial Loss | II |  |  | Last Review Date | 13/10/15 |
|  |  | Reputation | III |  |  | Next Milestone Date | 15/11/17 |
|  |  | Legal Implications | III |  |  | Next Review Date | 15/11/17 |
|  |  | People | II |  |  | Date Closed | -- |
| 2 | Total failure of ICT systems | Service Disruption | III | E | Some services could continue without access to ICT systems for a short period. Priority services are identified in the Service Continuity Plan and Disaster Recovery Plan. | Requires Treatment | Yes |
|  |  | Financial Loss | II |  |  | Last Review Date | 13/10/15 |
|  |  | Reputation | III |  |  | Next Milestone Date | 15/11/17 |
|  |  | Legal Implications | I |  |  | Next Review Date | 15/11/17 |
|  |  | People | II |  |  | Date Closed | -- |
| 3 | Loss of accommodation | Service Disruption | III | E | Some services could operate from alternative locations. Must be customer facing service for statutory duty. Priority services are identified in the Service Continuity Plan. | Requires Treatment | Yes |
|  |  | Financial Loss | I |  |  | Last Review Date | 13/10/15 |
|  |  | Reputation | III |  |  | Next Milestone Date | 15/11/17 |
|  |  | Legal Implications | III |  |  | Next Review Date | 15/11/17 |
|  |  | People | II |  |  | Date Closed | -- |
| 4 | Fraudulent Activity | Service Disruption | II | E | Procedures are in place and regularly audited to deal with internal fraudulent activity. Also a risk of fraud from the public. | Requires Treatment | Yes |
|  |  | Financial Loss | II |  |  | Last Review Date | 13/10/15 |
|  |  | Reputation | III |  |  | Next Milestone Date | 15/11/17 |
|  |  | Legal Implications | I |  |  | Next Review Date | 15/11/17 |
|  |  | People | I |  |  | Date Closed | -- |
| 5 | Loss or insufficient temporary accommodation | Service Disruption | III | B | Statutory duty to provide temporary accommodation, current insufficient temporary accommodation | Requires Treatment | Yes |
|  |  | Financial Loss | III |  |  | Last Review Date | 13/10/15 |
|  |  | Reputation | III |  |  | Next Milestone Date | 15/05/17 |
|  |  | Legal Implications | III |  |  | Next Review Date | 15/11/17 |
|  |  | People | I |  |  | Date Closed | -- |
| 6 | Failure to provide out of hours emergency provision | Service Disruption | I | E | Statutory duty to provide out of hours emergency provision. Contracted to Hertsmere Council to provide service | Requires Treatment | Yes |
|  |  | Financial Loss | I |  |  | Last Review Date | N/A |
|  |  | Reputation | II |  |  | Next Milestone Date | 15/11/17 |
|  |  | Legal Implications | III |  |  | Next Review Date | 15/11/17 |
|  |  | People | I |  |  | Date Closed | -- |

| Likelihood | A |  |  |  |  |  | Impact | Likelihood |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | B |  |  | 5 |  |  | V = Catastrophic | A = ≥98% |
|  | C |  |  |  |  |  | IV = Critical | B = 75% - 97% |
|  | D |  |  |  |  |  | III = Significant | C = 50% - 74% |
|  | E |  |  | 1, 2, 3, 4, 6 |  |  | II = Marginal | D = 25% - 49% |
|  | F |  |  |  |  |  | I = Negligible | E = 3% - 24% |
|  |  | I | II | III | IV | V |  | F = ≤2% |
|  | Impact |  |  |

Version Control

| Version No. | Date | Reason for Update / Significant Changes | Made By |
| --- | --- | --- | --- |
| 1.0 | 03/10/16 | First Draft | KG |
| 2.0 | 05/10/16 | Update following team consultation | KG |
| 3.0 | 15/11/16 | Updated risk information | KG |
| 4.0 | 02/03/2017 | Added budgets | GG |