CUSTOMER SERVICES CENTRE

SERVICE PLAN

2016 – 2019

Version 1.0

CONTENTS

| Section | Item | Page |
| --- | --- | --- |
|  | Introduction | 3 |
| 1 | Inputs | 5 |
| 1.1 | Budgets | 5 |
| 2 | Outputs and Outcomes | 6 |
| 2.1 | Performance management | 6 |
| 2.2 | Projects | 8 |
| 2.3 | Risk Management | 9 |
|  | Version Control | 11 |

INTRODUCTION

The progress of this service plan will be monitored in the following ways:

- Through regular discussion at departmental management team (DMT) and Section Heads meetings and logged in the version control section of this document

- Performance indicator monitoring by the Council’s Management Board on a quarterly basis

- By Committee reports twice a year (at the end of quarters two and four)

KEY PURPOSE OF THE SERVICE

|  | Scope of the Service |
| --- | --- |
| The Customer Services Centre (CSC) is a department within the Community and Environment directorate. The CSC provides a front line service for the Council on behalf of all departments, supporting all Service and Corporate priorities contained within the Council’s Strategic Plan. The Technical Support section of CSC provides admin services on behalf of various council departments. - The CSC provides a quality service to all those who contact the Council via the Customer Services Centre. It aims to provide improved access and high levels of customer care for customers to all Council services and is resourced to meet customer access requirements via email, telephone and visitors. Performance is reported weekly. The CSC follows the Corporate Customer Care Standards Policy which is published on the Intranet and Council website. Customer Care is monitored within the CSC monthly by Team Mangers and through the use of Customer Satisfaction Surveys - Ensure that the service we provide is sustained and sustainable by supporting all our staff with appropriate training and the tools to do the job - Support all service departments in the provision of front line services and seek to ensure that the CSC remains ‘joined up’ with all departments - Continue to develop the service in line with corporate and service priorities - To seek to manage available resources to maximise the service that can be provided to the benefit of all. - Support all service departments in identifying and implementing service improvements. - Management of Corporate Complaints - to assist all Council departments to improve their services through managing complaints. - Management of the Council’s outsourced standby (out of hours emergency) service - Delivery of administrative duties on behalf of all Council departments – to improve efficiency & reduce costs. |  |

|  | Service Standards |
| --- | --- |
| The Service Standards below outline the level of service customers can expect and will be monitored and developed as appropriate. The Council’s corporate customer service standards will also be applied and are published in the Council’s Strategic Plan. |  |

| Service standards: our aims To provide a quality service to all those who contact the Council via the Customer Services Centre by: | How our standards are measured and monitored |
| --- | --- |
| Easy access to council services: Telephone target to answer 85% of calls within 20 seconds Visitors to Three Rivers House One Stop Shop (OSS) to have their enquiry attended to within 10 minutes Emails to provide initial response within 2 days; full response within 10 days | Telephone call answering rates are measured by CSC Automatic Call Distribution (ACD) system & reported weekly to the Resources Portfolio Holder & the Director of Corporate Resources & Governance. Visitor queues are monitored daily by CSC Management Team and resources reallocated to meet peaks. Emails received are monitored daily by CSC staff to ensure targets are met. Customer satisfaction with our performance in these areas is measured & monitored through rolling satisfaction surveys & analysing complaints Departments provide feedback on CSC performance at regular liaison meetings |
| Polite, friendly & helpful service | Telephone calls - CSC Team Managers regularly monitor & score all CSC staff to measure their performance in these areas. Feedback is provided in one-to-one meetings. Customer satisfaction with our performance in these areas is measured & monitored through rolling satisfaction surveys & analysing complaints Departments provide feedback on CSC performance at regular liaison meetings |
| Giving the correct information/service our customers require. | Telephone calls - CSC Team Managers regularly monitor & score all CSC staff to measure their performance in these areas. Feedback is provided in one-to-one meetings. CSC Team Managers liaise with all Council departments to identify service delivery shortfalls and to review CSC scripting and training requirements. Customer satisfaction with our performance in these areas is measured & monitored through rolling satisfaction surveys & analysing complaints. Departments provide feedback on CSC performance at regular liaison meetings |

Service Plans will be formally updated on an annual basis, taking into account internal and external influences arising from monitoring arrangements throughout the year.

SECTION 1:	INPUTS

| 1.1 | Budgets |
| --- | --- |

|  | 2016/17 Latest | 2017/18 Latest | 2018/19 Latest |
| --- | --- | --- | --- |
|  | £ | £ | £ |
| Net Cost of Service (Direct Cost / Income only) | 790,260 | 801,560 | 808,540 |

Further financial analysis can be found by using this link

SECTION 2:	OUTPUTS AND OUTCOMES

| 2.1 | Performance management |
| --- | --- |

2.1.1	Contribution to the Councils’ Strategic Aims and Objectives

| Strategic Plan Priority theme | Strategic Plan objective (inc. ref) | Measure (including the reference) | Target |
| --- | --- | --- | --- |
| Safety & Well-being | 1.1 We will work with partners to make the district a safer place 1.2 We will provide a safe and healthy environment 1.3 We reduce health inequalities will promote healthy lifestyles | CSC will provide Reception counter services at TRH on behalf of Herts Constabulary CP14 - Council initiatives will be supported through CSC scripting (ASB & graffiti reports) EHC04/05 – Tech Support will provide admin support to EH Commercial to assist the completion and recording of food premises inspections LL29 - CSC support all Leisure initiatives, providing information & taking bookings on activities at all venues | Support corporate targets |
| Clean & Green | 2.1 We want to maintain a high quality local environment | EP10 - We will ensure that waste is managed by supporting initiatives and collection rates through CSC processes & scripting EP06 - We will optimise recycling by supporting initiatives and collection rates through CSC processes & scripting CP01 – CSC will assist with ‘keeping public land clear of litter and refuse’ through CSC processes & scripting | Support corporate targets |
| Economic opportunities | 3.2 Prosperity for all and access to opportunities | CSC scripting (providing access to Benefits & Housing applications) | Support corporate targets |
| Customer Service | 4.1 We will deliver our services to a standard that meet the needs and expectations of all of our customers | CSC01 - Percentage of calls answered CSC02 - Percentage of calls answered within 20 seconds We will publish our standards on the website & in the One Stop Shop We will report on Complaints and identify service improvements CP05 - We will constantly review our processes and procedures to improve the customer experience We will improve capacity by identifying staff training requirements and delivering them Reduce average CSC sickness levels CSC03 - We aim to improve customer satisfaction levels. Survey results identify % of customers who felt that CSC staff did their best to be helpful | 97% 85% Support corporate targets 5.0 days 97% |

2.1.2 	Performance indicators

Performance indicators are used to aid the decision making process as well as assess the efficiency and effectiveness of service delivery. The data that we use must be accurate, reliable and timely. To meet these requirements we have adopted the Audit Commission’s Standards for Better Data Quality. Further details of the Council’s commitment to data quality can be found in the Strategic Plan.

| Ref | Description | 2014/15 Actual | 2015/16 Target (Current year) | 2016/17 Target (Next year) | 2017/18 Target | 2018/19 Target |
| --- | --- | --- | --- | --- | --- | --- |
| CS01 | % of calls answered | 97% | 97% | 97% | 97% | 97% |
| CS02 | % of calls answered within 20 secs | 72% | 85% | 85% | 85% | 85% |
| CS03 | Customer satisfaction with CSC service | N/A | 95% | N/A | 95% | N/A |

The Head of Customer Services is responsible for the source data, data entry and checking the data. The purpose of collating this data is to ensure that our services improve.

| 2.2 | Projects |
| --- | --- |

| - Project details |  | - Project timescales |  |  |
| --- | --- | --- | --- | --- |
| - Project title | - Proposed outcome | 2016/17 | 2017/18 | 2018/19 |
| CRM Replacement | Improved customer service & satisfaction, and more efficient use of corporate resources | Ongoing | Ongoing | Ongoing |

| 2.3 | Risk Management |
| --- | --- |

RISK REGISTER

| Service Plan: Customer Service Centre 2016-2019 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Customer Service Centre Risks |  |  |  |  |  |  |  |
| 1 | Insufficient staff | Service Disruption | IV | E | Could be covered initially with overtime and possibly hiring temp-staff. | Requires Treatment | Yes |
|  |  | Financial Loss | I |  |  | Last Review Date | 01/10/15 |
|  |  | Reputation | IV |  |  | Next Milestone Date | 01/10/16 |
|  |  | Legal Implications | II |  |  | Next Review Date | 01/10/16 |
|  |  | People | I |  |  | Date Closed | --/--/-- |
| 2 | Total failure of ICT systems | Service Disruption | III | E | Addressed in Service Continuity Plan | Requires Treatment | Yes |
|  |  | Financial Loss | III |  |  | Last Review Date | 01/10/15 |
|  |  | Reputation | III |  |  | Next Milestone Date | 01/10/16 |
|  |  | Legal Implications | III |  |  | Next Review Date | 01/10/16 |
|  |  | People | III |  |  | Date Closed | --/--/-- |
| 3 | Loss of accommodation | Service Disruption | III | E | Addressed in Service Continuity Plan | Requires Treatment | Yes |
|  |  | Financial Loss | III |  |  | Last Review Date | 01/10/15 |
|  |  | Reputation | III |  |  | Next Milestone Date | 01/10/16 |
|  |  | Legal Implications | III |  |  | Next Review Date | 01/10/16 |
|  |  | People | III |  |  | Date Closed | --/--/-- |
| 4 | Fraudulent activity | Service Disruption | II | E | Staff training & controls in place to reduce likelihood. Departmental controls in place | Requires Treatment | No |
|  |  | Financial Loss | I |  |  | Last Review Date | 01/10/15 |
|  |  | Reputation | II |  |  | Next Milestone Date | 31/10/15 |
|  |  | Legal Implications | I |  |  | Next Review Date | 31/10/15 |
|  |  | People | I |  |  | Date Closed | --/--/-- |
| 5 | Total failure of Telephone systems | Service Disruption | V | E | Addressed in Service Continuity Plan | Requires Treatment | Yes |
|  |  | Financial Loss | I |  |  | Last Review Date | 01/10/15 |
|  |  | Reputation | IV |  |  | Next Milestone Date | 01/10/16 |
|  |  | Legal Implications | II |  |  | Next Review Date | 01/10/16 |
|  |  | People | I |  |  | Date Closed | --/--/-- |

| 6 | Increased number of customer contacts | Service Disruption | IV | E | Could be covered initially with overtime and possibly hiring temp-staff. | Requires Treatment | Yes |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Financial Loss | II |  |  | Last Review Date | 01/10/15 |
|  |  | Reputation | IV |  |  | Next Milestone Date | 01/10/16 |
|  |  | Legal Implications | II |  |  | Next Review Date | 01/10/16 |
|  |  | People | I |  |  | Date Closed | --/--/-- |
| 7 | Robbery in TRH OSS | Service Disruption | II | E | Staff training & controls in place to reduce likelihood. No incidents since OSS opened | Requires Treatment | Yes |
|  |  | Financial Loss | I |  |  | Last Review Date | 01/10/15 |
|  |  | Reputation | II |  |  | Next Milestone Date | 01/10/16 |
|  |  | Legal Implications | I |  |  | Next Review Date | 01/10/16 |
|  |  | People | III |  |  | Date Closed | --/--/-- |
| 8 | Physical assault on staff or visitors to TRH | Service Disruption | I | E | Staff training & controls in place to reduce likelihood. No incidents since OSS opened | Requires Treatment | Yes |
|  |  | Financial Loss | I |  |  | Last Review Date | 01/10/15 |
|  |  | Reputation | II |  |  | Next Milestone Date | 01/10/16 |
|  |  | Legal Implications | I |  |  | Next Review Date | 01/10/16 |
|  |  | People | III |  |  | Date Closed | --/--/-- |

| Likelihood | A |  |  |  |  |  | Impact | Likelihood |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | B |  |  |  |  |  | V = Catastrophic | A = ≥98% |
|  | C |  |  |  |  |  | IV = Critical | B = 75% - 97% |
|  | D |  |  |  |  |  | III = Significant | C = 50% - 74% |
|  | E |  | 4 | 2, 3, 7, 8 | 1, 6 | 5 | II = Marginal | D = 25% - 49% |
|  | F |  |  |  |  |  | I = Negligible | E = 3% - 24% |
|  |  | I | II | III | IV | V |  | F = ≤2% |
|  | Impact |  |  |  |  |  |  |  |

Version Control

| Version No. | Date | Reason for Update / Significant Changes | Made By |
| --- | --- | --- | --- |
| 1.0 | 12/10/2015 | First Draft | BH |
| 2.0 |  | Second Draft following team consultation. |  |
| 3.0 | 29/02/2016 | Budget data included, section 1.1 | GG |