REVENUES AND BENEFITS

SERVICE PLAN

2016 – 2019

Head of Service : Robert Della-Sala

CONTENTS

| Section |  | Page |
| --- | --- | --- |
| 1 2 3 4 5 6 | Introduction Achievements in 2015/16 Departmental priorities for 2016/17 Service area priorities Challenges Monitoring the Service Plan | 3 3 5 6 7 7 |
| 7 | Inputs | 8 |
| 8 | Outputs and outcomes | 8 |
| 9 | Performance Indicators | 10 |
| 10 | Risk management | 13 |
| 11 | Version Control | 14 |

- INTRODUCTION

IT has been a significant challenge and problem with unsustainable down time on all the systems used by the team that has been a real barrier to increasing the pace of change. In many examples, change has stalled due to IT modules not being implemented or because systems have been too unreliable to use modules that are already in existence. Much effort has gone into migrating from 2003 servers to 2008 servers for both the Academy systems (revs and bens) and Anite  (document management system), as well as doing multiple upgrades to both systems so that they are now up to date. Progress has been made on a number of other IT projects, including stabalising the customer self-service portal and introducing e-billing for council tax and NNDR customers. However what has been demonstrated is that many of the structural and organisational problems that have beset the team have been managed out of the service, as evidenced by the improvement in almost all of the PI’s despite the IT. There is no reason why both Watford and Three Rivers should not be a top performing authority in 2016/16, if the IT can be finally resolved.

Below is list (though not exhaustive) of the work that has been achieved in the last 12 months. This has been year of re-building, stabalisation and achieving basic levels of service for customers.

- 2015/16 Achievements

2.1	General issues

•	All staff received an appraisal and key work objectives

•	Sickness Absence now being actively managed and continues to fall

•	Regular liaison meetings being held with the Housing Trusts

•	Regular Liaison meetings being held with Housing (WBC)

•	Regular Liaison being held with WBC and TRDC CSC

- Regular meeting with TRDC legal section on enforcement of debts

•	Performance monitoring introduced for revenues staff

•	Performance monitoring dashboards in place for all service areas

•	Procedural changes to maximise collection levels

- All audit reports completed and action arising have been actioned or are in progress

- Coherent process for complaints management and managing FOI requests

•	Revamped and review of all revenues and benefits web pages for TRDC and WBC

- Introduced telephone wallboards on the section for both revenues and benefits

- Calls answered both over 95% (from a low of 60% benefits and 80% council tax) for both revenues and benefits and waiting 	times reduced from over 20 minutes to less than 90 seconds

- Anite document management system updated to latest version in August 2015

2.2	Council Tax Achievements in 2015/16

•	Successful year end process for council tax with no known problems or errors in billing in 2015/16

•	Council tax write offs are being done monthly

•	VOA band changes and new properties registered weekly and no backlogs in issuing new/revised bills

•	Council tax bill and adjustments notices reviewed, updated and simplified having not been reviewed since the inception of 	shared services

•	Council tax credits are being actively managed

•	New contract and monitoring in place for Enforcement Agents (previously known as Bailiffs)

- In first 11 months of 2015/16 Council Tax arears have reduced by 32.6% (TRDC) and 30.7% (WBC)

- Introduced committal hearing surgeries for taxpayers to advise of committal if debts not settled

- Two successful committal hearings resulting in suspended sentence orders

- Successful year end process for council tax with no known problems or errors in billing in 2016/17

- Introduced Anite/Academy suppression module in March 2016 for council tax summons cases

- Self-service letters in council tax working from January 2016 for both councils

- E-billing fixed from December 2015 for both councils

2.3	NNDR Achievements in 2015/16

•	Successful year end process for council tax with no known problems or errors in billing in 2015/16

•	Successful winding up petition on Watford case resulting in a £173k debt being paid

- Worked with Watford council to prepare for the Watford BID in October 2015

- Implemented Analyse local to manage and forecast NNDR appeals

- In first 11 months of 2015/16 NNDR arrears have reduced by 47% (TRDC) and 44% (WBC)

- Undertaken a review of discretionary rate reliefs for both councils

- Successful year end process for business rates with no known problems or errors in billing in 2016/17

- Introduced Anite/Academy suppression module in March 2016 for council tax summons cases

- Self-service letters in NNDR working from January 2016 for both councils

- E-billing fixed from December 2015 for both councils

2.4	Sundry Debtors Achievements in 2015/16

•	Invoice templates and letters reviewed and refreshed on COA

•	Work started to work more closely with departments on managing outstanding invoices

•	Aged Debt analysis introduced on a monthly basis and departments chased regarding historic debts

- Bailiff collection increased by 21.3% for WBC and 15.2% for TRDC

2.5	HB Overpayments – Debtors Achievements in 2015/16

•	Reduced the number of outstanding invoices where customer is back on benefit and deductions from benefit restarted

•	Increased the number of Attachment of Earnings Order where customer no longer on benefits but is known to be employed

•	Exercise completed to up rate deduction amounts that had not been reviewed for a number of years

•	Overpayments recovery increased by 25.62% (TRDC) and 24.5% (WBC)

- Attachment of earnings orders increased from 15 (£16k) to 61 (£125k) TRDC; 133 for WBC (£202k)

2.6	Benefits Achievements in 2015/16

•	Successful year end process for housing benefit with no known problems or errors in billing in 2015/16

- Atlas files are up to date and over 50% of files are now automated

•	RTI downloads started October 2014 and are up to date

- Claim form redesigned and updated

- On line claim form (BECS) introduced in November 2015

- Level of LA error overpayments for Watford and Three Rivers below 0.54% at February 2016 and will attract subsidy for first 	time

- Successfully bid for FERIS funding for both councils in March 2016

- QA module in Academy now working

- Self-service letters in benefits working from January 2016 for both councils

- Successful year end process for council tax with no known problems or errors in billing in 2016/17

- Departmental priorities in 2016/17

3.1	2016/17 will be a re-launch of the phase two of the modernisation programme for Revenues and Benefits and we are not complacent about the task ahead of us. As well as building on the work done in 2014/15 and 2015/16, we must now focus on bringing “added value” to our services. In addition, we have a number of identified major projects to be undertaken in 2016/17 which are listed below but is not an exhaustive list :

•	Introduction of AUDDIS paperless direct debits for WBC wil go live in April 2016

•	Focus on QA and reducing overpayments

•	Review all processes to stream line and make them efficient and effective

•	Improve on our PIs in all areas

•	Focus on customer service in general and how to improve, i.e., channel shift

3.2	We have identified a number of distinct IT projects including that will require implementation including :

•	Re-launch of self service for customers and landlords

•	introduce “trusted third party access” for the CAB

•	VOA interface / integration

- Building Inspection module for CTAX and NNDR

- Service area priorities

For each Service Area we have identified, after discussion with staff, areas for development and service improvement which are listed 	below.

4.1	Revenues (Council Tax, NNDR and Sundry Debtors)

•	Maximising revenues collection for council tax and NNDR

- Further focus on arrears collection

- Targeted use of charging orders, possession orders and committals

- Direct Debit take up campaign

- Campaign to increase usage of self-service for council tax and NNDR

- Review and consult on changes to the council tax reduction scheme, to be effective from 1/4/17, in light of other benefit 	changes which could result in increase expenditure for both councils on Council tax reduction

4.2	Benefits

•	Introduce risk based (FERIS) interventions for change in circumstances to reduce fraud and error

- Promote and encourage use of on line claims form

- Roll out DHP on line claim form

- Roll out of on-line change of circumstances module

- Promote greater use and take up of self-service with landlords and claimants

- Challenges

From 1s June 2016 there will be a new Head of Service in post. They will have a significant role in formulating the procurement of the new IT contract to support revenues and benefits after the Capita contract ends on 30/6/16.  Regardless of this, the service is extremely reliant of IT to not only manage and process claims, but for managing the paperwork. In order to deliver our aims and objectives for 2016/17 we have identified the following challenges :

•	IT upgrades and hardware road map modernisation agenda

•	Stable IT platform

•	Government legislative changes

- Welfare reform and continued roll out of universal Credit

•	Economic environment and caseload profile changes

•	Effective management of staff and staff performance

•	Management and Introduction of a Business Improvement District in WBC

- Monitoring the Service Plan

The progress of this service plan will be monitored in the following ways:

- Through regular discussion at departmental management teams and at Section Heads meetings and logged in the version control section of this document

- Performance indicator monitoring by the Council’s Management Board on a quarterly basis

- By Committee reports twice a year (at the end of quarters two and four)

Service Plans will be formally updated on an annual basis, taking into account internal and external influences arising from monitoring arrangements throughout the year.

7:	INPUTS

| 7.1 | Budgets |
| --- | --- |

|  |  | 2016/17 | 2017/18 | 2018/19 |
| --- | --- | --- | --- | --- |
|  |  | Latest | Latest | Latest |
|  | Net Cost of Service (Direct cost / Income Only) | 1,319,000 | 1,328,880 | 1,341,990 |

Further financial analysis can be found by using this link

8.	Outputs and Outcomes

| 8.1 | Performance management |
| --- | --- |

8.2	Contribution to Three Rivers’ Councils’ Strategic Aims and Objectives

| Strategic Plan Priority theme | Strategic Plan objective | Measure | Target |
| --- | --- | --- | --- |
| Economic opportunities | Ensure businesses and council tax payers are properly advised what discounts they are entitled to. Reducing their liability for NNDR and Council Tax increases their spending power which is of benefit to the wider local economy. Ensuring people do not get discounts they are not entitled to reduce the burden on other rate and tax payers. | Council Tax collection rates NNDR collection rates | 97.5% 99.7% |
| Customer Service | Processing benefit claims on time and accurately ensures claimants can budget accordingly. This reduces complaints and overpayments by processing change of circumstances. | New claim processing time Change of circumstances processing time | 22 days 15 days |

8.3	Contribution to Watford Councils’ Strategic Aims and Objectives

| Strategic Plan Priority theme | Strategic Plan objective | Measure | Target |
| --- | --- | --- | --- |
| Making Watford a better place | Work with Watford Community Housing Trust, the CAB , Housing and other agencies to reduce homelessness by ensuring benefits are paid on time Support the Watford Business Improvement District implementation if successful from October 2015 by managing the billing arrangements etc. | Council Tax collection rates NNDR collection rates | 96% 97% |
| Operating the Council efficiently and effectively | Processing benefit claims on time and accurately ensures claimants can budget accordingly. This reduces complaints and overpayments by processing change of circumstances. We will support and enable the Council and its’ services to meet it’s objectives. | New claim processing time Change of circumstances processing time | 22 days 15 days |

9 	Performance indicators

Performance indicators are used to aid the decision making process as well as assess the efficiency and effectiveness of service delivery. The data that we use must be accurate, reliable and timely. To meet these requirements we have adopted the Audit Commission’s Standards for Better Data Quality. Further details of the Council’s commitment to data quality can be found in the Strategic Plan.

| Service Area | Description of target | 2015/16 Feb 16 | 2016/17 Target |
| --- | --- | --- | --- |
| Housing Benefit | Av time to process housing benefits claims (from date of claim) | 18 (TRDC) 20 (WBC) | 22 days (to 31/1/16) |
| Housing Benefit | Av time to process change of circumstances | 10 (TRDC) 13 (WBC) | 15 days (to 31/1/16) |
| Housing Benefit | Accuracy of Financial assessments of HB cases in payment | n/a | 90% |
| Council Tax | Collection rates of council tax (against profiled target) | 94.59% | WBC 95.5% |
| Council Tax | Collection rates of council tax (against profiled target) | 97.02% | TRDC 97.5% |
| Council Tax | Time taken to register new liabilities as are result of notifications from VOA | 100% | 90% within 10 days |
| Business Rate (NNDR) | Collection rates of NNDR (against profiled target) | 95.4% | WBC 97.3% |
| Business Rate (NNDR) | Collection rates of NNDR (against profiled target) | 97.0% | TRDC 99.7% |
| Business Rates (NNDR) | Time taken to process any changes affecting NNDR liability including rate reliefs | 100% | 90% within 10 days |
| Business Rates (NNDR) | Time taken to register new liabilities as are result of notifications from VOA | 100% | 90% within 10 days |
| Business Rates (NNDR) | Time taken to set up a Direct Debit | 100% | 100% within 2 days |
| HB Overpayments | % of HB overpayments recovered in year | 93.71% TRDC 94.14 WBC | >92.5% |
| HB Overpayments | % of all HB overpayments recovered as a % of total outstanding overpayments | 29.89% TRDC 30.77% WBC | >20% |
| HB Overpayments | % of overpayments classified as "LA error | 0.39% WBC 0.39% TRDC | <0.54% (to 31/1/16) |
| Overpayments and sundry debtors | % of invoices raised within 10 days of a debt being received | n/a | 100% |
| Sundry debtors | Value of total outstanding invoices >2 months <12 months old compared to total raised in a rolling 12 month period | 1% TRDC 2% WBC | <3% of total outstanding debt under 12 months old |
| Sundry debtors | Value of total outstanding invoices over 12 months | 9% TRDC 7% WBC | <10% of total outstanding debt |

The Head of Revenues and Benefits is responsible for the source data, data entry and checking the data. The purpose of collating this data is to ensure that our services improve.

| 10. | Projects |
| --- | --- |

| - Project details |  | - Project timescales |  |  |
| --- | --- | --- | --- | --- |
| - Project title | - Proposed outcome | 2015/16 | 2016/17 | 2017/18 |
| Introduce Auddis for Watford |  |  |  |  |
| Manage new processes for NNDR BID |  |  |  |  |

| 10. | Risk Management |
| --- | --- |

RISK REGISTER

| Service Plan: Revenues and Benefits Plan 2015-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Ref | Risk | Impact | Impact Classification | Likelihood Classification | Reason for Assessment |  |  |
|  | Brief Description – Title of Risk | See Impact Table | See Impact Table | See Likelihood Table | Use this box to describe how the score has been derived |  |  |
| 1 | Insufficient staff | Service Disruption | III | E |  | Requires Treatment | Yes |
|  |  | Financial Loss | III |  |  | Last Review Date | 19/7/14 |
|  |  | Reputation | IV |  |  | Next Milestone Date | 1/4/15 |
|  |  | Legal Implications | IV |  |  | Next Review Date | 31/10/15 |
|  |  | People | - |  |  | Date Closed | dd/mm/yy |
| 2 | Total failure of ICT systems | Service Disruption | V | A |  | Requires Treatment | Yes/No |
|  |  | Financial Loss | IV |  |  | Last Review Date | dd/mm/yy |
|  |  | Reputation | IV |  |  | Next Milestone Date | dd/mm/yy |
|  |  | Legal Implications | III |  |  | Next Review Date | dd/mm/yy |
|  |  | People | - |  |  | Date Closed | dd/mm/yy |
| 3 | Loss of accommodation | Service Disruption | III | E |  | Requires Treatment | Yes/No |
|  |  | Financial Loss | - |  |  | Last Review Date | dd/mm/yy |
|  |  | Reputation | - |  |  | Next Milestone Date | dd/mm/yy |
|  |  | Legal Implications | - |  |  | Next Review Date | dd/mm/yy |
|  |  | People | III |  |  | Date Closed | dd/mm/yy |
| 4 | Fraudulent activity | Service Disruption | III | E |  | Requires Treatment | Yes/No |
|  |  | Financial Loss | III |  |  | Last Review Date | dd/mm/yy |
|  |  | Reputation | IV |  |  | Next Milestone Date | dd/mm/yy |
|  |  | Legal Implications | IV |  |  | Next Review Date | dd/mm/yy |
|  |  | People | - |  |  | Date Closed | dd/mm/yy |

| 5 | Failure of Academy or Anite DIP System | Service Disruption | V | A |  | Requires Treatment | Yes/No |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Financial Loss | V |  |  | Last Review Date | dd/mm/yy |
|  |  | Reputation | V |  |  | Next Milestone Date | dd/mm/yy |
|  |  | Legal Implications | IV |  |  | Next Review Date | dd/mm/yy |
|  |  | People | III |  |  | Date Closed | dd/mm/yy |

| Likelihood | A |  |  |  |  |  | Impact | Likelihood |  | Enter Risk number in the profiling grid (left) against the highest impact classification for the risk and the appropriate likelihood classification taken from the table above. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | B |  |  |  |  |  | V = Catastrophic | A = ≥98% |  |  |
|  | C |  |  |  |  |  | IV = Critical | B = 75% - 97% |  |  |
|  | D |  |  |  |  |  | III = Significant | C = 50% - 74% |  |  |
|  | E |  |  |  |  |  | II = Marginal | D = 25% - 49% |  |  |
|  | F |  |  |  |  |  | I = Negligible | E = 3% - 24% |  |  |
|  |  | I | II | III | IV | V |  | F = ≤2% |  |  |
|  | Impact |  |  |  |  |  |  |  |  |  |

Version Control

Example

| Version No. | Date | Reason for Update / Significant Changes | Made By |
| --- | --- | --- | --- |
| 1 | 14/10/15 | First version |  |
| 2 | 15/10/15 | Updated achievements | RDS |
| 3 | 22/10/15 | Updated Pis | RDS |
| 4 | 4/3/16 | Updated Pis | RDS |
| 5 | 7/03/2016 | Budget info added, section 7.1 | GG |