## Sheet1
SOI Delegated Authority 210316
Item | Policy & Resources Committee | SO Scrutiny Board (Members) | SO Project Board (Officers)
1 | Receive headline progress reports | Review detailed progress reports & programme updates | Receive detailed progress reports & programme updates
|  | Review Risk Matrix | Agree Risk Matrix updates
Monitor DA obligations
Monitor planning progress
Receive asset management reports
Receive reports from Development Partners
Monitor Stakeholder activity (HCA, LEP, HCC, Parish Council)
2 | Scrutinise & approve budgetary changes (up or down) | Review financial projections & project accounts | Approve financial projections & project accounts
|  | Note acquisition activity (within budget) | Agree acquisition activity (within budget)
|  | Note minor changes to project resouces (within budget) | Recommend changes to project resouces (within budget)
3 | Approve major variations to project objectives or strategic direction | Review revised scheme proposals | Receive revised scheme proposals
|  | Review Communications & PR activity | Approve Communications & PR activity
4 | Approve new land appropriation requirements outside agreed policy | Note appropriation requirements | Set appropriation requirements
5 | Approve CPO resolution & recommend to Council | Monitor CPO progress | Receive detailed CPO updates
6 | Establish Community Board | Note reports from Community Board | Liaise with Community Board
7 | Support SOI at strategic & corporate level | Represent SOI in public forums
8 | Oversee political dimension of SOI & ensure Member support | Escalate issues to P&R Committee where necessary