Community Governance Review 2015/16 – Timetable (Subject to change)

| Stage | Action | Timeline | Outline of Action |
| --- | --- | --- | --- |
| 1. | Report to the Regulatory Services Committee | 2 December 2015 | The Committee recommends to Council the terms of reference of the Community Governance Review (CGR) |
| 2 | Report to Full Council | 7 December 2015 | Council determines the terms of reference of the CGR |
| 3 | Publish terms of reference | 10 December | Council publishes terms of reference and notifies stakeholders of the commencement of the review. |
| 4 | Phase 1 - Consultation period on the terms of reference (TofR will be published on the TRDC website. Hardcopies in TRDC reception and community centres. Comments back via the ‘consult’ email address) | 10 December to midday on 15 January 2016 | - electors in the un-parished area - Herts. County Council - Local MPs - Other Parish Councils - District councillors representing the un-parished area - Local residents’ and amenity groups operating within the un-parished area - Local businesses operating within the un-parished area |
| 5 | Consider responses to initial consultation | 18 January 2016 to 29 January 2016 | Consider submissions and prepare draft recommendations for report to Council |
| 6 | Working Party to meet to consider draft proposals | February 2016 |  |
| 7 | Public meetings held and questions / opinions sought via the TRDC website | February – March 2016 |  |
| 8 | Working Party to meet | 2 March 2016 |  |
| 9 | Regulatory Services Committee | 2 March 2016 | To agree the Terms of Reference and amended timetable |
| 10 | Working Party to meet | 14 March 2016 |  |
| 11 | Officers to prepare draft proposals | 23 March 2016 to 9 May 2016 | This is Purdah period prior to the Election on the 5th May 2016 |
| 12 | Report to full Council | 17 May 2016 | Council to receive details of outcome of initial consultation and consider draft recommendations |
| 13 | Regulatory Services Committee to agree final proposals | Late May 2016 (If required) |  |
| 14 | Publish draft recommendations | 15 June 2016 | Council publishes draft recommendations |
| 15 | Possible Referendum | Late June / Early July 2016 | Scope of the Referendum to be confirmed |
| 16 | Consider responses to further consultation | 2 August 2016 to 19 August 2016 | Consider further submissions and results of Referendum. Prepare final recommendations for report to Council |
| 17 | Report to full Council | 5 September 2016 | Council to receive details of outcome of Referendum and make decision |
| 18 | Publish decision | 18 October 2016 | Publish decision |