## Overall
APPENDIX D
South Oxhey Initiative | 2014/15 |  |  |  | 2015/16 |  |  |  | 2016/17 |  |  |  | 2017/18 |  |  |  | 2018/19 |  |  |  | 2019/20 |  |  |  | 2020/21 |  |  |  | 2021/22 |  |  |  | 2022/23
Overall Programme | 2014 |  |  | 2015 |  |  |  | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
v 25/01/16 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Developer Procurement
Conditional Development Agreement
Planning Application
Planning Approval
Approve CPO Resolution
CPO Inquiry
CPO Decision & End Challenge Period
Vacant Possession
Satellite Sites
Henbury Way Car Park
Phase 1a (Garages & Car Park)
Phase 1b (Station Approach)
Phase 2a (Ox Pub site)
Phase 2b (North)
Phase 3 (South)
Construction
Satellite Sites
Henbury Way Car Park
Phase 1a (Garages & Car Park)
Phase 1b (Station Approach)
Phase 2a (Ox Pub site) (Blocks D,D1)
Phase 2b (North) (Blocks M,N,N1)
Phase 2b (North) (Blocks H,I)
Phase 3 (South) (Block O)
Phase 3 (South) (Block P,Q)
Phase 3 (South) (Block J,K,L)

## Detail
APPENDIX C
South Oxhey Initiative | 2014/15 |  |  | 2015/16 | [11 empty] | 2016/17 | [11 empty] | 2017/18 | [11 empty] | 2018/19
| 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018
Detail Programme | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
v 25/01/16 | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
Advice Procurement
Legal Services
Property Services
Project Board
Report to P&R Ctte
Establish Project Board
Approvals
P&R Committee approve Commercials
P&R Committee approve DA
Full Council approve Finances
Developer
Competitive Dialogue (PQQ 09/14)
Select Preferred Bidder
Commercial Negotiations
Development Agreement Negotiations
Exchange contract
Viability Appraisal
Design & Planning
Design process
Planning Application
Planning Consent
End Planning Challenge
Compulsory Purchase
Formulation
Resolution
Order
Objections
Inquiry
Decision/ Challenge Period
Vacant Possession
Satellite Sites
Henbury Way Car Park
Phase 1a (Car Park) (Blocks E,F,G,G1)
Phase 1b (Station Approach)
Phase 2a (Ox Pub site)
Phase 2b (North)
Phase 3 (South)
Construction
Satellite Sites
Henbury Way Car Park
Phase 1a (Car Park) (Blocks E,F,G,G1)
Phase 1b (Station Approach)
Phase 2a (Ox Pub site) (Blocks D,D1)
Phase 2b (North) (Blocks M,N,N1)
Phase 2b (North) (Blocks H,I)
Phase 3 (South) (Block O)
Phase 3 (South) (Block P,Q)
Phase 3 (South) (Block J,K,L)
| J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
| Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
| 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018