EXECUTIVE COMMITTEE – 12 JULY 2010

PART I - DELEGATED

11.	REVIEW OF STRATEGIC RISKS

(DCRG)

1.	Summary

1.1	This report gives details of progress against the Risk Treatment Plans for the Strategic Risks identified in the Strategic Plan 2010-13.

2.	Details

2.1	In accordance with the Council’s Risk Management Strategy, the Executive Committee determines which of the Council’s risks are ‘strategic’ and receives progress reports on their treatment.

2.2	The Council’s Strategic Plan 2010-2013, approved by Council on 16 February 2010, contained 7 strategic risks.  These risks, and the Service Plans in which they are managed, are listed below:

| Strategic Risk | Service Plan |
| --- | --- |
| 1) Failure to secure improvements to services | Leisure and Community Services |
| 2) Failure to tell residents about improvements | Corporate Services |
| 3) Failure to make progress on the sustainability action plan | Sustainability |
| 4) Failure to engage the community in the Strategic Plan | Leisure and Community Services |
| 5) Failure to achieve our access / equality targets | Leisure and Community Services |
| 6) Failure to achieve Community Safety targets | Leisure and Community Services |
| 7) Failure to achieve the priorities of the community strategy through the LSP | Leisure and Community Services |

2.3	The relevant Head of Service has reviewed the strategic risk(s) for which they are responsible and have updated their Risk Assessment and Treatment Plan(s).

2.4	Following the Diversity Peer Challenge assessment at the ‘achieving’ level of the Equality Framework for Local Government, it is proposed that strategic risk no 5 – “Failure to achieve our access/equality targets” be removed form the Strategic Risk Register.  It would still be included in the Leisure and Community Services Risk Register as an operational risk.

2.5	The updated Strategic Risk Register and the Assessment & Treatment Plans, with amendments shaded, are attached at Appendix 1.

3.	Options/Reasons for Recommendation

3.1	The Executive Committee is responsible for monitoring the treatment of strategic risks.

4.	Policy/Budget Reference and Implications

4.1	The recommendations in this report are within the Council’s agreed policy and budgets.

5.	Financial, Legal, Equal Opportunities, Staffing, Environmental, Community Safety, Customer Services Centre, Communications & Website, Risk Management and Health & Safety Implications

5.1	None specific.

6.	Recommendation

6.1	That the Executive Committee note the review of the Strategic Risk Register and approve the changes to the Risk Assessment & Treatment Plans.

6.2	That the strategic risk no 5 – ‘Failure to achieve our access / equality targets’ be removed from the Strategic Risk Register.

Report prepared by:	Phil King, Emergency Planning and Risk Manager

# Data Quality

Data sources: Risk Registers and Risk Assessment & Treatment Plans

Data checked by: Phil King, Emergency Planning and Risk Manager

Data Rating:

| 1 | Poor |  |
| --- | --- | --- |
| 2 | Sufficient | ( |
| 3 | High |  |

Background Papers

Strategic Plan 2010-2013

Risk Management Strategy

The recommendations contained in this report DO NOT constitute a KEY DECISION.

APPENDICES / ATTACHMENTS

Appendix 1 – Strategic Risk Register and Assessment & Treatment Plans

APPENDIX 1

STRATEGIC RISK REGISTER

| Risk Ref | Risk | Impact | Impact Classification | Likelihood Classification | Reason for Assessment |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Brief Description – Title of Risk | See Impact Table | See Impact Table | See Likelihood Table | Use this box to describe how the score has been derived |  |  |
| 1 | Failure to secure improvements to services | Service Disruption | II | E | The Council’s reputation for improving services would be at risk although the recent history of performance measures would suggest that the likelihood of significant failure is low | Requires Treatment | Yes |
|  |  | Financial Loss | I |  |  | Last Review Date | 30/06/10 |
|  |  | Reputation | III |  |  | Next Milestone Date | 31/12/10 |
|  |  | Legal Implications | I |  |  | Next Review Date | 31/10/10 |
|  |  | People | I |  |  | Date Closed | -- |
| 2 | Failure to tell residents about improvements | Service Disruption | I | D | The Council’s reputation might suffer if residents weren’t informed of the Council’s successes. The measure in place to inform residents of improvements (e.g. Three Rivers Times) reduces the likelihood of residents not being informed | Requires Treatment | Yes |
|  |  | Financial Loss | I |  |  | Last Review Date | 30/06/10 |
|  |  | Reputation | III |  |  | Next Milestone Date | 31/12/10 |
|  |  | Legal Implications | I |  |  | Next Review Date | 31/10/10 |
|  |  | People | I |  |  | Date Closed | -- |
| 3 | Failure to make progress on the sustainability action plan | Service Disruption | I | E | Having made sustainability one of the two ‘outward’ looking themes of the Strategic Plan, the Council’s reputation might suffer if the outcomes were not achieved. The Council is organising itself to meet this challenge and by putting greater emphasis on sustainability the likelihood of not progressing the plan is thought to be relatively low. | Requires Treatment | Yes |
|  |  | Financial Loss | II |  |  | Last Review Date | 30/06/10 |
|  |  | Reputation | IV |  |  | Next Milestone Date | 31/12/10 |
|  |  | Legal Implications | II |  |  | Next Review Date | 31/10/10 |
|  |  | People | I |  |  | Date Closed | -- |

| Risk Ref | Risk | Impact | Impact Classification | Likelihood Classification | Reason for Assessment |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Brief Description – Title of Risk | See Impact Table | See Impact Table | See Likelihood Table | Use this box to describe how the score has been derived |  |  |
| 4 | Failure to engage the community in the Strategic Plan | Service Disruption | I | E | The Council has established good consultation mechanisms which have been subject to the Diversity Peer Challenge and Customer Service Excellence accreditation. | Requires Treatment | Yes |
|  |  | Financial Loss | I |  |  | Last Review Date | 30/06/10 |
|  |  | Reputation | III |  |  | Next Milestone Date | 31/12/10 |
|  |  | Legal Implications | I |  |  | Next Review Date | 31/10/10 |
|  |  | People | I |  |  | Date Closed | -- |
| 5 | Failure to achieve our access / equality targets | Service Disruption | I | E | The Diversity Peer Challenge has assessed the Council as ‘Achieving’ against the Equality Framework for Local Government. Action Plan has been written and exception reporting occurring to Management Board as well as annual update to Resources Policy and Scrutiny Committee. Regular briefings with Champion and Leader on Progress. | Requires Treatment | No |
|  |  | Financial Loss | I |  |  | Last Review Date | 30/06/10 |
|  |  | Reputation | II |  |  | Next Milestone Date | -- |
|  |  | Legal Implications | I |  |  | Next Review Date | -- |
|  |  | People | I |  |  | Date Closed | -- |
| 6 | Failure to achieve Community Safety targets | Service Disruption | II | E | Strategy is on target, which should minimise risk. Public perception recognises improvement. | Requires Treatment | Yes |
|  |  | Financial Loss | I |  |  | Last Review Date | 30/06/10 |
|  |  | Reputation | III |  |  | Next Milestone Date | 31/12/10 |
|  |  | Legal Implications | I |  |  | Next Review Date | 31/10/10 |
|  |  | People | I |  |  | Date Closed | -- |
| 7 | Failure to achieve the priorities of the Community Strategy through the LSP | Service Disruption | I | E | PCT has identified budget for LSP. New priorities identified. LAA Performance Reward Grant is available for investment in priorities. | Requires Treatment | Yes |
|  |  | Financial Loss | I |  |  | Last Review Date | 30/06/10 |
|  |  | Reputation | III |  |  | Next Milestone Date | 31/12/10 |
|  |  | Legal Implications | I |  |  | Next Review Date | 31/10/10 |
|  |  | People | I |  |  | Date Closed | -- |

| Likelihood | A |  |  |  |  |  |  | Impact | Likelihood |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | B |  |  |  |  |  |  | V = Catastrophic | A = ≥98% |
|  | C |  |  |  |  |  |  | IV = Critical | B = 75% - 97% |
|  | D |  |  | 2 |  |  |  | III = Significant | C = 50% - 74% |
|  | E |  | 5 | 1,4,6,7 |  |  |  | II = Marginal | D = 25% - 49% |
|  | F |  |  |  |  |  |  | I = Negligible | E = 3% - 24% |
|  |  | I | II | III | IV | V |  |  | F = ≤2% |
|  | Impact |  |  |  |

RISK ASSESSMENT AND TREATMENT PLAN

| Risk Ref: | 1 | Risk Title: | Failure to secure improvements to services |
| --- | --- | --- | --- |
| Responsibility | Who is managing the risk? | Management Board |
| Consequence | What can go wrong? How can it go wrong? Has it gone wrong before? | There is a new set of Performance Indicators with no historic base Remaining PIs may dip PIs have suffered in periods of significant change |
| Cause / Trigger | What happens to bring the risk into being? | Quarterly report to Management Board and half-yearly report to Policy and Scrutiny Committees flags up failures to hit targets National quartile measures improve at quicker pace than improvements at TRDC |
| Existing Control | What controls exist now to minimise the risk? | Quarterly reporting to Management Board and half-yearly reporting to Committees Service Planning framework and Star Chamber exercise Benchmarking Internal Audits Value for Money Strategy Corporate Consultation Action Plan |
| Adequacy of Control | What evidence is there that the existing Controls are working? What would the Risk Rating be without the existing controls? | PIs have improved year on year for the past 3 years | Impact | Likelihood |
|  |  |  | III | D |
| Further Action / Controls Required | What gaps have been identified? What can be done to reduce the likelihood of something going wrong and/or reduce the Impact if something does go wrong? | Use of Resources assessment highlighted need to formalise value for money studies/reviews. The Value for Money Strategy has now been agreed and implemented. The CAA Framework has now been abolished by the Government Value for Money and Scrutiny Strategy to be implemented Place Survey has been on hold by Government. A local survey can be commissioned in partnership with other Hertfordshire authorities to maintain benchmarking of public perception measures |
| Cost / Resources | Are there cost / resource implications in achieving the further action above? | No additional resource requirements identified | £ |
| Current Status | What is the current position on introducing additional controls? What is the current Risk Rating | Additional controls to be completed during 2010 are to produce a public perception survey. Impact and probability have not changed since last review. CAA Organisational Statement will not be received due to abolishment | Impact | Likelihood |
|  |  |  | III | E |
| Critical Success Factor | How will you know that the action taken has worked? What will be the Risk Rating outcome with the new controls? | Consultation feedback should show perceived improvements PIs will improve | Impact | Likelihood |
|  |  |  | III | F |

RISK ASSESSMENT AND TREATMENT PLAN

| Risk Ref: | 2 | Risk Title: | Failure to tell residents about improvements |
| --- | --- | --- | --- |
| Responsibility | Who is managing the risk? | Communications Manager |
| Consequence | What can go wrong? How can it go wrong? Has it gone wrong before? | Poor response rates from hard to reach groups Stakeholders not understanding/valuing the services the Council provides Low levels of public satisfaction with the Council |
| Cause / Trigger | What happens to bring the risk into being? | Citizen’s Panel not representative of community Consultation methods fail to engage hard to reach groups Insufficient resources to engage hard to reach groups Hard to reach groups fail to remain engaged due to limited response from TRDC Messages unclear or garbled Responsive rather than proactive Distribution failures (Three Rivers Times) |
| Existing Control | What controls exist now to minimise the risk? | Corporate consultation data analysed by race, gender and disability Service lead consultations recommended good practice Regularly updated strategy and action plan with increased emphasis on quality controls Editorial Working Party reviews TRT and A-Z TRT distributor provides street by street delivery report and delivery quality checked with staff who live in the district TRT delivery reminder service implemented Annual focus groups for TRT, A-Z and priority issues Press release output and coverage targets in place Feedback mechanisms include Pensioners’ Forum, Youth Council, prize draw survey in democracy packs, surveys in TRT, surveys at key points of contact including Canal Festival and Benefit surgeries Communications team action plan produced annually and reviewed twice a year Cross-department communications group gives feedback three times a year Staff marketing and press release workshops held three times a year Web development workshops implemented and web editors now expected to attend cross-department communications group Audio version of Three Rivers Times actively distributed for visually impaired or those with reading difficulties Use of web analytics tools Internal Communications survey completed |
| Adequacy of Control | What evidence is there that the existing Controls are working? What would the Risk Rating be without the existing controls? | Customer Service Excellence accreditation Council recognised as good communicator by LGA | Impact | Likelihood |
|  |  |  | III | C |
| Further Action / Controls Required | What gaps have been identified? What can be done to reduce the likelihood of something going wrong and/or reduce the Impact if something does go wrong? | Communications focus groups to be held Continued resident focus groups for website development Overarching communications strategy for sustainability Telephone surveys on delivery of TRT |
| Cost / Resources | Are there cost / resource implications in achieving the further action above? | No additional resource requirements identified | £ |
| Current Status | What is the current position on introducing additional controls? What is the current Risk Rating | Additional controls to be completed during 2010/11. Impact and probability have not changed since last review | Impact | Likelihood |
|  |  |  | III | D |
| Critical Success Factor | How will you know that the action taken has worked? What will be the Risk Rating outcome with the new controls? | All key groups will be represented in consultation feedback. | Impact | Likelihood |
|  |  |  | III | E |

RISK ASSESSMENT AND TREATMENT PLAN

| Risk Ref: | 3 | Risk Title: | Failure to make progress on the sustainability action plan |
| --- | --- | --- | --- |
| Responsibility | Who is managing the risk? | Head of Sustainability |
| Consequence | What can go wrong? How can it go wrong? Has it gone wrong before? | The authority fails to lead by example on sustainable initiatives and does not provide the opportunities for residents to take advantage of, for example, energy saving measures Failure to resource the plan properly Lack of awareness of current initiatives New NIs have been introduced. The Council is at a high level already and a high base line may prove difficult to improve on |
| Cause / Trigger | What happens to bring the risk into being? | Monitoring reveals that the actions in the plan are not taking place and the targets are not being achieved Withdrawal of Government funding for home insulation schemes |
| Existing Control | What controls exist now to minimise the risk? | Action Plan for the development of Climate Change Strategy agreed Sustainability team has been set up Regular progress reports on strategy development reported to Sustainable Environment Policy and Scrutiny Committee Standing items for Cabinet/Management Board and Management Board meetings Partnership arrangements have been set up with the LSP Membership of the University of Herts Climate Change Group with bi-monthly meetings Information is provided via the “Our Climate Is Changing” website Local Climate Impacts Profile has been prepared and submitted to DEFRA |
| Adequacy of Control | What evidence is there that the existing Controls are working? What would the Risk Rating be without the existing controls? | Stakeholders are kept up to date on progress via regular reports Internal audits Submissions to DEFRA | Impact | Likelihood |
|  |  |  | IV | D |
| Further Action / Controls Required | What gaps have been identified? What can be done to reduce the likelihood of something going wrong and/or reduce the Impact if something does go wrong? | Continued monitoring of National Indicators (186 and 188) Seeking accreditation for ISO14001 by Autumn 2010 Continued promotion of Government (CERT) funding Continued development and promotion of the “Our Climate Is Changing” website |
| Cost / Resources | Are there cost / resource implications in achieving the further action above? | No additional resource requirements identified | £ |
| Current Status | What is the current position on introducing additional controls? What is the current Risk Rating | Additional controls to be completed during 2010/11. Impact and probability have not changed since last review | Impact | Likelihood |
|  |  |  | IV | E |
| Critical Success Factor | How will you know that the action taken has worked? What will be the Risk Rating outcome with the new controls? | Successful ISO14001 accreditation | Impact | Likelihood |
|  |  |  | IV | F |

RISK ASSESSMENT AND TREATMENT PLAN

| Risk Ref: | 4 | Risk Title: | Failure to engage the community in the Strategic Plan |
| --- | --- | --- | --- |
| Responsibility | Who is managing the risk? | Community Partnerships Manager |
| Consequence | What can go wrong? How can it go wrong? Has it gone wrong before? | Poor response rates from hard to reach groups Lack of consultation of community in priorities set by the Council |
| Cause / Trigger | What happens to bring the risk into being? | Citizen’s Panel not representative of community Consultation methods fail to engage hard to reach groups or the community in general Insufficient resources to engage hard to reach groups or the community in general Hard to reach groups fail to maintain engagement due to limited response from TRDC |
| Existing Control | What controls exist now to minimise the risk? | Corporate consultation data is analysed by race, gender, disability and household income Consultation best practice guidance updated for all services Corporate focus groups held with BME communities Research with young people on community safety Stakeholder engagement with low income groups, people with mental health and learning disabilities and low literacy groups Consultation Action Plan has been developed Pilot project for customer profiling is continuing Priorities for engagement have been identified Diversity Peer Challenge completed Customer Service Excellence accreditation of all services |
| Adequacy of Control | What evidence is there that the existing Controls are working? What would the Risk Rating be without the existing controls? | Evidence held on successful consultation and customer satisfaction | Impact | Likelihood |
|  |  |  | III | D |
| Further Action / Controls Required | What gaps have been identified? What can be done to reduce the likelihood of something going wrong and/or reduce the Impact if something does go wrong? | Maintain implementation of corporate Consultation Action Plan |
| Cost / Resources | Are there cost / resource implications in achieving the further action above? | No additional resource requirements identified | £ |
| Current Status | What is the current position on introducing additional controls? What is the current Risk Rating | Impact and probability have not changed since last review | Impact | Likelihood |
|  |  |  | III | E |
| Critical Success Factor | How will you know that the action taken has worked? What will be the Risk Rating outcome with the new controls? | All key groups represented in corporate consultation feedback. Risk could be closed. | Impact | Likelihood |
|  |  |  | III | F |

RISK ASSESSMENT AND TREATMENT PLAN

| Risk Ref: | 5 | Risk Title: | Failure to achieve our access / equality targets |
| --- | --- | --- | --- |
| Responsibility | Who is managing the risk? | Community Partnerships Manager |
| Consequence | What can go wrong? How can it go wrong? Has it gone wrong before? | Poor reputation for equal opportunities Challenge to CRE or CEHR |
| Cause / Trigger | What happens to bring the risk into being? | Corporate Equality Action Plan is not implemented on time Departments fail to implement their actions Insufficient resources to support implementation of action plan |
| Existing Control | What controls exist now to minimise the risk? | Annual reporting of Corporate Equality Performance to Resources P&SC External assessment against the Equality Framework for Local Government completed and valid until 2013 New Action Plan agreed Action Plan draft in response to Equality Act 2010 |
| Adequacy of Control | What evidence is there that the existing Controls are working? What would the Risk Rating be without the existing controls? | Limitations on corporate resources to support progress | Impact | Likelihood |
|  |  |  | III | D |
| Further Action / Controls Required | What gaps have been identified? What can be done to reduce the likelihood of something going wrong and/or reduce the Impact if something does go wrong? | Implement actions against gap analysis Joint work on Shared Services with Watford BC |
| Cost / Resources | Are there cost / resource implications in achieving the further action above? | No additional resource requirements identified | £ |
| Current Status | What is the current position on introducing additional controls? What is the current Risk Rating | Diversity Peer Challenge now completed | Impact | Likelihood |
|  |  |  | II | E |
| Critical Success Factor | How will you know that the action taken has worked? What will be the Risk Rating outcome with the new controls? | Assessed at the “achieving” level of the Equality Framework for Local Government. Performance reports to Policy and Scrutiny Committees and Management Board. Risk could be closed. | Impact | Likelihood |
|  |  |  | I | E |

RISK ASSESSMENT AND TREATMENT PLAN

| Risk Ref: | 6 | Risk Title: | Failure to achieve Community Safety targets |
| --- | --- | --- | --- |
| Responsibility | Who is managing the risk? | Community Safety Manager |
| Consequence | What can go wrong? How can it go wrong? Has it gone wrong before? | Ineffective target setting Resources not allocated to address actions Changes in systems for assessing the level of ASB and/or crime increases total count Initiatives fail to meet targets Public do not understand what work is being achieved |
| Cause / Trigger | What happens to bring the risk into being? | Strategy not translated into work programme for each partner Action Plan not monitored for impact and corrective action taken where needed MIDAS / other partnership monitoring systems fail Poor practice / enforcement by other agencies Residents misinformed and resulting perceptions does not demonstrate achievement of targets National media overshadows local campaign work on strategy Funding reduced or cut by HCC or Government |
| Existing Control | What controls exist now to minimise the risk? | Quarterly reports to Co-ordinating Group, Board and Executive Committee and 6 monthly reports to Leisure and Community Safety Policy and Scrutiny Committee District represented at Chief Officer Group and County Practitioners Group. Briefings held with CE and leader/portfolio holder Participation in Offender Management Group to share information on prolific and persistent offenders Partnership risk assessment completed Common equality impact assessment framework for projects Clarity of staffing commitments and match funding on joint projects Clarity of governance arrangements for LAA Clarity of equality compliance from all bidders for funding CRB checks from applicants for funding, where relevant Data Protection arrangements for non-statutory partners reviewed Review of CCTV processes completed Anti-social Behaviour Group in place Family Intervention pilot project in place |
| Adequacy of Control | What evidence is there that the existing Controls are working? What would the Risk Rating be without the existing controls? | Strategy over-achieved on targets Public perception has improved | Impact | Likelihood |
|  |  |  | III | D |
| Further Action / Controls Required | What gaps have been identified? What can be done to reduce the likelihood of something going wrong and/or reduce the Impact if something does go wrong? | Risk assessments to be done for projects at local and county levels Request business continuity and disaster recovery plans for county level projects Review performance of ASB initiatives in hotspot areas |
| Cost / Resources | Are there cost / resource implications in achieving the further action above? | No additional resource requirements identified | £ |
| Current Status | What is the current position on introducing additional controls? What is the current Risk Rating | Additional controls to be completed during 2010/11. Impact and probability have not changed since last review. | Impact | Likelihood |
|  |  |  | III | E |
| Critical Success Factor | How will you know that the action taken has worked? What will be the Risk Rating outcome with the new controls? | All actions achieved and targets reached as a result. Funding continues to be received by CSP and strategy is achieved in all target areas. Risk could be closed. | Impact | Likelihood |
|  |  |  | II | F |

RISK ASSESSMENT AND TREATMENT PLAN

| Risk Ref: | 7 | Risk Title: | Failure to achieve the priorities of the Community Strategy through the LSP |
| --- | --- | --- | --- |
| Responsibility | Who is managing the risk? | Community Partnerships Manager |
| Consequence | What can go wrong? How can it go wrong? Has it gone wrong before? | Failure to deliver on priorities of the Community Strategy by some partners Action Plans not effectively implemented |
| Cause / Trigger | What happens to bring the risk into being? | Changes in national targets by central government Changes in priorities of organisations covering larger geographical areas Budget limitations Poor development of Action Plans Limited buy-in to strategy by partners Impact of recession on local deprivation |
| Existing Control | What controls exist now to minimise the risk? | Action Plan updates in place for Community Safety, Housing, DCTP, Health Partnership, Poverty Action Group and Prosperity & Employment elements Regular briefing with Leader Quarterly meetings of the LSP Board LAA targets agreed Strategy reviewed against county targets Self-assessment of LSP completed New partnerships for Health, Poverty and Prosperous Employment established Performance reporting of all sub-partnerships to relevant Policy and Scrutiny Committee |
| Adequacy of Control | What evidence is there that the existing Controls are working? What would the Risk Rating be without the existing controls? | Gaps in Action Plans identified for action by LSP Board | Impact | Likelihood |
|  |  |  | III | E |
| Further Action / Controls Required | What gaps have been identified? What can be done to reduce the likelihood of something going wrong and/or reduce the Impact if something does go wrong? | Undertake risk assessments for each priority area when action plans completed and review Further risk assessment of LSP at stage that any partner changes, withdraws or identifies new targets Performance Reward Grant projects to be implemented Identify strategic PIs for the Community Strategy |
| Cost / Resources | Are there cost / resource implications in achieving the further action above? | No additional resource requirements identified | £ |
| Current Status | What is the current position on introducing additional controls? What is the current Risk Rating | Additional controls to be completed during 2010/11. Impact and probability have not changed since last review. | Impact | Likelihood |
|  |  |  | III | E |
| Critical Success Factor | How will you know that the action taken has worked? What will be the Risk Rating outcome with the new controls? | Progress made on all priorities by LSP. Partners remain committed to priorities of Community Strategy. Risk could be closed. | Impact | Likelihood |
|  |  |  | III | F |