EXECUTIVE COMMITTEE – 20 JUNE 2011

PART I - DELEGATED

11.	REVIEW OF STRATEGIC RISKS

(DCRG)

1.	Summary

1.1	This report gives details of progress against the Risk Treatment Plans for the Strategic Risks identified in the Strategic Plan 2011-14.

2.	Details

2.1	In accordance with the Council’s Risk Management Strategy, the Executive Committee determines which of the Council’s risks are ‘strategic’ and receives progress reports on their treatment.

2.2	The Council’s Strategic Plan 2011-2014, which was approved by Council on 22 February 2011, contained 6 strategic risks.  These risks, and the Service Plans in which they are managed, are listed below:

| Strategic Risk | Service Plan |
| --- | --- |
| 1) Failure to secure improvements to services | Leisure and Community Services |
| 2) Failure to tell residents about improvements | Corporate Services |
| 3) Failure to make progress on the sustainability action plan | Sustainability |
| 4) Failure to engage the community in the Strategic Plan | Leisure and Community Services |
| 5) Failure to achieve Community Safety targets | Leisure and Community Services |
| 6) Failure to achieve the priorities of the community strategy through the LSP | Leisure and Community Services |

2.3	The relevant Head of Service has reviewed the strategic risk(s) for which they are responsible and have updated their Risk Assessment and Treatment Plan(s).  There are no changes to the risk ratings.

2.4	The updated Strategic Risk Register and the Assessment & Treatment Plans, with amendments shaded, are attached at Appendix 1.

3.	Options/Reasons for Recommendation

3.1	The Executive Committee is responsible for monitoring the treatment of strategic risks.

4.	Policy/Budget Reference and Implications

4.1	The recommendations in this report are within the Council’s agreed policy and budgets.

5.	Financial, Legal, Equal Opportunities, Staffing, Environmental, Community Safety, Customer Services Centre, Communications & Website, Risk Management and Health & Safety Implications

5.1	None specific.

6.	Recommendation

6.1	That the Executive Committee note the review of the Strategic Risk Register and approve the changes to the Risk Assessment & Treatment Plans.

Report prepared by:	Phil King, Emergency Planning and Risk Manager

# Data Quality

Data sources: Risk Registers and Risk Assessment & Treatment Plans

Data checked by: Phil King, Emergency Planning and Risk Manager

Data Rating:

| 1 | Poor |  |
| --- | --- | --- |
| 2 | Sufficient | ( |
| 3 | High |  |

Background Papers

Strategic Plan 2011-2014

Risk Management Strategy

The recommendations contained in this report DO NOT constitute a KEY DECISION.

APPENDICES / ATTACHMENTS

Appendix 1 – Strategic Risk Register and Assessment & Treatment Plans

# APPENDIX 1

# STRATEGIC RISK REGISTER

| Risk Ref | Risk | Impact | Impact Classification | Likelihood Classification | Reason for Assessment |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Brief Description – Title of Risk | See Impact Table | See Impact Table | See Likelihood Table | Use this box to describe how the score has been derived |  |  |
| 1 | Failure to secure improvements to services | Service Disruption | II | E | Data fails to be captured due to decrease in resources and outcomes cannot be demonstrated to residents or members. | Requires Treatment | Yes |
|  |  | Financial Loss | I |  |  | Last Review Date | 31/05/11 |
|  |  | Reputation | III |  |  | Next Milestone Date | 30/09/11 |
|  |  | Legal Implications | I |  |  | Next Review Date | 17/10/11 |
|  |  | People | I |  |  | Date Closed | -- |
| 2 | Failure to tell residents about improvements | Service Disruption | I | E | The Council’s reputation might suffer if residents weren’t informed of the Council’s successes. The measure in place to inform residents of improvements (e.g. Three Rivers Times) reduces the likelihood of residents not being informed | Requires Treatment | Yes |
|  |  | Financial Loss | I |  |  | Last Review Date | 01/06/11 |
|  |  | Reputation | III |  |  | Next Milestone Date | 30/09/11 |
|  |  | Legal Implications | I |  |  | Next Review Date | 17/10/11 |
|  |  | People | I |  |  | Date Closed | -- |
| 3 | Failure to make progress on the sustainability action plan | Service Disruption | I | E | Having made sustainability one of the two ‘outward’ looking themes of the Strategic Plan, the Council’s reputation might suffer if the outcomes were not achieved. | Requires Treatment | Yes |
|  |  | Financial Loss | II |  |  | Last Review Date | 04/05/11 |
|  |  | Reputation | IV |  |  | Next Milestone Date | 30/09/11 |
|  |  | Legal Implications | II |  |  | Next Review Date | 17/10/11 |
|  |  | People | I |  |  | Date Closed | -- |
| 4 | Failure to engage the community in the Strategic Plan | Service Disruption | I | E | Data fails to be captured due to decrease in resources and outcomes cannot be demonstrated to residents or members | Requires Treatment | Yes |
|  |  | Financial Loss | I |  |  | Last Review Date | 31/05/11 |
|  |  | Reputation | III |  |  | Next Milestone Date | 30/09/11 |
|  |  | Legal Implications | I |  |  | Next Review Date | 17/10/11 |
|  |  | People | I |  |  | Date Closed | -- |
| 5 | Failure to achieve Community Safety targets | Service Disruption | II | E | Strategy continues to meet majority of targets. Individual targets not met are being addressed by local action plans. | Requires Treatment | Yes |
|  |  | Financial Loss | I |  |  | Last Review Date | 31/05/11 |
|  |  | Reputation | III |  |  | Next Milestone Date | 30/09/11 |
|  |  | Legal Implications | I |  |  | Next Review Date | 17/10/11 |
|  |  | People | I |  |  | Date Closed | -- |

| Risk Ref | Risk | Impact | Impact Classification | Likelihood Classification | Reason for Assessment |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Brief Description – Title of Risk | See Impact Table | See Impact Table | See Likelihood Table | Use this box to describe how the score has been derived |  |  |
| 6 | Failure to achieve the priorities of the Community Strategy through the LSP | Service Disruption | I | D | Loss of 50% of the Performance Reward Grant reduces capacity for local projects. | Requires Treatment | Yes |
|  |  | Financial Loss | I |  |  | Last Review Date | 31/05/11 |
|  |  | Reputation | III |  |  | Next Milestone Date | 30/09/11 |
|  |  | Legal Implications | I |  |  | Next Review Date | 17/10/11 |
|  |  | People | I |  |  | Date Closed | -- |

The above risks are plotted on the matrix below depending on the scored assessments of impact and likelihood, detailed definitions of which are included in the risk management strategy. The Council has determined its aversion to risk and is prepared to tolerate risks where the combination of impact and likelihood are plotted in the shaded area of the matrix. The remaining risks require a treatment plan.

| Likelihood | A |  |  |  |  |  | Impact | Likelihood |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | B |  |  |  |  |  | V = Catastrophic | A = ≥98% |
|  | C |  |  |  |  |  | IV = Critical | B = 75% - 97% |
|  | D |  |  | 6 |  |  | III = Significant | C = 50% - 74% |
|  | E |  |  | 1, 2, 4, 5 | 3 |  | II = Marginal | D = 25% - 49% |
|  | F |  |  |  |  |  | I = Negligible | E = 3% - 24% |
|  |  | I | II | III | IV | V |  | F = ≤2% |
|  | Impact |  |  |

All the risks that require management and monitoring are included in the appropriate service plans.

RISK ASSESSMENT AND TREATMENT PLAN

| Risk Ref: | 1 | Risk Title: | Failure to secure improvements to services |
| --- | --- | --- | --- |
| Responsibility | Who is managing the risk? | Community Partnerships Manager |
| Consequence | What can go wrong? How can it go wrong? Has it gone wrong before? | Management fail to monitor performance and address under performance and targets not met. Some service areas have failed. |
| Cause / Trigger | What happens to bring the risk into being? | Data fails to be captured to assess achievement of the Strategic Plan. Services fail to input data into performance management system. No action taken to address poor performance. Management and Members only monitoring performance. |
| Existing Control | What controls exist now to minimise the risk? | Performance monitoring system in place. Quarterly reports to management board and 6 monthly reports to Policy and Scrutiny Committees. Performance Improvement Officer. Performance plus being replaced. New procedure notes in place to manage performance data |
| Adequacy of Control | What evidence is there that the existing Controls are working? What would the Risk Rating be without the existing controls? | Majority of corporate targets are on track. Or being over achieved. | Impact | Likelihood |
|  |  |  | III | D |
| Further Action / Controls Required | What gaps have been identified? What can be done to reduce the likelihood of something going wrong and/or reduce the Impact if something does go wrong? | Annual review of targets with Heads of Service. Improvements to shared services performance management systems in collaboration with Watford Borough Council. |
| Cost / Resources | Are there cost / resource implications in achieving the further action above? | Staff time. | £ 0 |
| Current Status | What is the current position on introducing additional controls? What is the current Risk Rating | New system developed and being implemented. Strategic plan reviewed with Heads of Service and Management Board. Improvement measured in corporate customer satisfaction through the Omnibus Survey. | Impact | Likelihood |
|  |  |  | III | E |
| Critical Success Factor | How will you know that the action taken has worked? What will be the Risk Rating outcome with the new controls? | Strategic plan targets achieved. Customer satisfaction improves. | Impact | Likelihood |
|  |  |  | II | F |

RISK ASSESSMENT AND TREATMENT PLAN

| Risk Ref: | 2 | Risk Title: | Failure to tell residents about improvements |
| --- | --- | --- | --- |
| Responsibility | Who is managing the risk? | Communications Manager |
| Consequence | What can go wrong? How can it go wrong? Has it gone wrong before? | Poor response rates from hard to reach groups Stakeholders not understanding/valuing the services the Council provides Low levels of public satisfaction with the Council |
| Cause / Trigger | What happens to bring the risk into being? | Citizen’s Panel not representative of community Consultation methods fail to engage hard to reach groups Insufficient resources to engage hard to reach groups Messages unclear or garbled Responsive rather than proactive Distribution failures (Three Rivers Times) |
| Existing Control | What controls exist now to minimise the risk? | Corporate consultation data analysed by race, gender and disability Regularly updated strategy and action plan with increased emphasis on quality controls Editorial Working Party reviews TRT and A-Z TRT distributor provides GPS tracking of delivery teams and delivery quality checked with staff who live in the district TRT delivery reminder service implemented Annual focus groups for TRT, A-Z and priority communications issues Press release output and coverage targets in place Feedback mechanisms include Pensioners’ Forum, Youth Council, prize draw survey in democracy packs, welcome packs for new residents, surveys in TRT and at key points of contact. Communications team action plan produced annually and reviewed twice a year Staff marketing and press release workshops held three times a year Web development workshops implemented and web editors now expected to attend cross-department communications group Audio version of Three Rivers Times actively distributed for visually impaired or those with reading difficulties Use of web analytics tools Internal Communications survey completed Monthly “What’s On” poster placed on noticeboards and distributed to community venues Increased use of social media, including Twitter, Facebook and e-newsletters |
| Adequacy of Control | What evidence is there that the existing Controls are working? What would the Risk Rating be without the existing controls? | Customer Service Excellence accreditation Council recognised as good communicator by LGA Omnibus survey (wave 1 & 2) shows 79% of respondents felt they were well informed or fairly well informed about Council services | Impact | Likelihood |
|  |  |  | III | C |
| Further Action / Controls Required | What gaps have been identified? What can be done to reduce the likelihood of something going wrong and/or reduce the Impact if something does go wrong? | Communications and resident focus groups to be held Overarching communications strategy for sustainability Telephone surveys on delivery of TRT |
| Cost / Resources | Are there cost / resource implications in achieving the further action above? | No additional resource requirements identified | £ |
| Current Status | What is the current position on introducing additional controls? What is the current Risk Rating | Additional controls to be completed during 2011/12. Impact and probability have not changed since last review | Impact | Likelihood |
|  |  |  | III | E |
| Critical Success Factor | How will you know that the action taken has worked? What will be the Risk Rating outcome with the new controls? | All key groups will be represented in consultation feedback. | Impact | Likelihood |
|  |  |  | II | E |

RISK ASSESSMENT AND TREATMENT PLAN

| Risk Ref: | 3 | Risk Title: | Failure to make progress on the sustainability action plan |
| --- | --- | --- | --- |
| Responsibility | Who is managing the risk? | Head of Sustainability |
| Consequence | What can go wrong? How can it go wrong? Has it gone wrong before? | The authority fails to lead by example on sustainable initiatives and does not provide the opportunities for residents to take advantage of, for example, energy saving measures Failure to resource the plan properly Lack of awareness of current initiatives National Indicators have been abolished. The Council is at a high level already and a high base line may prove difficult to improve on if new Indicators are introduced. |
| Cause / Trigger | What happens to bring the risk into being? | Monitoring reveals that the actions in plan are not taking place and targets are not being achieved Withdrawal of Government funding for sustainable initiative subsidies |
| Existing Control | What controls exist now to minimise the risk? | Action Plan for the development of Climate Change Strategy agreed Sustainability team has been set up Regular progress reports on strategy development reported to SEPSC Standing items for Cabinet/Management Board and Management Board meetings Partnership arrangements have been set up with the LSP and Energy Savings Trust Membership of the University of Herts Climate Change Group with bi-monthly meetings Information is provided via the “Our Climate Is Changing” website Local Climate Impacts Profile has been submitted to DEFRA ISO14001 accreditation achieved (excluding Batchworth Depot) |
| Adequacy of Control | What evidence is there that the existing Controls are working? What would the Risk Rating be without the existing controls? | Stakeholders are kept up to date on progress via regular reports Internal audits Submissions to DEFRA | Impact | Likelihood |
|  |  |  | IV | D |
| Further Action / Controls Required | What gaps have been identified? What can be done to reduce the likelihood of something going wrong and/or reduce the Impact if something does go wrong? | Continued local monitoring of ex NI186 via Climate Change Partnership Annual audit and re-accreditation of ISO14001 – Due October, 2011 Seeking accreditation for ISO14001 for Batchworth Depot by early 2012 Continued promotion of Government (CERT) funding, whilst available Continued development and promotion of the “Our Climate Is Changing” website |
| Cost / Resources | Are there cost / resource implications in achieving the further action above? | No additional resource requirements identified | £ |
| Current Status | What is the current position on introducing additional controls? What is the current Risk Rating | Additional controls to be completed during 2010/11. Impact and probability have not changed since last review | Impact | Likelihood |
|  |  |  | IV | E |
| Critical Success Factor | How will you know that the action taken has worked? What will be the Risk Rating outcome with the new controls? | Successful ISO14001 accreditation for Batchworth Depot Successful ISO14001 re-accreditation | Impact | Likelihood |
|  |  |  | IV | F |

RISK ASSESSMENT AND TREATMENT PLAN

| Risk Ref: | 4 | Risk Title: | Failure to engage the community in the Strategic Plan |
| --- | --- | --- | --- |
| Responsibility | Who is managing the risk? | Community Partnerships Manager |
| Consequence | What can go wrong? How can it go wrong? Has it gone wrong before? | Poor engagement with hard to reach groups results in lack of evidence base to meet vulnerable group needs. Recent consultation has seen increase in engagement of key hard to reach groups. Loss of funding for engagement work. |
| Cause / Trigger | What happens to bring the risk into being? | Citizen’s panel becomes unrepresentative. Consultation methods fail to engage hard to reach groups. Insufficient resources to engage groups. Hard to reach groups fail to remain engaged due to lack of TRDC response to needs. |
| Existing Control | What controls exist now to minimise the risk? | Corporate consultation budget in place to support work. Panel membership updated each year. Response rates to surveys monitored. Joint work developed across county and locally with partners to reduce costs and increase overall engagement outcomes. Engagement in public engagement partnership. Diversity group with Thrive NHS HCC and Police in District. LGBT Partnership. County Omnibus survey. |
| Adequacy of Control | What evidence is there that the existing Controls are working? What would the Risk Rating be without the existing controls? | Improvement to joint working e.g. LGBT consultation. Follow up work with BME communities. New projects with people with mental health problems. Increased participation of people with learning disabilities. | Impact | Likelihood |
|  |  |  | III | D |
| Further Action / Controls Required | What gaps have been identified? What can be done to reduce the likelihood of something going wrong and/or reduce the Impact if something does go wrong? | Further joint work to engage low income groups and those with low literacy on area basis with partners’ agencies. Maintain Herts Omnibus under new Market Research call out contract. |
| Cost / Resources | Are there cost / resource implications in achieving the further action above? | Staff time | £ |
| Current Status | What is the current position on introducing additional controls? What is the current Risk Rating | Plans to increase joint working developed to reduce costs. Contractor in place for Herts Omnibus. Improvement in public perception that services are acting on the concerns of residents. | Impact | Likelihood |
|  |  |  | III | E |
| Critical Success Factor | How will you know that the action taken has worked? What will be the Risk Rating outcome with the new controls? | Increase in residents’ view that they can influence local decision making. Increase in residents satisfaction Increased understanding of the needs of hard to reach groups | Impact | Likelihood |
|  |  |  | III | F |

RISK ASSESSMENT AND TREATMENT PLAN

| Risk Ref: | 5 | Risk Title: | Failure to achieve Community Safety targets |
| --- | --- | --- | --- |
| Responsibility | Who is managing the risk? | Community Safety Manager |
| Consequence | What can go wrong? How can it go wrong? Has it gone wrong before? | Ineffective target setting Resources not allocated to address actions Changes in recording systems Initiatives fail to meet targets Public do not understand what work is being achieved Overall strategy has met strategic targets |
| Cause / Trigger | What happens to bring the risk into being? | Strategy not translated into plans for each partners’ agency Action Plan not monitored for impact and corrective action MIDAS / monitoring systems fail Poor practice and enforcement by partners Residents misinformed by national media Reduction in funding for partnership No joint risk management Lack of commitment of staffing resources from partners Lack of equality monitoring No business continuity or disaster recovery plans |
| Existing Control | What controls exist now to minimise the risk? | Quarterly reports to Community Safety Board and Co-ordination Group, Six monthly reports to Leisure and Community Safety Policy and Scrutiny Committee Briefings with CEO and portfolio holder Participation in Family Intervention Project, Offender Management Group and ASB Action Group Equality impact monitored |
| Adequacy of Control | What evidence is there that the existing Controls are working? What would the Risk Rating be without the existing controls? | Strategy overall is on target. Where individual targets not met new action plans have been put in place and targets revised annually. | Impact | Likelihood |
|  |  |  | III | D |
| Further Action / Controls Required | What gaps have been identified? What can be done to reduce the likelihood of something going wrong and/or reduce the Impact if something does go wrong? | Review all bids for sustainability. Assess risks of all partnership projects. Request clarity of staffing commitments from all partners through annual action plan. Request CRB checks for partnership funded projects where relevant. Request equality impact on all funding proposals. Health and safety terms to be given to all grants. Review data protection arrangements for non-statutory partners. Assess business continuity needs for all partnership projects. Implement shared ASB management system. Seek county clarity on funding sources. |
| Cost / Resources | Are there cost / resource implications in achieving the further action above? | Staff time. ICT support to implement new ASB system. | £ tbc |
| Current Status | What is the current position on introducing additional controls? What is the current Risk Rating | Grants reviewed, and sustainability proposals being reviewed. Dialogue started with LSP regarding funding sources. CRB checks requested where relevant. County funding cuts identified Health and safety terms provided with all grants Equality data gathered where relevant. | Impact | Likelihood |
|  |  |  | III | E |
| Critical Success Factor | How will you know that the action taken has worked? What will be the Risk Rating outcome with the new controls? | Targets of strategy met for year. Review new risks at that point. | Impact | Likelihood |
|  |  |  | III | F |

RISK ASSESSMENT AND TREATMENT PLAN

| Risk Ref: | 6 | Risk Title: | Failure to achieve the priorities of the Community Strategy through the LSP |
| --- | --- | --- | --- |
| Responsibility | Who is managing the risk? | Community Partnerships Manager |
| Consequence | What can go wrong? How can it go wrong? Has it gone wrong before? | Failure to deliver on the strategy by some partners Loss of resources to support achievement of the priorities. Action Plans not effectively implemented |
| Cause / Trigger | What happens to bring the risk into being? | Loss of national targets and funding streams. Changes in priorities of individual partners. Budget limitations. Poor development of action plans. Limited buy in to strategy by partners. |
| Existing Control | What controls exist now to minimise the risk? | Action Plan updates provided to board from all sub-partnerships. Key performance indicators being tracked. Regular briefings with Leader. Regular meeting of LSP Board. |
| Adequacy of Control | What evidence is there that the existing Controls are working? What would the Risk Rating be without the existing controls? | Progress made on key projects in the District. Challenge provided to poor performance. Board reviewing impact of CSR and new changes. Sustainability key decision element to project funding. | Impact | Likelihood |
|  |  |  | III | C |
| Further Action / Controls Required | What gaps have been identified? What can be done to reduce the likelihood of something going wrong and/or reduce the Impact if something does go wrong? | Complete review of LSP post CSR. Assess new sources of potential shared funding for local priorities. Maintain risk assessment of all proposals for funding and joint action. |
| Cost / Resources | Are there cost / resource implications in achieving the further action above? | Staff time. Partners funding and commitment. | £0 |
| Current Status | What is the current position on introducing additional controls? What is the current Risk Rating | Review of partnership has started to risk address future needs. Potential sources of funding identified by some LSP Partners for different projects. Risk assessment framework maintained. Public perception data demonstrates achievements in key priority areas of crime and sustainability. | Impact | Likelihood |
|  |  |  | III | D |
| Critical Success Factor | How will you know that the action taken has worked? What will be the Risk Rating outcome with the new controls? | Partnership achieves further progress on priorities in areas of deprivation in sustainable manor. | Impact | Likelihood |
|  |  |  | III | E |