## Expenditure
Appendix A - Original and Proposed schemes for the small leisure capital programme 2018/19 – 2023-24, including associated budgets
Year | Project | Original Budget Agreed | Revised Proposal | Difference | Notes
2018/19 | Skidmore Way, Rickmansworth | 50000 | 50000 | 0 | Procurement complete. Installation due to be completed by the end of July 2018
| Croxley Green Skate Park – removal of existing park and creation of new skate area | 232871 | 232871 | 0 | Agreed capital funding of £100k carried forward from 2017/18 and £100k from 2018/19, £32,871 S106 funding. Unsuccessful with Sport England Funding bid
| Leavesden Country Park | 0 | 100000 | 100000
| Chorleywood Play Area | 102320 | 0 |  | This is an estimate time based on planning approval, Section 38 approval, Parish Council approval
|  |  |  | -102320 | Delayed a year due to the process of submitting an application to the Planning Inspectorate (To commence 2019/20)
2018/19 Total |  | 385191 | 382871 | -2320
2019/20 | Denham Way, Maple Cross | 50000 | 0 | -50000 | Very small play area – toddler equipment
| The Swillet, Chorleywood | 50000 | 0 | -50000 | As agreed by Members in June 2016
| Chorleywood Play Area | 0 | 102300 | 102300 | Delayed a year (from 2018/19 to 2019/20) due to the process of submitting an application to the Planning Inspectorate
2019/20 Total |  | 100000 | 102300 | 2300
2020/21 | Leavesden Country Park | 100000 | 0 | -100000 | Upgrade existing play area.
| Denham Way, Maple Cross | 0 | 50000 | 50000 | Very small play area – toddler equipment
| The Swillet, Chorleywood | 0 | 50000 | 50000 | As agreed by Members in June 2016
Total 2020/21 |  | 100000 | 100000 | 0
2021/22 | Oxhey Playing Fields | 100000 | 0 | -100000 | Linked to the proposed new Management Plan and may include a new skate facility or play provision, dependent on community preference.
| General Upgrading of play areas | 0 | 100000 | 100000 | To upgrade elements within play areas refurbished since 2008
Total 2021/22 |  | 100000 | 100000 | 0
2022/23 | Oxhey Playing Fields | 0 | 100000 | 100000 | Linked to the proposed new Management Plan and may include a new skate facility or play provision, dependent on community preference.
| General Upgrading of play areas | 100000 | 0 | -100000 | To upgrade elements within play areas refurbished since 2008
Total 2022/23 |  | 100000 | 100000 | 0
2023/24 | Fearney Mead, Mill End | 50000 | 50000 | 0 | These would be smaller projects
| Lincoln Drive, South Oxhey | 50000 | 50000 | 0 | These would be smaller projects
Total 2023/24 |  | 100000 | 100000 | 0
Shortfall/ (Surplus) |  |  |  | -20

## Funding
Year | Codes
2018/19 | 7926 | Chorleywood Play Area | 102320