| ASTOR TITLE | Race Equality And Equalities Schemes Action Plan & Timescale |
| --- | --- |
| Aims & Intended Outcomes | To review list of functions, policies and proposed policies for relevance of the general statutory race equality duty by 31st May 2005 |
| Setting | Three Rivers District Council, Management Board |
| Target Group / Customers | Service Directors and all service managers |
| Objectives | Service directors and managers to complete review template for all policies (services), and proposed policies by 31st March 2005 (including services not listed on RES 20032006) To prioritise relevant functions, policies and proposed policies in relation to their relevance to race equality by 31st May 2005 To identify a 3 year Equalities impact assessment plan for 2005-2008 by 29th April 2005 To review the Race Equality Scheme 2003-2006 and agree any amendments for 2005-06 by 29th April 2005 To publish the revised RES by 31 May 2005 To implement a rolling programme of Equalities Impact Assessment Training for all service managers by 31st March 2005 |
| Resources | £2,500 consultancy and training fees (Corporate Development existing budget) Staff time – 3 days per service department Corporate Development – 10 days work |
| Monitoring | Progress against objectives and methods to be undertaken by Corporate Development. |
| Customer Results Indicators | All service departments have identified revised relevance of functions, policies and proposed policies. |
| Outcome Measures | TRDC is compliant with the Race Relations Act (Statutory Duties) Order 2001. Equalities impact assessment plan agreed for 2005-2008 Revising to race equality scheme identified for 2005-2006. |
| Method | Timescale | Resources | Performance Indicators | Outcome Indicators | Staff responsible |
| Circulate review template to all directors and service managers | By 17 March |  | Template circulated to all relevant staff with instructions | Staff able to undertake relevance test. | AS |
| Organise training and consultancy support on relevance test | By 18th March | £2,500 | Contractor identified and purchased | Consultancy support available to departmental staff | AS |
| Service directors and managers to complete review template for all policies (services), and proposed policies | 4th April | 1 day | Individual services and departments complete relevance test. | Draft revised list of functions, policies and future policies returned to Corporate development | DG TB FD PB SH |
| Service directors and managers to prioritise functions and policies for impact assessment over next 3 years. | 11th April | In above | Individual services and departments complete prioritisation exercise | Draft priorities submitted to Corporate development | DG TB FD PB SH |
| Draft equalities impact assessment plan to be circulated and agreed by all Directors. | 3 May | 3 days | Plan drafted and circulated. | Impact assessment plan agreed for 2005-2008 | AS |
| Identify draft amendments to RES and circulate to all directors for agreement | 17 May | 2 days | Revisions circulated. | Revisions agreed | AS |
| Publish revised RES, Equalities Impact Assessment Plan and review of relevance | 31 May | 2 days | Updated plans and schemes published | Members of the community engaged with TRDC equalities scheme and RES | AS KF |
| Rolling programme of Equalities Impact Assessment training provided to all staff | Ongoing | 2 days | Rolling training and development plan in place to support RES and Equalities Impact Plan | Staff are equipped to implement action plan and impact assessments | AS |
| Performance manage equalities impact assessment plan and race equality scheme | Quarterly |  | Quarterly reports provided to management board on progress. | All actions and impact assessments completed on time. Improvement in equality of service delivery – CPA assessment improved. | DG TB FD PB SH AS |