## AGS Aug 2016
APPENDIX 1
No. | Issue | Action | Resolved | Update
1 | The Disaster Recovery Plan is not current. The Council should take priority to ensure the kit list is updated and fit for purpose | The Council will ensure that the kit lists are updated and fit for purpose in conjunction with Capita who are responsible for Third party contracts for DR. Disaster Recovery and business continuity plans will be reviewed annually to ensure suitability, adequacy and effectiveness | No | All asset lists, including desktops, servers and network equipment have been updated and are managed by the Service Desk Provider. Procedures documents are currently being reviewed and updated. Revised Deadline: 31st October 2016 From the 1 July 2016 the council has let a new contract for ICT support. All controls in place from the new provider will be reviewed by internal audit as part of future audits.
2 | The lack of an effective testing strategy for Disaster Recovery may mean that gaps and defects in the plan may not be identified | Once the kit lists are updated, DR tests will take place on critical systems and their key dependencies | No | The testing will take place once the DR procurement has taken place, a requirement to undertake this is being built into the specification. Revised deadline: 31st December 2016 From the 1 July 2016 the council has let a new contract for ICT support. All controls in place from the new provider will be reviewed by internal audit as part of future audits.
3 | There is insufficient evidence from Capita Secure Information Solutions Ltd (CSIS) to support the closure of actions to address performance issues | The CSIS account Director will agree a clear formal process for completion and closure of incidents within their team and gain formal approval of this process from the Council | Yes | The contract with CSIS Ltd was terminated on 30th June 2016 - this action is now superceded.
4 | Key Performance Indicators (KPI's) and the inclusive Service Level Agreements are not being met, having been agreed by both parties and appropriate financial penalties Are not being enforced | Discussions between the Council and CSIS will take place once improvements have been observed with the delivery of ICT Shared Services. This should encompass the current KPI definitions and how they are measured with associated targets. This will include the amount of physical evidence deemed appropriate and sufficient to support closure of tickets | Yes | The contract with CSIS Ltd was terminated on 30th June 2016 - this action is now superceded.