EXECUTIVE COMMITTEE – 21 JULY 2008

PART I - DELEGATED

15.	REVIEW OF STRATEGIC RISKS

(DCRG)

1.	Summary

1.1	This report gives details of progress against the Risk Treatment Plans for the Strategic Risks identified in the Strategic Plan 2008-11 and any subsequently identified strategic risks.

2.	Details

2.1	In accordance with the Council’s Risk Management Strategy, the Executive Committee determines which of the Council’s risks are ‘strategic’ and receives progress reports quarterly on their treatment.

2.2	The Council’s Strategic Plan 2008-2011, approved by Council on 19 February 2008, contained 6 strategic risks.  These risks are:

1) Failure to secure improvements to services

2) Failure to tell residents about improvements

3) Failure to make progress on the sustainability action plan

4) Failure to engage the community in the Strategic Plan

5) Failure to achieve our access / equality targets

6) Failure to achieve Community Safety targets

2.3	At its meeting on 3 March 2008, the Executive Committee approved the Hertfordshire Draft Sustainable Community Strategy and resolved “that it be confirmed that not achieving the priorities of the community strategy through the LSP be treated as a strategic risk and be added to the Strategic Plan”.

2.4	The 6 strategic risks in the Strategic Plan 2008-2011 were included in the Corporate Development Service Plan. Since the publication of the Strategic Plan 2008-2011, the Council has undergone a restructure.  The table below shows which Service Plans now contain strategic risk(s).

| Strategic Risk | Service Plan |
| --- | --- |
| 1) Failure to secure improvements to services | Performance Management and Scrutiny |
| 2) Failure to tell residents about improvements | Performance Management and Scrutiny |
| 3) Failure to make progress on the sustainability action plan | Sustainability |
| 4) Failure to engage the community in the Strategic Plan | Leisure and Community Services |
| 5) Failure to achieve our access / equality targets | Leisure and Community Services |
| 6) Failure to achieve Community Safety targets | Leisure and Community Services |
| 7) Failure to achieve the priorities of the community strategy through the LSP | Leisure and Community Services |

2.5	The relevant Head of Service has reviewed the strategic risk(s) for which they are responsible and have updated their Risk Treatment Plan(s).  None of the impact or likelihood scores have changed from the original version contained in the Strategic Plan 2008-2011.

2.6	The updated Strategic Risk Register, Identification & Assessment Form and the associated Treatment Plans, with amendments shaded, are attached at Appendices 1, 2 and 3.

3.	Options/Reasons for Recommendation

3.1	The Executive Committee is responsible for monitoring the treatment of strategic risks.

4.	Policy/Budget Reference and Implications

4.1	The recommendations in this report are within the Council’s agreed policy and budgets.

5.	Financial, Legal, Equal Opportunities, Staffing, Environmental, Community Safety, Customer Services Centre, Communications & Website, Risk Management and Health & Safety Implications

5.1	None specific.

6.	Recommendation

6.1	That the Executive Committee note the review of the Strategic Risk Register and approve the changes to the Risk Treatment Plans

Report prepared by:	Phil King, Emergency Planning and Risk Manager

Background Papers

Strategic Plan 2008-2011

Risk Management Strategy

The recommendations contained in this report DO NOT constitute a KEY DECISION.

APPENDICES / ATTACHMENTS

Appendix 1 – Strategic Risk Register

Appendix 2 – Risk Identification & Assessment Form

Appendix 3 – Risk Treatment Plans

APPENDIX 1

RISK REGISTER TEMPLATE

| Risk Ref | Risk | Impact | Likelihood | Risk Tolerance Requires Treatment | Next Milestone Date | Next Review Date | Is the risk Strategic? |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Brief description – title of risk | Score from horizontal axis of profiling grid | Score from vertical axis of profiling grid | Yes – if score is above the shaded area on the profiling grid. No – if the score is in the shaded area | Dates that may effect the progress of this risk e.g. budgets, elections | All risks will be reviewed yearly. Some will require more regular review. | Final decision on strategic risks to be taken by Executive Committee |
| 1 | Failure to secure improvements to services | III | E | Yes | Oct 08 | Oct 08 | Yes |
| 2 | Failure to tell residents about improvements | III | D | Yes | Mar 09 | Oct 08 | Yes |
| 3 | Failure to make progress on the sustainability action plan | IV | E | Yes | Nov 08 | Oct 08 | Yes |
| 4 | Failure to engage the community in the Strategic Plan | III | E | Yes | Mar 09 | Oct 08 | Yes |
| 5 | Failure to achieve our access / equality targets | III | D | Yes | Mar 09 | Oct 08 | Yes |
| 6 | Failure to achieve Community Safety targets | III | E | Yes | Mar 09 | Oct 08 | Yes |
| 7 | Failure to achieve the priorities of the community strategy through the LSP | III | D | Yes | Mar 09 | Oct 08 | Yes |

| Likelihood | A |  |  |  |  |  | Impact | Likelihood |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | B |  |  |  |  |  | V = Catastrophic | A = >98% |
|  | C |  |  |  |  |  | IV = Critical | B = 75% - 98% |
|  | D |  |  | 2,5,7 |  |  | III = Significant | C = 50% - 75% |
|  | E |  |  | 1,4,6 | 3 |  | II = Marginal | D = 25% - 50% |
|  | F |  |  |  |  |  | I = Negligible | E = 2% - 25% |
|  |  | I | II | III | IV | V |  | F = <2% |
|  | Impact |  |  |

APPENDIX 2

RISK IDENTIFICATION AND ASSESSMENT FORM

|  | Risk | Vulnerability | Cause/Trigger | Impact | Impact Classification | Likelihood Classification |
| --- | --- | --- | --- | --- | --- | --- |
|  | Describe the Risk | What can go wrong? How can it go wrong? Has it gone wrong before? | What happens to bring the risk into being? | How serious would it be if the risk comes into being? | See Impact Table | See Likelihood Table |
| 1 | Failure to secure improvements to services | There will be a new set of performance indicators with no historic base. Remaining PIs might dip PIs have suffered in periods of significant change | Quarterly report to Committee flags up failure to hit targets. National quartile measures improve at quicker pace than improvement at TRDC | Service Disruption | II | E |
|  |  |  |  | Financial Loss | I |  |
|  |  |  |  | Reputation | III |  |
|  |  |  |  | Legal Implications | I |  |
|  |  |  |  | People | I |  |
|  |  |  |  | Performance Management & Scrutiny Service Plan The Council’s reputation for improving services would be at risk although the recent history of performance measures would suggest that the likelihood of significant failure is low. |
| 2 | Failure to tell residents about improvements | Poor response rates from hard to reach groups Stakeholders not understanding / valuing the services the Council provides Low levels of public satisfaction with the Council | Citizen’s panel not representative of community Consultation methods fail to engage hard to reach groups Insufficient resources to engage hard to reach groups Hard to reach groups fail to remain engaged due to limited response from TRDC. Messages unclear or garbled Responsive rather than proactive Distribution failures (Three Rivers Times) | Service Disruption | I | D |
|  |  |  |  | Financial Loss | I |  |
|  |  |  |  | Reputation | III |  |
|  |  |  |  | Legal Implications | I |  |
|  |  |  |  | People | I |  |
|  |  |  |  | Performance Management & Scrutiny Service Plan The Council’s reputation might suffer if residents weren’t informed of the council’s successes. The measures in place to inform residents of improvements (e.g. Three Rivers Times) reduces the likelihood of residents not being informed. |

RISK IDENTIFICATION AND ASSESSMENT FORM

|  | Risk | Vulnerability | Cause/Trigger | Impact | Impact Classification | Likelihood Classification |
| --- | --- | --- | --- | --- | --- | --- |
|  | Describe the Risk | What can go wrong? How can it go wrong? Has it gone wrong before? | What happens to bring the risk into being? | How serious would it be if the risk comes into being? | See Impact Table | See Likelihood Table |
| 3 | Failure to make progress on the sustainability action plan | The authority fails to lead by example on sustainable initiatives and does not provide the opportunities for residents to take advantage of, for example, energy saving measures. Failure to resource the plan properly. Lack of awareness of current initiatives. New PIs are to be introduced. The Council is likely to be at a high level already and a high base line may prove difficult to improve on. | Monitoring reveals that the actions in the plan are not taking place and the targets are not being achieved. | Service Disruption |  | E |
|  |  |  |  | Financial Loss |  |  |
|  |  |  |  | Reputation | IV |  |
|  |  |  |  | Legal Implications |  |  |
|  |  |  |  | People |  |  |
|  |  |  |  | Sustainability Service Plan Having made sustainability one of the two ‘outward’ looking themes of the Strategic Plan, the Council’s reputation might suffer if the outcomes were not achieved. The Council is organising itself to meet this challenge and by putting greater emphasis on sustainability the likelihood of not progressing the plan is thought to be relatively low. |
| 4 | Failure to engage the community in the Strategic Plan | Poor response rates from hard to reach groups | Citizen’s panel not representative of community Consultation methods fail to engage hard to reach groups Insufficient resources to engage hard to reach groups Hard to reach groups fail to remain engaged due to limited response from TRDC. | Service Disruption | I | E |
|  |  |  |  | Financial Loss | II |  |
|  |  |  |  | Reputation | III |  |
|  |  |  |  | Legal Implications | III |  |
|  |  |  |  | People | II |  |
|  |  |  |  | Leisure & Community Services Service Plan Panel membership monitored. Response rates monitored. BME consultation needs to be boosted. |

RISK IDENTIFICATION AND ASSESSMENT FORM

|  | Risk | Vulnerability | Cause/Trigger | Impact | Impact Classification | Likelihood Classification |
| --- | --- | --- | --- | --- | --- | --- |
|  | Describe the Risk | What can go wrong? How can it go wrong? Has it gone wrong before? | What happens to bring the risk into being? | How serious would it be if the risk comes into being? | See Impact Table | See Likelihood Table |
| 5 | Failure to achieve our access / equality targets | Poor reputation for equal opportunities. Challenge to CRE or CEHR. | Corporate Equality Action Plan is not implemented on time. Departments fail to implement their actions. Insufficient resources to support implementation of action plan. | Service Disruption | I | D |
|  |  |  |  | Financial Loss | I |  |
|  |  |  |  | Reputation | III |  |
|  |  |  |  | Legal Implications | I |  |
|  |  |  |  | People | I |  |
|  |  |  |  | Leisure & Community Services Service Plan Action plan has been written and exception reporting occurring to Management Board as well as annual update to Equal Opportunities Forum. Regular briefings with champion and leader on progress. |
| 6 | Failure to achieve Community Safety targets | Ineffective target setting Resources not allocated to address actions Changes in systems for assessing the level of ASB and/or crime increases total count. Initiatives fail to meet targets Public do not understand what work is being achieved. | Strategy not translated into work programme for each partner Action plan not monitored for impact and corrective action taken where needed. MIDAS / other partnership monitoring systems Poor practice / enforcement by other agencies. Residents misinformed and resulting BVPI survey does not demonstrate achievement of targets. National media over shadows local campaign work on strategy. Funding reduced or cut by HCC or Go-East | Service Disruption | II | E |
|  |  |  |  | Financial Loss | I |  |
|  |  |  |  | Reputation | IV |  |
|  |  |  |  | Legal Implications | III |  |
|  |  |  |  | People | IV |  |
|  |  |  |  | Leisure & Community Services Service Plan Community Safety Partnership is on target to meet decrease in all crimes for Community Safety Strategy 2005-2008. Currently there has been a 17% decrease on baseline measures, against a reduction target of 16%. Evidence would suggest a likelihood of failure at the lower end. Failure, though, could result in a critical impact for residents. |

RISK IDENTIFICATION AND ASSESSMENT FORM

|  | Risk | Vulnerability | Cause/Trigger | Impact | Impact Classification | Likelihood Classification |
| --- | --- | --- | --- | --- | --- | --- |
|  | Describe the Risk | What can go wrong? How can it go wrong? Has it gone wrong before? | What happens to bring the risk into being? | How serious would it be if the risk comes into being? | See Impact Table | See Likelihood Table |
| 7 | Failure to achieve the priorities of the community strategy through the LSP | Failure to deliver on priorities of the community strategy by some partners. Action plans not effectively implemented. | Changes in national targets by central government Changes in priorities of organisations covering larger geographical areas. Budget limitations Poor development of action plans Limited buy in to strategy by partners. | Service Disruption | I | D |
|  |  |  |  | Financial Loss | I |  |
|  |  |  |  | Reputation | III |  |
|  |  |  |  | Legal Implications | I |  |
|  |  |  |  | People | I |  |
|  |  |  |  | Leisure & Community Services Service Plan PCT is currently re-organising. Police merger now less likely. Both Police and PCT are driven by national targets. LAA now dominating funding decisions – confirmed by White Paper. |

APPENDIX 3

RISK TREATMENT PLAN

| Risk Ref. | Risk | Existing Control | Adequacy of Control | Further Action Required | Responsibility | Critical Success Factor | Key Dates | Review Date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | As described on the risk identification and assessment form above | What controls exist now to minimise the risk? | What evidence is there that the existing controls are working? What would the risk rating be without the existing controls? | What gaps have been identified? What can be done to reduce the likelihood of something going wrong or reduce the impact if something does go wrong? | Who is managing the risk? | How will you know that the action taken has worked? What will be the rating outcome with the new controls? | Milestones |  |
| 1 | Failure to secure improvements to services | Quarterly reporting to Committee. Service planning framework. Star Chamber exercise. Benchmarking | PIs have improved year on year for the past three years. Risk without these controls would be (III D) | Use of resources assessment has highlighted need to formalise value for money studies / reviews. | Management Board | Direction of Travel Statements will provide external judgement. Consultation feedback should show perceived improvements. PIs will improve. (Aim to achieve III F) | Quarterly Monitoring reports | Oct 2008 |
| 2 | Failure to tell residents about improvements | Corporate consultation data analysed by race, gender and disability as a minimum. Service lead consultations recommended good practice. Regularly updated strategy and action plan with increased emphasis on quality controls Editorial Working Party reviews TRT “New” Communications team formed | Poor response rates from BME communities, and young people. Member perceptions Number of “positive hits” in local press | Continue to review response rates and recommend alternative consultation methods to review. | Management Board | All key groups represented in corporate consultation feedback. | End of each financial year | Oct 2008 |

RISK TREATMENT PLAN

| Risk Ref. | Risk | Existing Control | Adequacy of Control | Further Action Required | Responsibility | Critical Success Factor | Key Dates | Review Date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | As described on the risk identification and assessment form above | What controls exist now to minimise the risk? | What evidence is there that the existing controls are working? What would the risk rating be without the existing controls? | What gaps have been identified? What can be done to reduce the likelihood of something going wrong or reduce the impact if something does go wrong? | Who is managing the risk? | How will you know that the action taken has worked? What will be the rating outcome with the new controls? | Milestones |  |
| 3 | Failure to make progress on the sustainability action plan | Action Plan for the development of Climate Change Strategy agreed Sustainability Team has been set up. Regular progress reports on strategy development reported to Sustainable Environment Policy and Scrutiny Committee. Standing items for Cabinet/Board and Management Board meetings. | Stakeholder kept up to date on progress via regular reports. | Set up partnership arrangements with LSP Monitoring National Indicators (186 and 188). | Head of Sustainability | Climate Change Strategy approved and published in Autumn 2009 | Quarterly monitoring report (Nov 08) | Oct 2008 |
| 4 | Failure to engage the community in the Strategic Plan | Corporate consultation data analysed by race, gender and disability as a minimum. Service lead consultations recommended good practice. Corporate focus groups held with BME communities Research with young people on community safety | Evidence held on successful consultation. | Continue to review response rates and implement corporate Consultation Action Plan | Community Partnerships Manager | All key groups represented in corporate consultation feedback. | End of each financial year | Oct 2008 |

RISK TREATMENT PLAN

| Risk Ref. | Risk | Existing Control | Adequacy of Control | Further Action Required | Responsibility | Critical Success Factor | Key Dates | Review Date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | As described on the risk identification and assessment form above | What controls exist now to minimise the risk? | What evidence is there that the existing controls are working? What would the risk rating be without the existing controls? | What gaps have been identified? What can be done to reduce the likelihood of something going wrong or reduce the impact if something does go wrong? | Who is managing the risk? | How will you know that the action taken has worked? What will be the rating outcome with the new controls? | Milestones |  |
| 5 | Failure to achieve our access / equality targets | Quarterly exception reporting on Corporate Equality Plan to Management Board and annual reporting to EO Forum. External support for review against revised Equality Framework commissioned | Limitations on corporate resources to support progress. | Gap analysis report to Management Board in October 2008 | Community Partnerships Manager | Equivalent of Level 3 under the revised framework to be achieved in 2009/10 | End of each financial year | Oct 2008 |
| 6 | Failure to achieve Community Safety targets | Quarterly reports to Co-ordinating Group, Board and Executive Committee and 6 monthly reports to Leisure & Community Safety Policy and Scrutiny Committee. District represented at Chief Officer Group, County Practitioners Group and Safer Stronger Block group. Briefings held with CEO and leader/portfolio holder. Participation in YISP to develop individual action plans across agencies for youths at risk of offending. Participation in Offender Management Group to share information on prolific and persistent offenders. Partnership risk assessment completed. Monitoring impact of actions on targets and bids for resources for revenue requirements reviewed. Common equality impact assessment framework for projects. Clarity of staffing commitments and match funding on joint projects. Clarity of governance arrangements for LAA. CRB checks from applicants for funding, where relevant. Clarity of equality compliance from all bidders for funding. Health & Safety terms added to funding terms. Data Protection arrangements for non-statutory partners reviewed. | Strategy over achieved on targets. Risk of funding withdrawal or put off. | Risk assessments to be done for projects at local and county level. Request business continuity and disaster recovery plans for County level projects. Review CCTV processes once pilot is completed. | Community Partnerships Manager | All actions achieved and targets achieved as a result. Funding continues to be received by CDRP and strategy is achieved in all target areas. | End of each financial year | Oct 2008 |

RISK TREATMENT PLAN

| Risk Ref. | Risk | Existing Control | Adequacy of Control | Further Action Required | Responsibility | Critical Success Factor | Key Dates | Review Date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | As described on the risk identification and assessment form above | What controls exist now to minimise the risk? | What evidence is there that the existing controls are working? What would the risk rating be without the existing controls? | What gaps have been identified? What can be done to reduce the likelihood of something going wrong or reduce the impact if something does go wrong? | Who is managing the risk? | How will you know that the action taken has worked? What will be the rating outcome with the new controls? | Milestones |  |
| 7 | The priorities of the Community Strategy are not achieved through the LSP. | Action plan updates in place for Community Safety, Housing and DCTP elements. Regular briefing with leader. Quarterly meetings of the LSP Board. Handover arrangements agreed at all critical times. LAA targets agreed. Strategy reviewed against County targets. Self-assessment of LSP completed. | Gaps in action plans identified for action by LSP Board | Undertake risk assessment for each priority area when action plans completed and review. Further risk assessment of LSP at stage that any partner changes, withdrawals or identifies new targets. | Community Partnerships Manager | Progress made on all priorities by LSP. Partners remain committed to priorities of Community Strategy. | End of each financial year | Oct 2008 |