EXECUTIVE COMMITTEE – 3 DECEMBER 2012

SUSTAINABLE ENVIRONMENT POLICY AND SCRUTINY COMMITTEE – 6 NOVEMBER 2012

PART I – DELEGATED

9c. 	REVISED LOCAL DEVELOPMENT SCHEME FOR THE LOCAL PLAN (DCES)

This is not a KEY DECISION

1.	Summary

1.1		To advise the Committee about proposed changes to the project timetable for the Local Plan (previously known as the Local Development Framework). This is set out in a revised Local Development Scheme (LDS).

2.	Details

2.1	As part of the Local Plan process, the Council is required to prepare an LDS under the provisions of the Planning and Compulsory Purchase Act 2004. The LDS is a project plan which sets out the timescales for the Local Plan documents to be produced. It also identifies any risks to the process and how those risks might be mitigated.

2.2	The Council’s first LDS was submitted in April 2005 and subsequently revised in March 2007, February 2010 and September 2011.

2.3	It is now necessary to review the LDS again to reflect the delays in the production of the Site Allocations Local Development Document (due to additional consultation being undertaken) and the subsequent delays in the production of the Development Management Policies LDD and the Gypsy, Traveller & Travelling Showpeople LDD.

2.4               The implications of these changes are included in the revised LDS (Appendix 1).  The Committee’s attention is drawn to Appendix 2, which summarises the key milestones in the production of the Local Plan documents.

3.	Options/Reasons for Recommendation

3.1	The Council is required to prepare and regularly review an LDS under the provisions of the Planning and Compulsory Act 2004 as amended by the Localism Bill 2011. An up-to-date LDS is an essential tool for the Council to effectively manage document production and for monitoring to take place.

4.	Policy/Budget Reference and Implications

4.1	The risk implications to the Council are set out fully in Sections 12 of the attached draft LDS (Appendix 1). The Development Plans Service Plan 2012-2015 reflects the staffing and financial matters set out in the revised LDS. The recommendations in this report are within the Council’s agreed policy as set down in the Strategic Plan to prepare the Local Plan (Local Development Framework) to promote the theme of Sustainable Communities.

5.	Financial Implications

5.1	The financial implications are set out in the attached draft revised LDS. The preparation of the Local Plan will be met by the existing revenue budget for Development Plans.

6.	Legal Implications

6.1	As set out in paragraphs 2.1 and 3.1, the Council is, at present, legally required	to have an LDS in place. Failure to have one in place could ultimately lead to

legal action and/or Government intervention.

7.	Equal Opportunities Implications

7.1	Relevance Test

| Has a relevance test been completed for Equality Impact? | Yes |
| --- | --- |
| Did the relevance test conclude a full impact assessment was required? | No |

7.2	Impact Assessment

What actions were identified to address any detrimental impact or unmet need?

None required.

8.	Staffing Implications

8.1	These are set out in the attached draft LDS. The work scheduled for the Local Plan will be carried out largely by the Development Plans Service working with other parts of the Council and other stakeholders. The continued use of consultants will also be necessary to assist with technical work.

9.	Environmental Implications

9.1	The Local Plan will promote the Council’s priority to maintain a high quality local environment and reduce the carbon footprint of the District. The draft LDS also refers to the need for each relevant document of the Local Plan to be tested by a sustainability appraisal process so that any environmental impacts of policies can be minimised.

10.	Community Safety Implications

10.1	None specific.

11.	Customer Services Centre Implications

11.1	The CSC has been briefed to respond to requests for information on the Local Plan generally.

12.	Communications and Website Implications

12.1	Information about the Local Plan is included on the Council’s web site. The revised LDS will also be made available on the website once approved by the Government. This will include a basic summary version.

13.	Risk Management and Health & Safety Implications

13.1	The Council has agreed its risk management strategy which can be found on the website at http://www.threerivers.gov.uk.  In addition, the risks of the proposals in the report have also been assessed against the Council’s duties under Health and Safety legislation relating to employees, visitors and persons affected by our operations.  The risk management implications of this report are detailed below and within Section 13 of the draft LDS in Appendix 1.

13.2	The subject of this report is covered by the Development Plans service plan.  Any risks resulting from this report will be included in the risk register and, if necessary, managed within this plan.

13.3	The following table gives the risks if the recommendation(s) are agreed, together with a scored assessment of their impact and likelihood:

| Description of Risk | Impact | Likelihood |
| --- | --- | --- |
| 1 | Staffing levels may not be sufficient to take forward the Local Plan | IV | D* |
| 2 | Skills shortages may have an impact on the Local Plan programme. | III | E |
| 3 | Inadequate funding could affect the meeting of key milestones in the LDS, lead to a policy vacuum and increased risk of appeals and awards of costs against the Council. | IV | D* |
| 4 | The Planning Inspectorate may challenge the ‘soundness’ of Local Plan documents leading to delay and additional costs. | III | E |
| 5 | Delays in the Local Plan programme may be experienced as a result of the democratic process. | III | D |
| 6 | Baseline information used for the ‘evidence base’ may become out dated leading to challenge | III | E |
| 7 | The ability/capacity of stakeholders to input into the Local Plan process may be limited leading to potential delay and challenge | III | D |
| 8 | The ability/capacity of the Planning Inspectorate to deal with the examination process may lead to delays | III | E |
| 9 | Complications in the examination process may lead to delays in the process and increased costs | III | D |
| 10 | The ability/capacity of consultants to undertake sustainability appraisals and other technical work may lead to delay and challenge | III | E |
| 11 | Complications/delay in the use of Local Plan software may lead to delay | III | E |

*These may need to be re-assessed as part of the current round of service and	 financial planning

13.4		The following table gives the risks that would exist if the recommendation is rejected, together with a scored assessment of their impact and likelihood:

| Description of Risk | Impact | Likelihood |
| --- | --- | --- |
| 12 | The delay/lack of an up-to-date LDS could lead to legal challenge and/or Government intervention | IV | B |

13.5	Of the risks above the following are already included in service plans:

| Description of Risk | Service Plan |
| --- | --- |
| 1-12 | The Council is committed to producing a Local Plan which is a statutory requirement. | Development Plans |

13.6	The above risks are plotted on the matrix below depending on the scored assessments of impact and likelihood, detailed definitions of which are included in the risk management strategy. The Council has determined its aversion to risk and is prepared to tolerate risks where the combination of impact and likelihood are plotted in the shaded area of the matrix. The remaining risks require a treatment plan.

| Likelihood | A |  |  |  |  |  | Impact | Likelihood |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | B |  |  |  | 12 |  | V = Catastrophic | A = >98% |
|  | C |  |  |  |  |  | IV = Critical | B = 75% - 97% |
|  | D |  |  | 5,7,9 | 1,3 |  | III = Significant | C = 50% - 74% |
|  | E |  |  | 2,4,6,8,1011 |  |  | II = Marginal | D = 25% - 49% |
|  | F |  |  |  |  |  | I = Negligible | E = 3% - 24% |
|  |  | I | II | III | IV | V |  | F = <2% |
|  | Impact |  |  |

13.7	In the officers’ opinion none of the new risks above, were they to come about, would seriously prejudice the achievement of the Strategic Plan and are therefore operational risks.  The effectiveness of treatment plans are reviewed by the Audit Committee annually.

14.	Recommendation

14.1	That the Sustainable Environment Policy and Scrutiny Panel recommends the Executive Committee:

14.2	to approve the revised Local Development Scheme (LDS) as set out in Appendices 1 and 2

14.3	to approve the Local Development Scheme to be in effect from the 4 December 2012

Report prepared by:	 Claire May, Principal Planning Officer

# Data Quality

Data sources: Not applicable.

Background Papers

Local Development Scheme (submitted April 2005)					Local Development Scheme (Submitted March 2007)					Local Development Scheme (Withdrawn May 2009)					Local Development Scheme (Submitted February 2010)

Local Development Scheme (September 2011)

Localism Act 2011

Planning and Compulsory Purchase Act 2004

The recommendations contained in this report DO NOT constitute a KEY DECISION.

APPENDICES / ATTACHMENTS

Appendix 1 – Three Rivers Local Development Scheme December 2012		Appendix 2 – Timetable for Local Plan Preparation

Form A – Relevance Test -

Function/Service Being Assessed:

1. Populations served/affected:

√ Universal (service covering all residents)? Yes.

2. Is it relevant to the general duty? (see Q and A for definition of ‘general duty’)

Which of these three aspects does the function relate to (if any)?

√ 1 – Eliminating Discrimination

√ 2 – Promoting Equality of Opportunity

√ 3 – Promoting good relations

Is there any evidence or reason to believe that some groups could be differently affected?

√ No

3. What is the degree of relevance?

In your view, is the information you have on each category adequate to make a decision about relevance?

√Yes

Are there any triggers for this review (for example is there any public concern that functions/services are being operated in a discriminatory manner?) If yes please indicate which:

√ No Not at present

4. Conclusion

On the basis of the relevance test would you say that there is evidence that a medium or high detrimental impact is likely? (See below for definition)

No

Note: if a medium or high detrimental impact has been identified then a full impact assessment must be undertaken using Form B.

Completed forms should be attached as an appendix to the relevant report and a copy sent to the Community Partnerships Unit in Corporate Development, Strategic Services.

Definition of Low, Medium or High detrimental impact.

For any one (or more) equality group the following evidence is found:

|  | Evidence may come from one or more of the following sources: Local service data Data from a similar authority (including their EIA) Customer feedback Stakeholder feedback National or regional research |
| --- | --- |
| High Relevance | There evidence shows a clear disparity between different sections of the community in one or more of: levels of service access; quality of service received; or outcomes of service. |
| Medium Relevance | The evidence is unclear (or there is no evidence) if there is any disparity in terms of: levels of service access; quality of service received; or outcomes of service. |
| Low Relevance | The evidence shows clearly there is no disparity in terms of: levels of service access; quality of service received; or outcomes of service. |