EXECUTIVE COMMITTEE – 3 DECEMBER 2012

PART I - DELEGATED

15.	REVIEW OF STRATEGIC RISKS

(CED)

1.	Summary

1.1	This report gives details of progress against the Risk Treatment Plans for the Strategic Risks identified in the Strategic Plan 2012-15.

2.	Details

2.1	In accordance with the Council’s Risk Management Strategy, the Executive Committee determines which of the Council’s risks are ‘strategic’ and receives progress reports on their treatment.

2.2	The Council’s Strategic Plan 2012-2015, which was approved by Council on 21 February 2012, contained 6 strategic risks.  These risks, and the Service Plans in which they are managed, are listed below:

| Strategic Risk | Service Plan |
| --- | --- |
| 1) Failure to secure improvements to services | Leisure and Community Services |
| 2) Failure to tell residents about improvements | Corporate Services |
| 3) Failure to make progress on the sustainability action plan | Sustainability |
| 4) Failure to engage the community in the Strategic Plan | Leisure and Community Services |
| 5) Failure to achieve Community Safety targets | Leisure and Community Services |
| 6) Failure to achieve the priorities of the community strategy through the LSP | Leisure and Community Services |

2.3	Following the recent restructure of departments, strategic risks 1, 4, 5 and 6 will be included in the 2013-16 Community Partnerships Service Plan and strategic risk 3 will be included in the 2013-16 Economic and Sustainable Development Service Plan.

2.4	The relevant Head of Service has reviewed the strategic risk(s) for which they are responsible and have updated their Risk Assessment and Treatment Plan(s).

2.5	Whilst funding for the Community Safety Partnership has reduced, the re has not been a reduction in performance.  It is therefore proposed that the likelihood of Strategic Risk 5 occurring be changed from D (25%-49%) to E (3%-24%).  There are no other changes to the risk ratings.

2.6	The updated Strategic Risk Register and the Assessment & Treatment Plans, with deletions crossed through and new text shaded, are attached at Appendix 1.

3.	Options/Reasons for Recommendation

3.1	The Executive Committee is responsible for monitoring the treatment of strategic risks.

4.	Policy/Budget Reference and Implications

4.1	The recommendations in this report are within the Council’s agreed policy and budgets.

5.	Financial, Legal, Equal Opportunities, Staffing, Environmental, Community Safety, Customer Services Centre, Communications & Website, Risk Management and Health & Safety Implications

5.1	None specific.

6.	Recommendation

6.1	That the Executive Committee note the review of the Strategic Risk Register and approve the changes to the Risk Register and the Risk Assessment & Treatment Plans.

Report prepared by:	Phil King, Emergency Planning and Risk Manager

# Data Quality

Data sources: Risk Registers and Risk Assessment & Treatment Plans

Data checked by: Phil King, Emergency Planning and Risk Manager

Data Rating:

| 1 | Poor |  |
| --- | --- | --- |
| 2 | Sufficient | ( |
| 3 | High |  |

Background Papers

Strategic Plan 2012-2015

Risk Management Strategy 2012

The recommendations contained in this report DO NOT constitute a KEY DECISION.

APPENDICES / ATTACHMENTS

Appendix 1 – Strategic Risk Register and Assessment & Treatment Plans

# APPENDIX 1

| IMPACT SCORES |
| --- |
| Impact Classification | Service Disruption | Financial Loss | Reputation | Failure to provide statutory service/meet legal obligations | People |
| V Catastrophic | Total failure of service | >£1m | National Publicity. Resignation of leading member or chief officer | Litigation, claim or fine >£500k | Fatality of one or more clients/staff |
| IV Critical | Serious disruption to service | £500k - £1m | Local media criticism | Litigation, claim or fine £250k - £500k | Serious injury, permanent disablement of one or more clients/staff |
| III Significant | Disruption to service | £100k - £500k | Local public interest and complaints | Litigation, claim or fine £100k - £250k | Major injury to individual |
| II Marginal | Some minor impact on service | £10k - £100k | Contained within service | Litigation, claim or fine £10k - £100k | Minor injuries to several people |
| I Negligible | Annoyance but does not disrupt service | <£10k | Contained within section | Litigation, claim or fine <£10k | Minor injury to an individual |

| LIKELIHOOD SCORES |
| --- |
| A = ≥98% | Expected to occur in most circumstances | D = 25% - 49% | Might occur from time to time |
| B = 75% - 97% | Will probably occur in most circumstances | E = 3% - 24% | Could occur occasionally |
| C = 50% - 74% | Fairly likely to occur | F = ≤2% | May occur only in exceptional circumstances |

| STRATEGIC RISKS (NOVEMBER 2012) |
| --- |
| Likelihood | A |  |  |  |  |  | Impact | Likelihood |
|  | B |  |  |  |  |  | V = Catastrophic | A = ≥98% |
|  | C |  |  |  |  |  | IV = Critical | B = 75% - 97% |
|  | D |  |  | 6 |  |  | III = Significant | C = 50% - 74% |
|  | E |  |  | 1, 2, 4, 5 | 3 |  | II = Marginal | D = 25% - 49% |
|  | F |  |  |  |  |  | I = Negligible | E = 3% - 24% |
|  |  | I | II | III | IV | V |  | F = ≤2% |
|  | Impact |  |  |

# STRATEGIC RISK REGISTER

| Risk Ref | Risk | Impact | Impact Classification | Likelihood Classification | Reason for Assessment |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Brief Description – Title of Risk | See Impact Table | See Impact Table | See Likelihood Table | Use this box to describe how the score has been derived |  |  |
| 1 | Failure to secure improvements to services | Service Disruption | II | E | Additional Public Perception Surveys introduced. Review of shared Revenues and Benefits service. | Requires Treatment | Yes |
|  |  | Financial Loss | I |  |  | Last Review Date | 08/11/12 |
|  |  | Reputation | III |  |  | Next Milestone Date | 30/01/13 |
|  |  | Legal Implications | I |  |  | Next Review Date | 31/01/13 |
|  |  | People | I |  |  | Date Closed | -- |

RISK ASSESSMENT AND TREATMENT PLAN

| Risk Ref: | 1 | Risk Title: | Failure to secure improvements to services |
| --- | --- | --- | --- |
| Responsibility | Who is managing the risk? | Management Board |
| Consequence | What can go wrong? How can it go wrong? Has it gone wrong before? | There is a new set of Performance Indicators, some with no historic base Remaining PIs may dip PIs have suffered in periods of significant change |
| Cause / Trigger | What happens to bring the risk into being? | Quarterly report to Management Board and half-yearly report to Policy and Scrutiny Committees flags up failures to hit targets. Less national performance data available for comparison. Most comparison data within Hertfordshire for which other districts may not be nearest neighbours for comparative purposes. National quartile measures improve at quicker pace than improvements at TRDC |
| Existing Control | What controls exist now to minimise the risk? | Service Planning framework and Star Chamber exercise Benchmarking Internal Audits Value for Money Strategy Corporate Consultation Action Plan Omnibus survey in place Improvement action plan in place for shared Revenues and Benefits service Omnibus survey updated to track perceptions of changes to key services such as Refuse and Recycling |
| Adequacy of Control | What evidence is there that the existing Controls are working? What would the Risk Rating be without the existing controls? | PIs have improved year on year for the past 3 years | Impact | Likelihood |
|  |  |  | III | D |
| Further Action / Controls Required | What gaps have been identified? What can be done to reduce the likelihood of something going wrong and/or reduce the Impact if something does go wrong? | Use of Resources assessment highlighted need to formalise value for money studies/reviews. The Value for Money Strategy has now been agreed and implemented. Value for Money Strategy to be implemented. Omnibus survey to be maintained to monitor performance of key corporate PIs. |
| Cost / Resources | Are there cost / resource implications in achieving the further action above? | No additional resource requirements identified. | £ 0 |
| Current Status | What is the current position on introducing additional controls? What is the current Risk Rating | Additional public perception surveys introduced 2010. Impact and probability have not changed since last review. Omnibus survey in place to measure key corporate PIs. PIs have improved or been maintained. Failing services have been identified and additional performance support provided to them. | Impact | Likelihood |
|  |  |  | III | E |
| Critical Success Factor | How will you know that the action taken has worked? What will be the Risk Rating outcome with the new controls? | Consultation feedback should show perceived improvements PIs will improve. | Impact | Likelihood |
|  |  |  | III | F |

# STRATEGIC RISK REGISTER

| Risk Ref | Risk | Impact | Impact Classification | Likelihood Classification | Reason for Assessment |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Brief Description – Title of Risk | See Impact Table | See Impact Table | See Likelihood Table | Use this box to describe how the score has been derived |  |  |
| 2 | Failure to tell residents about improvements | Service Disruption | I | E | The Council’s reputation might suffer if residents weren’t informed about their services and improvements made. of the Council’s successes. Residents would not be able to make maximum use of local services. The measure in place to inform residents of improvements (e.g. Three Rivers Times) reduces the likelihood of residents not being informed | Requires Treatment | Yes |
|  |  | Financial Loss | I |  |  | Last Review Date | 09/11/12 |
|  |  | Reputation | III |  |  | Next Milestone Date | 30/01/13 |
|  |  | Legal Implications | I |  |  | Next Review Date | 31/03/13 |
|  |  | People | I |  |  | Date Closed | -- |

RISK ASSESSMENT AND TREATMENT PLAN

| Risk Ref: | 2 | Risk Title: | Failure to tell residents about improvements |
| --- | --- | --- | --- |
| Responsibility | Who is managing the risk? | Communications Manager |
| Consequence | What can go wrong? How can it go wrong? Has it gone wrong before? | Stakeholders not understanding/valuing the services the Council provides Low levels of public satisfaction with the Council Residents do not feel well informed Vulnerable residents are not sufficiently informed about local service improvements Communications are not received by residents Communications initiatives and messages are not effectively co-ordinated |
| Cause / Trigger | What happens to bring the risk into being? | Citizen’s Panel not representative of community Consultation methods fail to engage hard to reach groups Insufficient resources to engage hard to reach groups Messages unclear or garbled Responsive rather than proactive Distribution failures (Three Rivers Times) Prolonged staff absence Staff go on secondment, depart or are on sick leave |
| Existing Control | What controls exist now to minimise the risk? | Corporate consultation data analysed by race, gender and disability Regularly updated strategy and action plan with increased emphasis on quality controls. Editorial Working Party reviews TRT and A-Z. TRT distributor provides GPS tracking of delivery teams and delivery quality checked with staff who live in the district. Delivery reminder service implemented. Annual focus groups for TRT, A-Z and priority communications issues Press release output and coverage targets in place. Feedback mechanisms include Pensioners’ Forum, Youth Council, prize draw survey in democracy packs, welcome packs for new residents, surveys in TRT and at key points of contact. Communications team action plan produced annually and reviewed twice a year. Communications and engagement plans for sustainability, community safety, democracy and citizenship and South Oxhey Initiative include targets and evaluation. Herts Omnibus survey provides annual data on communications performance, including breakdowns for deprived and minority groups. Audio version of Three Rivers Times actively distributed for visually impaired or those with reading difficulties. Internal Communications survey completed annually. Monthly “What’s On” poster placed on noticeboards and distributed to community venues E-newsletters in place for Environment, Planning, Leisure and South Oxhey include feedback mechanisms. Facebook news pages introduced for key areas included those with significant deprivation and integrated with Twitter. Social media is monitored and responded to. Regular attendance at the county communications managers group |
| Adequacy of Control | What evidence is there that the existing Controls are working? What would the Risk Rating be without the existing controls? | Herts Omnibus survey 2011/12 shows 73% of respondents felt they were well informed or fairly well informed about Council services and overall satisfaction is 74% (75% average for county). | Impact | Likelihood |
|  |  |  | III | B |
| Further Action / Controls Required | What gaps have been identified? What can be done to reduce the likelihood of something going wrong and/or reduce the Impact if something does go wrong? | Scope of communications work is limited by below national average staffing level Below average staffing level weakens resilience |
| Cost / Resources | Are there cost / resource implications in achieving the further action above? |  | £ 0 |
| Current Status | What is the current position on introducing additional controls? What is the current Risk Rating | Additional controls to be considered as part of the Communications Plan 2012/13 | Impact | Likelihood |
|  |  |  | III | E |
| Critical Success Factor | How will you know that the action taken has worked? What will be the Risk Rating outcome with the new controls? | All key groups will be represented in consultation feedback. Satisfaction with information provision and overall satisfaction with the Council would increase | Impact | Likelihood |
|  |  |  | II | E |

STRATEGIC RISK REGISTER

| Risk Ref | Risk | Impact | Impact Classification | Likelihood Classification | Reason for Assessment |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Brief Description – Title of Risk | See Impact Table | See Impact Table | See Likelihood Table | Use this box to describe how the score has been derived |  |  |
| 3 | Failure to make progress on the sustainability action plan | Service Disruption | I | E | The “clean and green” aim of the Strategic Plan includes the objective “to maintain a high quality local environment and reduce the eco-footprint of the district”. The Council’s reputation would suffer if sustainability targets were not achieved. | Requires Treatment | Yes |
|  |  | Financial Loss | II |  |  | Last Review Date | 09/11/12 |
|  |  | Reputation | IV |  |  | Next Milestone Date | 30/01/13 |
|  |  | Legal Implications | II |  |  | Next Review Date | 31/01/13 |
|  |  | People | I |  |  | Date Closed | -- |

RISK ASSESSMENT AND TREATMENT PLAN

| Risk Ref: | 3 | Risk Title: | Failure to make progress on the sustainability action plan |
| --- | --- | --- | --- |
| Responsibility | Who is managing the risk? | Head of Sustainability Head of Economic and Sustainable Development |
| Consequence | What can go wrong? How can it go wrong? Has it gone wrong before? | The authority fails to lead by example on sustainable initiatives and does not provide the opportunities for residents to take advantage of, for example, energy saving measures Failure to resource the plan properly Lack of awareness of current initiatives National Indicators have been abolished. The Council is at a high level already and a high base line may prove difficult to improve on if new Indicators are introduced. |
| Cause / Trigger | What happens to bring the risk into being? | Monitoring reveals that the actions are not taking place and targets are not being achieved Withdrawal of Government funding for sustainable initiative subsidies |
| Existing Control | What controls exist now to minimise the risk? | Action Plan for the development of Climate Change Strategy agreed Sustainability team has been set up Regular progress reports on strategy development reported to SEPSC Standing items for Cabinet/Management Board and Management Board meetings Partnership arrangements have been set up with the LSP and Energy Savings Trust Membership of the Herts Sustainability Forum with bi-monthly meetings Information is provided via the “Our Climate Is Changing” website Greenhouse Gas emissions data has been submitted to DECC ISO14001 re-accreditation achieved (excluding Batchworth Depot) Membership of USEA Green Deal Community Interest Company agreed |
| Adequacy of Control | What evidence is there that the existing Controls are working? What would the Risk Rating be without the existing controls? | Stakeholders are kept up to date on progress via regular reports Internal audits Submissions to DEFRA and DECC | Impact | Likelihood |
|  |  |  | IV | D |
| Further Action / Controls Required | What gaps have been identified? What can be done to reduce the likelihood of something going wrong and/or reduce the Impact if something does go wrong? | Annual audit and re-accreditation of ISO14001 for Three Rivers House – Due October, 2012 Seeking accreditation for ISO14001 for Batchworth Depot Continued promotion of Government (CERT) funding, whilst available and investigation of Green Deal and ECO funding to replace CERT Continued development and promotion of the “Our Climate Is Changing” website Continued monitoring of Greenhouse gas emissions and reporting to DECC Development of a Climate Change Strategy and Action Plan to replace the Sustainability Action Plan. Progress the Green Deal initiative via the Community Interest Company |
| Cost / Resources | Are there cost / resource implications in achieving the further action above? | No additional resource requirements identified | £ 0 |
| Current Status | What is the current position on introducing additional controls? What is the current Risk Rating | Additional controls to be completed during 2012/13 Impact and probability have not changed since last review | Impact | Likelihood |
|  |  |  | IV | E |
| Critical Success Factor | How will you know that the action taken has worked? What will be the Risk Rating outcome with the new controls? | Successful ISO14001 accreditation for Batchworth Depot Successful ISO14001 re-accreditation each year. | Impact | Likelihood |
|  |  |  | IV | F |

STRATEGIC RISK REGISTER

| Risk Ref | Risk | Impact | Impact Classification | Likelihood Classification | Reason for Assessment |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Brief Description – Title of Risk | See Impact Table | See Impact Table | See Likelihood Table | Use this box to describe how the score has been derived |  |  |
| 4 | Failure to engage the community in the Strategic Plan | Service Disruption | I | E | Evidence held on successful consultations and high customer satisfaction data. | Requires Treatment | Yes |
|  |  | Financial Loss | I |  |  | Last Review Date | 08/11/12 |
|  |  | Reputation | III |  |  | Next Milestone Date | 30/01/13 |
|  |  | Legal Implications | I |  |  | Next Review Date | 31/01/13 |
|  |  | People | I |  |  | Date Closed | -- |

RISK ASSESSMENT AND TREATMENT PLAN

| Risk Ref: | 4 | Risk Title: | Failure to engage the community in the Strategic Plan |
| --- | --- | --- | --- |
| Responsibility | Who is managing the risk? | Community Partnerships Manager |
| Consequence | What can go wrong? How can it go wrong? Has it gone wrong before? | Poor response rates from the community or hard to reach groups. Lack of consultation of community in priorities set by the Council. |
| Cause / Trigger | What happens to bring the risk into being? | Citizen’s Panel becomes unrepresentative Consultation methods fail to engage hard to reach groups Poor consultation methods used Insufficient resources to engage groups Hard to reach groups fail to remain engaged due to lack of TRDC response |
| Existing Control | What controls exist now to minimise the risk? | Corporate consultation data is analysed by race, gender, disability, age, area of residence and household income Consultation best practice guidance updated for all services Corporate focus groups held with BME communities, LGBT communities and those dissatisfied with key services changes Research with young people on community safety, South Oxhey initiative and Community Strategy Stakeholder engagement with low income groups, people with mental health and learning disabilities and low literacy groups Consultation Action Plan has been developed Pilot project for customer profiling is continuing Priorities for engagement have been identified Diversity Peer Challenge completed Customer Service Excellence accreditation of all services |
| Adequacy of Control | What evidence is there that the existing Controls are working? What would the Risk Rating be without the existing controls? | Evidence held on successful consultation and customer satisfaction | Impact | Likelihood |
|  |  |  | III | D |
| Further Action / Controls Required | What gaps have been identified? What can be done to reduce the likelihood of something going wrong and/or reduce the Impact if something does go wrong? | Maintain implementation of corporate Consultation Action Plan. |
| Cost / Resources | Are there cost / resource implications in achieving the further action above? | No additional resource requirements identified. | £ 0 |
| Current Status | What is the current position on introducing additional controls? What is the current Risk Rating | Impact and probability have not changed since last review. Consultation on the review of the Community Strategy and South Oxhey Initiative undertaken. Consultation on changes to Council Tax Benefit | Impact | Likelihood |
|  |  |  | III | E |
| Critical Success Factor | How will you know that the action taken has worked? What will be the Risk Rating outcome with the new controls? | All key groups represented in corporate consultation feedback. Risk could be closed. | Impact | Likelihood |
|  |  |  | III | F |

STRATEGIC RISK REGISTER

| Risk Ref | Risk | Impact | Impact Classification | Likelihood Classification | Reason for Assessment |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Brief Description – Title of Risk | See Impact Table | See Impact Table | See Likelihood Table | Use this box to describe how the score has been derived |  |  |
| 5 | Failure to achieve Community Safety targets | Service Disruption | II | D E | Strategy continues to meet majority of targets. Individual targets not met are being addressed by local action plans. Reducing funding increases likelihood. | Requires Treatment | Yes |
|  |  | Financial Loss | I |  |  | Last Review Date | 08/11/12 |
|  |  | Reputation | III |  |  | Next Milestone Date | 30/01/13 |
|  |  | Legal Implications | I |  |  | Next Review Date | 31/01/13 |
|  |  | People | I |  |  | Date Closed | -- |

RISK ASSESSMENT AND TREATMENT PLAN

| Risk Ref: | 5 | Risk Title: | Failure to achieve Community Safety targets |
| --- | --- | --- | --- |
| Responsibility | Who is managing the risk? | Community Safety Manager |
| Consequence | What can go wrong? How can it go wrong? Has it gone wrong before? | Ineffective target setting. Resources not allocated to address actions. Changes in recording systems. Initiatives fail to meet targets. Public do not understand what work is being achieved. Overall strategy has met strategic targets. |
| Cause / Trigger | What happens to bring the risk into being? | Strategy not translated into action plans for each partner agency. Action plan not monitored for impact and corrective action. MIDAS/monitoring systems fail. Poor practice and enforcement by partners. Residents mis-informed by national media. Reduction in funding to partnership. No joint risk management. Lack of commitment of staffing resources from partners. Lack of equality monitoring. No business continuity or disaster recovery plans. |
| Existing Control | What controls exist now to minimise the risk? | Quarterly performance reports to Community Safety Board and Co-ordination Group. 6 monthly reports to Leisure and Community Safety Policy and Scrutiny committee. Briefings with Leader and Portfolio holder. Participation in Family Intervention Project, Offender Management Group and ASB Action Group. Equality impact monitored. Monthly updates to Members |
| Adequacy of Control | What evidence is there that the existing Controls are working? What would the Risk Rating be without the existing controls? | Strategy overall is on target. Where individual targets not met new action plans have been put in place and targets revised annually. | Impact | Likelihood |
|  |  |  | III | D |
| Further Action / Controls Required | What gaps have been identified? What can be done to reduce the likelihood of something going wrong and/or reduce the Impact if something does go wrong? | Review all bids for sustainability. Assess risks of all partnership projects. Request clarity of staffing commitments from all partners through annual action plan. Request CRB checks for partnership funded projects where relevant. Request equality impact on all funding proposals. Health and safety terms to be given to all grants. Review data protection arrangements for non-statutory partners. Assess business continuity needs for all partnership projects. Implement shared ASB management system. Seek county clarity on funding sources. Community Safety Board to review funding position following election of Police & Crime Commissioner |
| Cost / Resources | Are there cost / resource implications in achieving the further action above? | Staff time. ICT support to implement new ASB system. | £ tbc |
| Current Status | What is the current position on introducing additional controls? What is the current Risk Rating | Grants reviewed, and sustainability proposals being reviewed. Dialogue started with LSP regarding funding sources. Shared ASB management tool in place. Pilot area for transition from Family Intervention Project to Thriving Families programme. | Impact | Likelihood |
|  |  |  | III | D E |
| Critical Success Factor | How will you know that the action taken has worked? What will be the Risk Rating outcome with the new controls? | Targets of strategy met for year. Review new risks at that point. | Impact | Likelihood |
|  |  |  | III | F |

STRATEGIC RISK REGISTER

| Risk Ref | Risk | Impact | Impact Classification | Likelihood Classification | Reason for Assessment |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Brief Description – Title of Risk | See Impact Table | See Impact Table | See Likelihood Table | Use this box to describe how the score has been derived |  |  |
| 6 | Failure to achieve the priorities of the Community Strategy through the LSP | Service Disruption | I | D | Loss of 50% of the Performance Reward Grant reduces capacity for local projects. No further funding secured yet for Local Strategic Partnership. | Requires Treatment | Yes |
|  |  | Financial Loss | I |  |  | Last Review Date | 08/11/12 |
|  |  | Reputation | III |  |  | Next Milestone Date | 30/01/13 |
|  |  | Legal Implications | I |  |  | Next Review Date | 31/01/13 |
|  |  | People | I |  |  | Date Closed | -- |

RISK ASSESSMENT AND TREATMENT PLAN

| Risk Ref: | 6 | Risk Title: | Failure to achieve the priorities of the Community Strategy through the LSP |
| --- | --- | --- | --- |
| Responsibility | Who is managing the risk? | Community Partnerships Manager |
| Consequence | What can go wrong? How can it go wrong? Has it gone wrong before? | Failure to deliver on the strategy by some partners. Loss of resources to support achievement of the priorities. Action plans not effectively implemented. |
| Cause / Trigger | What happens to bring the risk into being? | Loss of national targets and funding streams. Changes in priorities of individual partners. Budget limitations. Poor development of action plans. Limited buy in to strategy by partners. |
| Existing Control | What controls exist now to minimise the risk? | Action Plan updates provided to board from all sub-partnerships. Key performance indicators being tracked. Regular briefing with leader. Regular meetings of LSP Board. Sustainable funding plan being developed by LSP. |
| Adequacy of Control | What evidence is there that the existing Controls are working? What would the Risk Rating be without the existing controls? | Progress made on key projects in the District. Challenge provided to poor performance. Board reviewing impact of CSR and new changes. Sustainability key decision element to project funding. | Impact | Likelihood |
|  |  |  | III | C |
| Further Action / Controls Required | What gaps have been identified? What can be done to reduce the likelihood of something going wrong and/or reduce the Impact if something does go wrong? | Complete review of LSP. Assess new sources of potential shared funding for local priorities. Maintain risk assessment of all proposals for funding and joint action. |
| Cost / Resources | Are there cost / resource implications in achieving the further action above? | Staff time. Partners funding and commitment. | £ 0 |
| Current Status | What is the current position on introducing additional controls? What is the current Risk Rating | Review of partnership has started to risk asses future needs. Community Strategy reviewed and new priorities to be consulted on agreed. Potential funding sources identified for future years. Growth bids submitted by some partner agencies Priorities raised with Hertfordshire Health and Wellbeing Board and Commissioning Staff. | Impact | Likelihood |
|  |  |  | III | D |
| Critical Success Factor | How will you know that the action taken has worked? What will be the Risk Rating outcome with the new controls? | Partnership achieves further progress on priorities in areas of deprivation in sustainable manor. | Impact | Likelihood |
|  |  |  | III | E |