## Key
Key
Action progress
Not started
In progress
Completed
Ongoing

## Enable and Engage
Theme: Enable and Engage
Aim: To inspire all stakeholders and residents of Three Rivers to work together to achieve carbon neutrality, build climate resilience and adopt sustainable choices and lifestyles.
We will / Objective: | Action: | Responsibility of [Department/Officer]: | Delivery Partners: | Completed By / Delivery Date: | Budget | Milestones/KPIs: | Status and Comments:
Embed the climate and ecological emergencies into the governance, culture and decision making of the Council so that the environmental impacts of all council projects, policies, procurements and services are considered. | Introduce climate change and sustainability training as mandatory e-learning courses for all council employees and members. | Community Partnerships | Human Resources | March 2023 | N/A | Content Created HR briefed | Course content created, and in the process of being converted into an e-learning module. ER 9/8/22
| Identify additional specialist training courses for relevant departments as appropriate to their function. | Community Partnerships | Human Resources | Action complete | £500 paid by training budget | Senior leaders Course completed. | HCCSP reviewed specialist training for planners and shared specific training guides produced by TCPA. These have been shared with Development Management JH 5/8/22
| Encourage a shift to remote working, where role allows, to at least 3 days per week to reduce the need for officer commuting through the New Ways of Working programme. | Senior Leadership Team | New Ways of Working Champions | Action complete | NWOW budget | NWOW commence | New Ways of Working is now in place. JH 01/02/22
| Develop Procurement Strategy which ensures purchasing decisions contribute to the Council's Climate Emergency and Sustainability Strategy. | Procurement | Procurement | March 2023 | N/A | Report to P&R Committee | Climate Change Team have completed work on sustainability. Waiting for DH to progress JH 29/06/22
| Enhance the environmental impact assessment and include adaption to extreme weather events where appropriate (Section 7) of the Committee Report template. | Community Partnerships | Committees | In operation by March '23 | N/A | Awaiting approval with CMT | Climate and sustainability Implications toolkit produced, test cases completed, awaiting approval to commence use by officers.
| Develop a Staff Environmental Charter to create a culture of environmental consideration for all the work officers and members undertake on behalf of the Council | Community Partnerships | Communications | Action complete |  | CMT January 2022 | Work complete, charter adopted and posters created
| Review staff benefits package connected to sustainability and publicise | HR |  |  |  | view | New Action, not commenced
| Ensure cleaning products used are those least harmful to the environment and which minimise waste. | Facilities | TenOn, | Action complete | In budget | At quarterly review meetings, update and reinforce standards - e.g. Opting for phosphate-free products to prevent eutrophication of waterways. | Three Rivers and Basing House, Watersmeet and Depot are already complying. Everyone Active will be adopting this too, as part of their Route to Zero plan.
| Continue to run the Environment Forum to enable networking and shared project working and learnings across the District amongst members, and to help officers receive specialist advice regarding the issues and opportunities in the District. | Community Partnerships | Relevant stakeholders, Members and Officers. | Ongoing | N/A | Meetings 3 times per year | Speakers are selected to assist in understanding local impacts and issues connected to the climate and ecological emergency JH 15/12/21
Continue to consult with residents, council tenants and stakeholders on climate change and sustainability issues and initiatives. | TRDC Water Partnership set up to address issues of flooding, sewage discharge, over abstraction and to ensure that water infrastructure is aligned with development requirements. | Community Partnerships | Officers and Members of TRDC, Thames, Affinity, Colne Can and relevant CVS's | Action complete | Will commence Autumn 2021, then have tri-annual meetings | Terms of Reference complete, 1st Meeting took place 1/12/21 | Ist meeting was informative, subsequent ones need to tackle issues. Survey sent to members to request topic list for discussion at next meeting My 2022 JH 15/12/21
| Develop a programme to engage with local businesses and organisations by advising on a sustainable recovery from Covid19, planning to be carbon neutral, and encouraging them to sign up to a county-wide carbon reduction pledge, committing themselves to take 3 strong actions. (HCCSP) | Community Partnerships | Sustainable X, Smarter Society | Programme complete March '23 Action Complete | Funded by ARG | 12 SME's received mentoring through workshops to produce net zero plan, and 14 received grant to assist in their decarbonisation
| Develop a communications plan including a timetable to ensure sustainability messaging is consistent and balanced. Include a Climate Change FAQ’s page to answer common questions. | Community Partnerships | Sustainable Three Rivers, TRDC Website, Friends of the Earth | Monthly newsletter taking place. Resident sustainability pamphlet on website December 2021 Planners sustainability advice document September '22 | N/A | FAQ's page written. 12 Greener Living newsletter annually, now with over 2000 followers. Great Big Green Week Pamphlet produced. | Sustainability document for planning applicants in final stages almost ready for circulation to planning officers. Newsletter has over 2000 readers JH 05/08/22
Engage with local businesses, council tenants, relevant corporates, schools, faith groups, youth groups, parish councils, highways, and campaign and conservation groups to inspire and support each other in adopting pro-environmental behaviours, for example water and energy conservation, waste reduction, and sustainable food consumption. | Develop an events programme to provide opportunities to engage and inspire residents to start making their own changes to tackle the climate emergency | Community Partnerships/ | Communications, Sustainable Three Rivers, Rickmansworth Festival Team and Leisure | Ongoing | In climate change budget | Great Big Green Week (GBGW) 2022 | During GBGW clothes swap and sewing, knitting, repairing, upcycling demonstration in Rickmansworth Library. Fast Fashion conference at Watersmeet took place. Screening of WALL-E for kids March '23 booked at Watersmeet. Ran information events at Rickmansworth Festival, Croxley Revels, weekly Open Sessions at Leavesden HIVE. Over 1020 people engaged with across the District, in person in 2022 so far......JH 5/8/22 ER 9/8/22
| Develop a programme to engage with local businesses and organisations by advising on a sustainable recovery from Covid19, planning to be carbon neutral, and encouraging them to sign up to a county-wide carbon reduction pledge, committing themselves to take 3 strong actions. (HCCSP) | Community Partnerships | HCCSP, LEP, Sustainable X | Action complete | ARG Funding (Approx. £35,000 |  | 22 companies registered for assistance, 14 attended workshops, 16 companies were awarded grants to reduce carbon emissions, JH 5/8/22+H18:H26H18:H28H16H18:H24H18:H26
| Raise awareness of the harms of car idling outside schools to encourage positive behavioural change, in collaboration with the Youth Council and local schools. | Community Partnerships and Leisure and Landscapes | , HCCSP Youth Council, Air pollution officer Local Schools, MumsNet / local influencers | March 2023 | £500 in carbon neutral budget for promotion | Clean air Day 16/06/222 | Social media campaign commenced June 2022. Requesting assistance from the community groups/ schools to run specific events in the winter. HCCSP have produced event material
| Promote ecologically-friendly funerals such as those offered by Woodcock Hill Cemetery on the Council website, and newsletter. | Community Partnerships | Cemeteries Team, Communications | Action complete | N/A | Information on Council website, advice in a newsletter
| Hold film screenings of environmental films at Watersmeet Theatre. | Community Partnerships | Watersmeet | Ongoing | In carbon neutral budget | GBGW '21 screened 2 films | Next screening for GBGW '22 and Spring '23
| Work with Rickmansworth Festival 2022 to use the opportunity to engage with a wide range of residents on how they can help tackle the climate emergency. | Leisure and Landscapes | Rickmansworth Festival Team / Leisure and Landscapes | June 2022 action complete June 2023 to take part again | £1,500 in carbon neutral budget 22/23
| Raise the awareness of property owners and businesses about flooding and overheating on Council website, Greener Living e-newsletters and social media channels. | Community Partnerships | Communications | Ongoing | N/A | Sustainable planning leaflet being issued. | Leaflet produced, next step is to agree delivery. Social media campaign on overheating ran during heatwave, items in newsletter JH 05/08/22
| Purchase the Energy Savings Trust (EST) App as a member of the HCCSP to give tailored low or no cost behaviour change advice to residents on how they can reduce their energy use to save carbon emissions and money. | Community Partnerships | HCCSP | Action complete | Less than £1000 in the first year and estimate annual costs under £500. Within carbon neutral budget | app purchased autumn 2021 | App launched and promoted January 2022 EN 17/01/22
Reduce our community’s vulnerability to the impacts of climate change and take advantage of any opportunities that arise. | To encourage sustainability in community and social enterprises in the District TRDC has provided a Sustainability Grant to fund initiatives or help groups work towards net zero | Community Partnerships | Watford and Three Rivers Trust (W3RT) | Ongoing | £10,000 in carbon neutral budget. Annually | Review with W3RT December 2021 | This financial year, three applications have been successful and received a total of £4000 for purchasing and refurbishing used furniture, Great Big Green Week promotions, and rain water harvesting for a community garden. ER 9/8/22
To regularly review and measure our successes against our Strategy and Action Plan to inform residents and stakeholders of the changes being made across the District and their contribution to fighting the climate and ecological emergency. | Formally review progress on the Strategy and Action Plan annually at the LEC committee communicating outcomes through social media and newsletters. | Community Partnerships | Community Partnerships | Ongoing | N/A | LEC October '21 . LEC March 2022. Baseline emissions published on website Feb 2022
20 Actions | Green

## Energy
Theme: Energy
Aim: Minimise energy-related emissions in the District through reducing consumption, improving efficiency and transitioning to renewable energy sources to achieve net-zero targets (2030 – council emissions, 2045 – district-wide emissions).
We will / Objective: | Action: | Responsibility of [Department/Officer]: | Delivery Partners: | Completed By / Delivery Date: | Budget | Milestones: | Status and Comments:
Regularly monitor and review council and district energy-related emissions to inform decision-making in achieving the net-zero targets. | Establish the Council's emissions baselines for its estate and operations in order to measure progress on decarbonisation. | Community Partnerships |  | 21/22 complete 22/23 target for completion Ocotber'23 | Completed from carbon neutral budget | 21/22 report produced | 21/22 data has been submitted, waiting for report
| Develop a sustainable method for collating emissions data each year. Encouraging utility suppliers to install smart meters to assist in automating this process. | Community Partnerships, Facilities, | All utility suppliers and relevant officers who manage the accounts, procurement | June-22, then updated annually. | N/A | Procurement for new water supplier | Start research to review automated data collection system JH 05/08/22
| Produce a the route to zero action plan. The project will work across the Council and result in an Action Plan which will detail the work and costing required to eliminate / mitigate emissions. | Community Partnership | Finance | Draft report submitted to officers June'22 Trajectory to zero produced and actions agreed Oct '23 | £8,500 from carbon neutral budget. | Emissions collated, surveys completed, rreport shared with Head of Service, Trajectory produced | Finance are modelling the route to zero trajectory
| Measure the transport-related emissions of Council staff following implementation of New Ways of Working through an annual survey. | Transport & Parking Projects | Sustainable Transport | Annually in April. | N/A | Annual Survey
Assess options for decentralised renewable energy generation within council operations and the wider district, working either independently or in partnership. | Reduce Council emissions in the short term by switching to a Power Purchase Agreement which utilises traceable renewable energy sources for 50% of requirement and green tariff for the remainder. This removes 86% of Scope 2 emissions (284 tonnes of carbon) | Procurement | LASER Energy | Action closed | approx. £20k to move gas and electricity to PPA, and offset - report submitted to P&R committee | CMT August '22 | Report went to JLT where it was decided not pursue this option due to cost (~£20k).
| Review options to optimise the amount of renewable energy production on TRDC buildings and car parks. | Property |  | Commenced in 2021 and completed over following 2 years | In budget | Business Case prepared | Assessment of land options taken place, and there is no available suitable land. Further options to consider optimising all buildings and car parks to find additional sites. | NEW
Share learnings from the Council and across industry with stakeholders and residents in the District to inspire and support others to start their own decentralised energy projects, or switch to a green energy provider. | Research options for District wide shared renewable energy scheme. | Community Partnerships | TBC | Commence September '22 | N/A | Solar Bulk buy for residents scheme adopted | 1213 registrations for the scheme. Auction took place 27th September.133 residents accepted
Utilise financial support measures wherever possible to install low-carbon energy technologies across Council buildings, and publicise relevant funding opportunities available to residents and businesses. | Monitor options for grant funding both for Council assets and for organisations within the District. | Community Partnerships/ Community Services |  | PSDF grant won to retrofit Three Rivers House. | N/A
| Create mailing list for local businesses and charities in order to direct grant opportunities more quickly to relevant organisations. | Community Partnerships | Communications | Action Closed | N/A

## Sustainable Design and Construc
Theme: Sustainable Design and Construction
Aim: The highest standards of sustainable design and construction should be achieved to create adaptable buildings which are resilient to the effects of climate change, and minimise the use of natural resources over the intended lifetime of a development.
We will / Objective: | Action: | Responsibility of [Department/Officer]: | Delivery Partners: | Completed By / Delivery Date: | Budget | Milestones: | Status and Comments: | Action Progress
Require major developments to submit a Sustainability Statement to demonstrate how the development will mitigate and adapt to climate change over its lifetime, minimise construction related waste and adhere to the sustainability requirements stipulated by the Local Plan. | Develop Policy DM4, already in place, in regards to the criteria for Sustainability Statements in new Local Plan. | Planning Policy | Development Management |  | N/A | 2025: Adoption of Local Plan | DM4 covers all developments - not just major.
Require all new commercial developments, and residential developments of one unit and above to produce an Energy Statement demonstrating how a minimum of 20% less carbon dioxide emissions than Building Regulations Part L requirements (2013) will be achieved. | Draft policy in Local Plan. | Planning Policy | Development Management |  | N/A | 2025: (CM 11/01/2022) Adoption of Local Plan | This may change subject to Government changes to Building Regulations. Draft Policy to be included in Local Plan (CM 11/01/2022)
Require the integration of renewable energy within any new council developments and existing assets, and (where possible) within public and private sector developments. | Draft policy in Local Plan. | Planning Policy/ Property | Development Management |  | By individual report per project | 2025: (CM 11/01/2022) Adoption of Local Plan | Suggestion that Property build this into their own policy re council developments (CM 11/01/21)
| Investigate opportunities to install solar street lighting across the District's 350 units. | Facilities | Hertfordshire County Council |  |  | 2021:Trial completed. Installation commences 2022 | Funding agreed with P&R committee to upgrade all 350 units in the district to solar.
Lobby Government to ensure Building Regulations do adopt the Future Homes and Buildings Standard by 2025 to ensure new build homes are future-proofed to net enable net zero with low carbon heating and exceptional levels of energy efficiency. | Monitor progress of Regulations and if the Bill falters, take action to lobby. | Community Partnerships | Development Management |  |  | Planned Introduction 2025 | Since creating this objective, Future Homes and Buildings Standards is progressing well through Parliament with stepped increments over and above 20% to 2025 when it will be enacted in full. No letter required at present (only if process stalls).
Expect all proposals for development to be designed sensitively to build in resilience to extreme weather events by managing flood risk, enhancing the Green and Blue Infrastructure Network, and optimising passive solar gain, whilst reducing the risk of overheating. Furthermore, development must protect and enhance existing social and community facilities, provide new facilities where necessary and provide essential infrastructure, including (but not limited to) transport, education, health, utilities, waste facilities, waste water, leisure, cultural and community facilities. | Draft policy in Local Plan. Sustainability aspects will be managed via the validation check list for planning applications. | Development Management | Development Management, | Adoption of Local Plan | N/A | Adoption of Local Plan
Upon enactment of the Environment Bill, require all new development in TRDC to result in a 10% net-gain for biodiversity (preferably within the District) and avoid the fragmentation, damage and isolation of existing habitats. | A report to be prepared to consider the resource requirement for a dedicated officer to ensure the requirements of the Environment Bill (and Local Plan once adopted) can be implemented. | Development Management | Development Management / Community Services/ Community Partnerships | This will not be possible until further details regarding Bio Div Net Gain have been published in 2022/23 [AR 23/12/21] | N/A | Adoption of Environment Bill. Publication of regulation requirements and new burden funds availability- if any | Environment Bill enacted 9/11/21 . Biodiversity Net Gain requirement likely to come into effect in 2023. (CM 11/01/2022)
| Develop a Biodiversity Supplementary Planning Document (SPD) / Guidance in order to identify how the 10% net gain will be accounted for and implemented and to identify appropriate sites for biodiversity net gain (BNG) compensation within Three Rivers. | Planning Policy (SPD). Guidance by Development Management | SPD: Planning Policy, Community Services, HCCSP. Guidance: Development Management | Guidance in line timings of Environment Bill, SPD with Local Plan Adoption | N/A | Environmental Act 2021 (9 November 2021) (CM 11/1/2022) | BNG Guidance to be prepared in line with the timing requirements of the ACT. BNG requirement likely to come into effect in 2023. (CM 11/01/2022) This will be developed into an SPD once the Local Plan is adopted and baseline and opportunity audits completed. This is required to manage net gain offsetting
For major non-residential developments, proposals should achieve BREEAM ‘Excellent’ as a minimum with the ambition to achieve “Outstanding.” | Draft policy in Local Plan. | Planning Policy | Development Management |  | N/A | 2025: Adoption of Local Plan.
Require new development to provide waste and recycling facilities in accordance with the Council’s Solid Waste Storage/Collection Guidance. | Draft policy in Local Plan. | Planning Policy | Development Management |  | N/A | 2025: Adoption of Local Plan.
Encourage consideration of sustainability in small scale building extensions, renovations and retrofits. | Draft policy in Local Plan. | Planning Policy | Development Management |  | N/A | 2025: Adoption of Local Plan.
Require the provision of sustainable low- and zero-carbon transport infrastructure in new developments. | Electric vehicle charging points required in Planning Policy. | Planning Policy | Development Management |  | N/a | 2025: Adoption of Local Plan.
Support off-site manufacturing of residential or commercial construction. | Draft policy in Local Plan encouraging modular construction. | Planning Policy |  |  | N/A | 2025: Adoption of Local Plan.
| Prepare a sustainability document in PDF form to be issued with planning applications to include advice on light pollution, wildlife corridors in gardens, nesting boxes, driveway construction, pollinator friendly features | Community Partnerships | Development Management | August 2022 Action completed | N/A |  | PDF leaflet is produced and planning are sending it planning acknowledgements

## Efficiency of Existing Building
Theme: Efficiency of Existing Buildings
Aim: Improve industrial, commercial and domestic energy efficiency in the District in existing buildings.
We will / Objective: | Action: | Responsibility of [Department/Officer]: | Delivery Partners: | Completed By / Delivery Date: | Budget | Milestones: | Status and Comments: | Action Progress
Publicise and assist the accessibility of any grants or incentive schemes which help reduce the carbon emissions of existing buildings including the Councils own and associated public buildings. | Complete Green Homes Grant schemes (LAD1B, LAD2 etc.). Commence new ECO4 scheme with E.ON. Continue to manage the SHDF Wave 1 scheme through to successful completion. (Officer appointed to manage.) Take all other grant-funded retrofit opportunities as they arise. | Community Partnerships | Watford LAD1B: Watford Borough Council (WBC) and E.ON. Hertsmere LAD1B: Hertsmere Borough Council (HBC) and National Energy Foundation. LAD2 + LAD3: South East Energy Hub. ECO4: E.ON and any other obligated energy companies. SHDF Wave 1: Watford Borough Council, Thrive Homes, Watford Community Housing, and OVO Energy. | June 2022 for Hertsmere LAD1B, September 2022 for Watford LAD1B. September 2022 for LAD2 , and March 2023 for LAD3. March 2023 for SHDF Wave 1. March 2026 for ECO4. | To date Grant received:- £2.67m shared with HBC and WBC LAD2 Grant via Energy Hub £340,000. LAD3 allocated £660,000 by Energy Hub - participation not yet confirmed by BEIS. ECO4: funding from energy companies - no grant funding received. £10,000 paid for officer resource to promote and support project. SHDF Wave 1: £1,647,692.7 | Hertsmere LAD1B project complete by June 2022. Watford LAD1B project complete by September 2022 (for physical installs). LAD 2 to complete September 2022. SHDF Wave 1 to complete March 2023. ECO4 scheme to begin Autumn 2022. EN 08/08/22 | The Hertsmere LAD1B project completed successfully in June 2022, having improved the energy efficiency of 78 homes across both areas. The Watford LAD1B scheme completed 174 homes in September '22. LAD2 has completed but waiting for outcomes from the South East Energy Hub who ran the project. TRDC has been accepted in to the Energy Hub's LAD3 scheme. This is running until March '23. All schems can be accessed from Home Energy Support Service TRDC is on Wave 1 of the Social Housing Decarbonisation Fund (SHDF) - a project aiming to improve over 130 social homes owned by Thrive and Watford Community Housing with EWI. The project has moved past initial set up stage and properties are now receiving surveys, with installations due to start in the Autumn (2022). A dedicated Energy Company Obligation Phase 4 scheme in partnership with E.ON, openend in Nov '22. This will enable eligible homes in target areas to receive multiple fully funded energy efficiency measures to improve homes by at least 2 EPC bands. JH 15/11/22 | Hertsmere LAD1B scheme - complete. All other schemes ongoing. EN 08/08/22
| Public Sector Decarbonisation Grants (PSDF) being actively sought by Facilities for all Council properties. | Facilities | Anthesis and new partner (in procurement at present) | Ongoing | Grant funded | PSDF 4 | TRH project server room is complete. Quotes for remainder of the project are being reviewed.
| Review EPC's for Lincoln Drive and Fairhaven Temporary Housing to determine if they can be included in a Social Housing Decarbonisation Fund application. | Property | Property/ Facilities, Watford Community Housing | Application to be submitted by | TBC | Outcome of property review. Action Closed | This accommodation was not suitable for grant funding as EPC's are too high. JH 17/08.22
Ensure utility contracts on Council-owned buildings utilise low-carbon energy tariffs. | Reduce Council emissions in the short term by switching to a Power Purchase Agreement which utilises traceable renewable energy sources for 50% of requirement and green tariff for the remainder. This removes 86% of Scope 2 emissions (284 tonnes of carbon) | Procurement | LASER Energy | Autumn '22 | approx. £20k to move gas and electricity to PPA, and offset - report submitted to P&R committee | CMT August '22 | Report to CMT 9/8/22, this being progressed to JLT JH 5/8/22
| Review with Leisure Contractor to determine what the opportunities are for them to adopt Green tariffs or PPA agreements. | Leisure | SLM (Everyone Active) |  | Unknown as yet |  | Decarbonisation studies are currently being undertaken. This will help to review any opportunities KB 08/08/22 |  | KB
Support the retrofitting of buildings for energy efficiency where planning permission is required. | Work with planning teams to discuss how they can support retrofit where planning is required. | Community Partnerships / Facilities | Planning | Ongoing | N/A |  | Planning permission given for EWI installation on one property in conservation area. Will be asking for more with the ECO4 project in the same area. Lawful Development Certificate sought by housing provider on SHDF Wave 1 project for works necessary to support EWI under PAS2035 standards. (EN 08/08/22) | Ongoing
Work with the utility companies to improve energy efficiency in homes locally. | Delivering the Green Homes Grant with E.ON , in addition to working with obligated energy companies to deliver ECO Flex funding to eligible residents. | Community Partnerships | E.ON, National Energy Foundation (helpline), OVO Energy and any other obligated energy companies. | Ongoing |  | Ongoing monitoring | ECO3 Flex contract with YES Energy has finished as funding provision is complete. ECO4 scheme with E.ON will commenced in November 22 for whole house retrofit. Major projects being planned in South Oxhey, Carpenders Park and Oxhey Hall /Hayling. The Council will support all other obligated energy companies or their delivery agents, in signing and verifying ECO Flex declarations through the National Energy Foundation's quality-checked Flex Supplier Network. JH 14/11/22 | Marketing letters for ECO4 target homes to be distributed Nov'22
Report on the implementation of residential energy efficiency measures in the District in line with the Home Energy Conservation Act. | HECA Report to be completed annually. | Community Partnerships | Facilities, Housing Associations | 2020/21 report submitted July 2021 | N/A | Completed Annually
Encourage housing associations, commercial properties, homeowners and landlords, and public buildings to adopt energy efficiency measures as soon as possible. | Publicise minimum energy efficiency standards for the private rented sector on Council website. District landlords who are not meeting the minimum standards will where applicable, be offered Green Homes Grant funding. | Housing | Facilities / Regulatory Services | 2021-11-01 | N/A | Properties on the Council's private rental scheme that currently have a low rating Energy Performance Certificate (Below D) have been identified | Letter to be sent out to the landlords of the properties identified, following template letter to be drafted by the Residential Environmental Health department. Website provides information on MEES for landlords. (EN 08/08/22) | Letter completed and website updated. | Jason - is the action now complete, and therefore closed/
| New Action Seek approval and then produce a Housing Decarbonisation Strategy to identify the scope and scale of the task to decarbonise existing housing stock in Three Rivers. The Strategy will identify actions to promote and enable increased uptake of retrofit and renewable energy capacity in the district. | Community Partnerships |  | August '23 |  | Approval to Progress Autumn '22 | Report to seek approval being submitted to CMT September '22 (JH 08/08/22)
| Contact letting agents and make them aware of best practices regarding energy efficiency and grant opportunities to share with landlords. | Housing | Housing | 2021-11-01 | N/A | List of letting agents to be compiled by September 21 | Annual Letter to Letting Agents advising them of legislative updates, grant opportunities and retrofit guidance / example case studies. Due to staff vacancy, this action point has not been progressed as yet. | list compiled
| Work with Housing Associations to reduce emissions in their stock by applying for Social Housing Decarbonisation Fund | Community Partnerships | WCH, Thrive, and other interested housing providers | Ongoing | SHDF Wave 1: £1.6m grant, part of £3m project funded by Thrive and WCH | subcontractors appointed Work on the ground commenced | TRDC is currently working with Thrive Homes to submit a bid to SHDF Wave2 to retrofit ~120 social homes and up to 30 private homes in South Oxhey. SHDF Wave 1 as above | Action ongoing
| Undertake Energy Audits for all relevant Council properties in order to understand what has to be done to reduce emissions, and be in a position to seek grant funding. In the immediate term complete EPC for TRDC owned assets in order to assist the prioritisation and route to zero calculations. | Facilities / Property | In procurement at present as part of the Route to Zero consultancy project. Although work has started via Facilities contractor on Three Rivers House | 2023-03-01 | In Buildings Decarbonisation Budget. EPC in property budget | Surveys completed Dec 2021 Reports expected March /April 2022 Action Closed | All council buildings have been surveyed, detailed options report expected by April 2023 JH 16/8/22
| Complete EPC's for Council owned tenanted assets in order to determine the exact position of the estate and what improvements are required to meet the new legislative requirement on energy efficiency for landlords. | Property | Property | 2022-03-01 | In budget | 90% complete | EPC’s have been undertaken across the asset portfolio. Of these properties, only one has fallen below the required E rating, and this is not a leased property; Barn Lea, which is ‘let’ out on a hire by session basis.
| Produce a report detailing work and investment required requirement to raise EPC's of tenanted assets to an EPC of C and above in readiness for 2025 legal requirement. | Property | Property | 2023-03-01 | To be managed by individual report | Report complete | A spreadsheet has been compiled which reviews the areas for improvement taken from the recommendation reports from each survey. This will inform the basis for moving all properties to a C.

## Water and Flooding
Theme: Water and Flooding
Aim: Reduce water consumption, prevent contamination of our river network, and mitigate and provide resilience to the increasing risk of flooding due to climate change.
We will / Objective: | Action: | Responsibility of [Department/Officer]: | Delivery Partners: | Budget | Completed By / Delivery Date: | Milestones: | Status and Comments: | Action Progress
Assess the Council’s water consumption across its estate and implement measures and targets to achieve substantive reductions. | Monitor water consumption across the Council estate annually | Facilities | Leisure and Landscapes, Grounds, Property, Facilities, Community Partnerships and Water supplier, | N/A | Figure are collated annually | Annual Collection Water Procurement Commenced | Water data has been collected for previous 3 years. However it is patchy and very difficult to obtain. Hence a new contract for a water supplier will need to be re-procured to ensure the new contract has provision of annual data by smart meter where possible, plus installation of water saving devices. | The limited data available is collated and is shortly to be sent to procurement to retender the contract.
| All new Council buildings to achieve at least 4 BREEAM credits which means a 50% improvement on water efficiency over a baseline calculation | Property / Facilities | Contractors | In new depot budget | Action complete until another new building is constructed. | Depot finished and opened | Depot achieved x BREEAM credits for water provision
Require new development to adopt the toughest Building Regulation water efficiency target of 110 litres per household per day and for non-residential development to achieve a rating of BREEAM excellent for water efficiency. | Making planning policy provision to: - Ensure all new developments use Part G option for 110 litres per capita per household as consumption target and to use the fittings methodology. | Planning Policy | Development Management | N/A | In revised local plan draft policy Summer '23 | Local Plan adoption | 110 litres requirement in draft Local Plan
| Draft Local Plan requires that new developments conserve water risk by installing measures such as water butts and efficient appliances. | Planning Policy | Development Management | N/A | In revised local plan draft policy Summer '23 |  | In local plan draft policy |  | 4
Work in partnership on a catchment-scale with key stakeholders including environmental charities, catchment partnerships and neighbouring local authorities to protect and enhance local rivers and the habitats which surround them. | TRDC Water Partnership set up to address issues of flooding, sewage discharge, over abstraction and to ensure that water infrastructure is aligned with development requirements. | Community Partnerships | Officers and Members of TRDC, Thames, Affinity, Colne Can and relevant CVS's | N/A | Started Nov '21. Action complete | Bi Annual meetings | 2 meetings have taken place, the last with a focus on the issues connected with HS2. Water Partnership is hosting an engagement event for Affinity to explain their Water Resources Management Plan consultation to stakeholders.
| New Action Continue to host the TRDC water partnership (WP) to address issues of flooding, sewage discharge, over abstraction and to ensure that water infrastructure is aligned with development requirements. | Community Partnerships | Officers and Members of TRDC, Thames, Affinity, Colne Can and relevant CVS's | Ongoing | N/a | Meetings twice per year | JH 05/08/22
| Attend Colne Can Catchment Partnership to ensure the partnership can benefit from Local Government influence as required. | Community Partnerships | Colne Can | N/A | Ongoing, a | Attend meetings | commenced
| Work with key stakeholders to ensure that the raw sewage discharges in Harefield Road and other areas are managed effectively, both in terms of the clear up, but also long term infrastructure planning | Residential Environmental Health / Community Partnerships | Thames Water, Environment Agency, Lead Local Flood Authority | N/A |  | Letter to affected residents from Thames Water. Agreed process for clean-ups. | Thames Water have researched Harefield Road and established a meaningful solution is not possible within current budget. They have not sent a letter to residents advising this, despite may requests from TRDC. Hope is that Maple Cross and associated catchment is addressed in the next round of amp funding. The sewage flood in Batemen Road due to a concerted effort by residents, members and officers has benefitted from a thorough investigation by Thames, and is waiting for repairs to take place
| Receive results on the quality of our 3 key rivers from Environment Agency tests annually, in order to monitor progress of the partnerships and other organisations. | Residential Environmental Health | Environment Agency | N/A | Action Closed |  | The EA are unable to provide this information so this action cannot be taken forward.
Reduce consumption by working with Affinity Water to produce comprehensive actions plans to reduce water consumption and leakage, aid the adoption of compulsory water metering, and installation of water saving devices. | Facilitate contact between water companies and housing associations in support of the installation of water saving devices. | Community Partnerships | Affinity Water, Thrive, Watford Community Housing | N/A | Ongoing | LSP September '22 | Watford Community Housing are working to a limited extend with Affinity. Affinity attending LSP Sept '22 to advise offer to all other Housing Associations in the District.
Raise awareness among residents of the link between water consumption, waste and the health of chalk rivers. | Support water company campaigns such as the Affinity SOS campaign, to provide education on the value of water-saving behavioural change, by sharing their resources among residents, schools, and Members. | Community Partnerships | Affinity Water | N/A | Ongoing. Waiting for Affinity's new plan to be announced. | Reduce water consumption as measured by Affinity, by 10 litres per capita. | Campaign has had huge success with over 80,000 sign-ups. Planning taking place for 2022 programme
| Update website, use Greener Living newsletters and engagement events to raise awareness of water issues with residents. | Community Partnerships | Friends of the Earth, Comms, Rickmansworth Festival, Affinity and Thames Water | N/A | Ongoing |  | Great Big Green Week pamphlet completed. New planning guidance pdf alludes to this. Climate Change engagement work is constantly raising issue of water at every opportunity. JH 17/08/22
Require a Flood Risk Assessment to be completed for development proposals of 1ha or greater in an area within Flood Zone 1 and for any proposals of development within Flood Zones 2 and 3, and prevent development in areas at significant risk of flooding. | Require a Flood Risk Assessment to be completed for development proposals of 1ha or greater in an area within Flood Zone 1 and for any proposals of new development within Flood Zones 2 and 3, and prevent development in areas at significant risk of flooding. | Planning Policy, Development Management | Development Management/ Environment Agency | N/A | Ongoing | In operation | Ongoing | Ongoing, requires planning policy to support requirement
Refuse development if it is subject to unacceptable flood risk or if it would exacerbate flood risk on site or elsewhere. | Review Flood Risk Assessments/SUDS seeking Environment Agency & Lead Local Flood Authority advice if necessary to determine if development should proceed. Adhere to policy requiring that new developments are located at least 8m from main rivers and 5m from ordinary watercourses | Planning Policy, Development Management | Lead Local Flood Authority (LLFA),Environment Agency, Development Management | N/A | Ongoing |  | In draft local Plan Section 7.31. | Ongoing
Require Surface Water Drainage Strategies for all major development and where appropriate, for minor developments. | Surface Water Drainage Strategies required for all major developments. | Planning Policy, Development Management | Development Management / LLFA | N/A | Ongoing for major development |  |  | Ongoing
| Arrange CPD session by Hertfordshire Building Control (HBC) to raise awareness amongst building professionals on the problems and solutions to groundwater flooding caused by paving front gardens. | Community Partnerships | HBC | N/A | Autumn 2021 Action closed | Completed .
| Raise awareness among residents and agents of the CLG/Environment Agency's 'Guidance on the Permeable Surfacing of Front Gardens' when contacting the Council about development of front driveways. Add a policy requirement for hard surfaces to be permeable. | Community Partnerships | Development Management, Planning Policy Community Partnerships | N/A | Action complete | Planning Guidance document completed | Draft local plan has policy requirement for permeable driveways. Planning Guidance document https://www.threerivers.gov.uk/egcl-page/home-energy-efficiency on website and being issued with all planning acknowledgements
Work with the Local Lead Flood Authority to assess the sites within the District which are susceptible to flooding. Work with stakeholders, farmers and land managers to reduce the flood risk using natural flood management and sustainable drainage systems. | Consult water and sewerage undertakers at planning stage for all major developments of ten homes or above. | Development Management | Thames Water, Affinity Water | N/A | Ongoing Action closed |  | Current policy | ongoing
| Use Management Plans to provide flood alleviation and biodiversity benefits where possible. | Leisure and Landscapes | Countryside Management Service | Some projects are within existing budgets, others would need separate report. | Ongoing | Oxhey Wood Management plan in production, target March 2022 | Bishop Woods have leaky dams, these are being reviewed for Oxhey Woods. Management Plan for committee should be available by August 2022 .
| NEW LLFA have reviewed historic flooding in Three Rivers and have planned two pilot projects to asses the effectiveness of retrofit SUDS as a base for learning to take forward across the county. The sites are Northwood and South Oxhey | LLFA | Water Partnership Group | Grant funding has been acquired for planning and engagement phase. Additional funding will be needed for installation, and may require an application to CILL | 2027 | Stakeholder Engagement Meeting | Stakeholder meeting attended by TRDC landscape officer. Consultant WSP has been appointed for planning and engagement. Plan needs to work with TRDC open space management programme

## Sustainable Travel and Air Qual
Theme: Sustainable Travel and Air Quality
Aim: Enable and encourage journeys made by sustainable transport modes to reduce carbon fuel reliance, improve local air and environmental quality and promote sustainability.
We will / Objective: | Action: | Responsibility of [Department/Officer]: | Delivery Partners: | Budget | Completed By / Delivery Date: | Milestones: | Status and Comments: | Action Progress
Enable and encourage cycling and walking trips to replace carbon fuelled trips, through our updated Walking & Cycling Strategy by: - building new paths and upgrading existing paths, - promoting routes to key local destinations, - installing and influencing strategic infrastructure (including comprehensive cycle parking and other support facilities like Cycle Hubs), and - creating promotional opportunities with external partners. | Progress the emerging review of the Cycling and Walking Strategy (part of the Sustainable Travel Strategy) to adoption . | Transport & Parking Projects | HCC, WBC, DfT | In cycling and walking schemes and cycling strategy budgets | Expected December 2021 | Public consultation expected to be published end of 2022 | Draft strategy under review following outcomes of stakeholder engagement. | 1
| Progress delivery of any agreed schemes through our existing and future Cycling and Walking work programmes (including Walking Wayfinding, Cycle Parking and Walkability schemes) |  |  |  | Ongoing | Not known | Croxley Walking Wayfinding scheme introduced summer '22.
| Promote our networks to local community groups, integrate local data to improve travel planning and increase support and awareness using local events and other marketing options |  |  |  | Ongoing | N/A | Active travel promoted continuously here:-vwww.threerivers.gov.uk/cyclin
Continue to develop, promote and improve passenger transport and infrastructure (bus and rail) and the public experience and perception of services. | Develop new Community Travel options (including Community Shopper Service) to give wider choice | Transport & Parking Projects |  | In existing budget | Action Complete |  | New Community Shopper service started March 2022
| Investigate and implement real time bus information at bus stops in conjunction with HCC | Transport & Parking Projects |  | External business support funding
Encourage fuel-efficient private hire vehicles and taxis. | Support the HCCSP led approach to develop a coordinated future taxi licencing policy to facilitate an accelerated shift to fully electric taxis being the norm across Hertfordshire. | Licensing / Transport & Parking Projects | HCCSP / Taxi Firms | N/A | 2023-03-01 |  | HCCSP have surveyed all LA's to establish baseline policies, next steps is meeting between all LA's to agree way forward |  | Support electric Blue published a vision to convert the whole taxi fleet electric by 2028, sustainability development committee agreed in principle
Reduce environmental impacts arising from commercial transport (including Three Rivers Council), by promoting and supporting Travel Plans which encourage homeworking, shared mobility and new forms of travel (such as hydrogen and electric). | Produce updated Green Travel Plan for staff and where feasible and funded introducing enabling measures. | Transport & Parking Projects |  | In existing budget | Expected March 2022 |  | New Travel Planning tool procured to assess potential carbon savings from staff mileage.
| Report to Lead Member on shared mobility options | Transport & Parking Projects
| New Ways of Working being introduced for Council employees, which will see a blended approach of home and office work. | Transport & Parking Projects, Facilities | N./A | N/A | Action complete |  | NWOW started 1 April 2022 NWOW introduced, includes reduction of staff attendance to one day per week..
| Support local Business Travel Plans through Smarter Choice project, Bike to Work sponsorship scheme and Cycle parking improvements to enable commuting using non-car modes. | Transport & Parking Projects |  |  | Scheme started July 2021 |  | Scheme ongoing; enhanced Jan 2021 to focus on major employers.
| Review the TRDC Fleet to consider the options for low carbon alternatives | Environmental Protection |  | N/A | Ongoing | Completion of Government Resources and Waste Strategy Outcome of Eunomia research | Electric charging points have been installed at the new Depot. Two Electric vans are due i Oct & Nov '22 for Enforcement and Animal Welfare Licensing Officers. The fleet team are working with several other Hertfordshire authorities to assess alternative fuel options to decipher how to decarbonise the fleet performance in a cost effective manner.
Monitor and review air quality across the District to determine whether national air quality objectives are being met. | Continue to monitor air quality and submit an Annual Status Report (ASR) to DEFRA ensuring any recommendations are considered and implemented accordingly | Environmental Health (Commercial) | N/A | In existing budget; external grant funding where applicable. | Ongoing | 20/21 ASR submitted and recommendation reviewed | March '22 12 new diffusion tubes agreed in in the Air Quality Management Plan and District to ensure sufficient monitoring of air quality.
Ensure that we request and where possible require the provision of sustainable low- and zero-carbon transport infrastructure in new developments. | TPP checks to ensure opportunities are maximised through all major applications by LHA and DM comments | Transport & Parking Projects | HCC | In existing budget | Action completed | N/A | Applications checked as required. Action no longer required after June 2022 following legislative change.
Continue to expand and encourage electric vehicle charging infrastructure around the District. | Promote EV options to local people | Transport & Parking Projects | DfT | In existing budget Investigating funding opportunities to develop proposal | Ongoing | N/A | Latest updates with regard to EV charging can be found at https://www.threerivers.gov.uk/egcl-page/electric-vehicle-charging April 2022 there are 60 public charging points. Pilot EVCP sites in Council car parks scheme finalised following scope changes and expected to deliver in May '23
| Provide EV information and (subject to consents and budgets) EV charge points on land owned by the District Council. | Transport & Parking Projects | DfT | Investigating funding opportunities to develop proposal | Ongoing | N/A

## Waste
Theme: Waste and a Circular Economy
Aim: To reduce the volume of waste produced and manage it sustainably through promoting a circular economy.
We will / Objective: | Action: | Responsibility of [Department/Officer]: | Delivery Partners: | Budget | Completed By / Delivery Date: | Milestones: | Status and Comments: | Action Progress
Further reduce waste and increase proportion of recycling and reuse within Council operations, including contractors and suppliers we work with through policy change. | Understand what waste we produce by carrying out an internal audit across Council buildings every 5 years. | Facilities |  | N/A | Ongoing | 2022 for first audit.
| Undertake regular staff awareness-raising around office recycling and the reduce, reuse, recycle hierarchy. | Facilities | Environmental Protection Communications Team, HR | N/A | Ongoing | Publish waste awareness materials quarterly among staff.
| Continue to promote the S.C.R.A.P Fly tipping Campaign; working with the Police, Environment Agency and community groups to reduce fly tipping. | Environmental Protection (JP), Communications Team | WasteAware/Police/Environment Agency | N/A | Ongoing |  | Social media posts continue, and ongoing attendance and input into Hertfordshire Fly Tipping Group ER/JP 11/08/22
Reduce the total amount of household and commercial waste produced, and minimise waste entering landfill and energy from waste plants through maximisation of reuse and recycling. | Review and seek opportunities to increase the reuse of furniture and large items collected by the Council in bulky waste collections. | Environmental Protection | Hertfordshire County Council/WasteAware | N/A | Ongoing |  | Discussions commenced at Waste Aware on how to optimise use of re-use centres, or find specialist recyclers
| Encourage the use of home composting where possible for food and garden waste. | Environmental Protection (ER) | Environmental Protection, Comms, WasteAware | N/A |  |  | Ongoing
| Work to reduce edible food waste from households. | Environmental Protection (ER) | Environmental Protection, Comms, WasteAware | N/A | Campaign to begin October 2022 ER/JP 11/08/22 |  | A campaign is being produced by WasteAware with the support of a Three Rivers Officer | The materials have undergone market research and pilot campaign is set to commence in Three Rivers in November 2022 following the development of further campaign materials and assets
| Continue to encourage the uptake of garden waste collections in the District where home composting is not possible. | Environmental Protection, | Hertfordshire County Council/WasteAware/Communications Team | N/A | Ongoing |  | Currently between 75% and 80% of eligible properties use this service
| Start to investigate how the Council may offer food waste collections to trade customers in line with future Government targets. | Environmental Protection | Environmental Protection | N/A | 2023-03-01 |  | This action would work towards the Government target within the Resources and Waste Strategy that 65% of municipal waste must be is recycled by 2035.
| Encourage the use of reusable nappies and period products through annual events and ongoing promotions. | Environmental Protection (ER) | Environmental Protection, Comms, WasteAware | N/A | Ongoing |  | A number of event's have been held in different locations including Rickmansworth Festival and Leavesden HIVE. Social media promotions continue. 3 in person reusable nappy events done.
| Look into how to increase the uptake of food collections from flats in District. | Environmental Protection | Environmental Protection, Waste Aware, Comms | N/A | 2023-03-01 |  | We are beginning to collect data on the current uptake and barriers to food waste collections in flats.
Maintain our position as the highest recycling authority in Hertfordshire. | The waste service provided has enabled such a high recycling performance. To keep improving it will be essential to follow actions in the this plan for example increasing food waste collections in flats and continue to promote waste reduction, in particular hard to recycle and non-recyclable items. | Environmental Protection | Environmental Protection Hertfordshire County Council/WasteAware | N/A | Ongoing |  | In 2020/21 we were 3rd in England, 2nd in Hertfordshire with recycling rate 63.1% | Currently awaiting latest figures
Continue to be an active member of the Hertfordshire Waste Partnership - working as a county to make waste collections more consistent and efficient, as well as engaging with producers and national bodies to improve packaging and recyclability. | Await results of Government Waste and Resources Strategy consultation in order to guide any future services changes and or communications. | Environmental Protection | Hertfordshire Waste Partnership / Central Government, Environmental Protection | N/A | Ongoing | Consultation outcomes published.
| Be part of at least two sub-groups specialising in a particular county-wide waste campaign or project. | Environmental Protection (ER) | Hertfordshire Waste Partnership | N/A | Ongoing |  | Currently part of the Reducing edible Food Waste, Herts Sustainable Periods, and Real Nappy sub-groups | First round of training teachers in sustainable periods was a success, the second round is commencing October/November 2022. The nappy scheme is due to expand with real nappy training for nursery and childcare staff training.
| Attend monthly Waste Partnership meetings to remain informed on going projects and to enable effective County wide communication and initiatives to be progressed. | Environmental Protection | Hertfordshire Waste Partnership | N/A | Monthly - Ongoing
Consider all suitable technology when replacing waste collection vehicles to reduce their carbon footprint, and continue to use them for promotion of reuse and recycling. | Continue to rotate and update signage on waste collection vehicles to encourage waste reduction, recycling, and other waste related issues. | Environmental Protection | Hertfordshire Waste Partnership | N/A | Ongoing |  | New litter campaign banners have been placed on vehicles to replace COVID-19 banners. Banners will continue to be rotated and updated as appropriate.
| Investigate the replacement / upgrade of waste vehicles with ULEV / Biogas / Hydrogen fuelled vehicles (including establishing fuel infrastructure) | Environmental Protection |  | N/A | Ongoing | Kick off Meeting September 2021. Completion of Government Resources and Waste Strategy | Research to establish what position all Herts Local Authorities are at, has completed. Kick off meeting to discuss the issues and possibilities. Learnings to date show technology is still unproven, but this action will review the options. Discussions have commenced with APSE and Eunomia | Electric charging points have been installed at the new Depot. Three Electric vans are due in the Autumn for Enforcement and Animal Welfare Licensing Officers. The fleet team are working with several other Hertfordshire authorities to assess alternative fuel options to decipher how to decarbonise the fleet performance in a cost effective manner.
Extend the plastic free policy of the Council by encouraging the local communities to adopt “plastic free” through supporting local low-waste businesses and refill points. | Refill scheme in Three Rivers has 20+ water stations. To increase participation, use and extend to other refills stations such as reusable coffee cups discounts a coordinated communication plan is being devised. | Environmental Protection, Communications Team | Hertfordshire Waste Partnership |  | Ongoing | Media commences 2022 | Ongoing promotions have taken place over the year, and Green Living newsletters have promoted the scheme particularly in summer. | You can find more information about refill here, along with a list of Hertfordshire's Refill shops: https://www.hertfordshire.gov.uk/services/recycling-waste-and-environment/recycling-and-waste/wasteaware-campaigns/reusables.aspx
Continue to engage with the community, and educate residents on recycling and reuse through schools, events, and social media campaigns. | Continue to provide resources to schools, businesses and residents on what to recycle and how. | Environmental Protection |  | N/A | Ongoing |  | Residents continue to receive information through social media, TRDC website and Greener Living newsletter. Trade customers receive recycling poster. New Sustainable Schools page now available with resources relating to a range of topics including increasing recycling. School talks have re-commenced.
| Encourage the establishment of repair shops/cafes, library of things, furniture re-use and skills workshops for local people through the Sustainability Fund and signposting enquiries to existing providers to share knowledge. | Environmental Protection, Communications Team |  | N/A | Ongoing |  | 14 community groups have received the funding so far, including iChooser who are using the funds to restore furniture. | Currently have had no interest aside from iChooser from external partners/residents in starting up a repair café or similar. We continue to promote the community sustainability grant.
| Support community litter-picks by providing equipment to volunteers and increase local awareness of the available support and opportunities. Use National events such Great British Spring-clean to encourage uptake. | Environmental Protection | Resident Action Groups/ Friends of Groups | N/A | Ongoing | Partake in Keep Britain Tidy 'Great British Spring Clean' event and 'Great British School Clean' event in 2022 and thereafter. | Part of communication plan and information is available on the website. Equipment was borrowed by residents and community groups for use during the Great British Spring Clean.
Reducing waste and alleviating food poverty by connecting retailers, hospitality and households to share edible excess food. | Support organisations through the sustainability Fund and signposting enquiries to assist their success and growth. | Environmental Protection, Communications Team | Resident Action Groups/ Friends of Groups. WasteAware/Sustainable Hertfordshire HCC group. | WasteAware and Sustainable Hertfordshire budget. | Commencement of trials in October 2022 | Communicate this idea a residents events such as Rickmansworth Festival and through engagement with Parish Councils, Residents Associations, and Friends Of groups. | Working towards an Edible Food Waste reduction pilot campaign to launch November 2022 with WasteAware and Sustainable Hertfordshire. | This was due to begin in April, however the group decided to spend extra time on research and developing artwork and communication materials. The group also wanted the 6 month trial to cover the Christmas period.
| Consider a networking event to bring together organisations in the District involved with Food sharing, food poverty and food suppliers in order to reduce food waste | Environmental Protection | Community Partnerships | N/A | Ongoing |  | Sharing excess food presents too many obstacles at the moment including food safety, hygiene and allergens | An event was held at Woodoaks Farm and formed part of the research for the Edible Food Waste reduction campaign. It was attended by a wide range of people who work with food.

## Biodiversity
Theme: Biodiversity
Aim: To ensure net gains in biodiversity to address the ongoing Ecological Emergency, protect and enhance precious habitats and species, and utilise nature to build climate resilience.
We will / Objective: | Action: | Responsibility of [Department/Officer]: | Delivery Partners: | Budget | Completed By / Delivery Date: | Milestones: | Status and Comments: | Officer comment
Ensure that all TRDC-owned land is managed sustainably and for the benefit of biodiversity and soil health. | Ensure all major TRDC Open Space has an up to date management plan with a focus on biodiversity and recreation. These plans will continue to evolve to incorporate new and different habitats, supporting a variety of species. | Leisure and Landscapes | Countryside Management Service (CMS) | Updating of Management Plans on a cyclical basis is included within the main Trees and Landscapes budget. | Ongoing | Annual work programme review with CMS | All major sites have current management plans. Aquadrome has a new management plan being drafted and this is due to go to LEC committee in June 2022 | Major sites include: Aquadrome, Leavesden Country Park, Chorleywood House Grounds, South Oxhey Playing Fields, Croxley Common Moor, Withey Beds and Woodlands, including Bishops Wood, Carpenters Wood
| Conduct an audit of TRDC land to evaluate the existing biodiversity value of minor council-owned land (developing a biodiversity baseline) and identify opportunities to further support and enhance biodiversity. | Services Leisure and Landscapes | Countryside Management Service | Audit Funded by Herts Sustainability Fund. Biodiversity Net Gain and grant opportunity will be sought to deliver initiatives found. | March 2022 | Report March 2022 | Biodiversity Opportunity Audit (BOA) Report is due to go to March P&R and LEC committees. audit complete and new management plan adopted
| The biodiversity opportunities audit above will inform the District Tree Strategy resulting in a long term plan for new tree planting on TRDC land. The aim of the District Tree Strategy is to significantly increase the number of trees. | Leisure and Landscapes | Countryside Management Service and Grounds | The long term plan to be produced with existing resource, the outcome will require additional budget which sought from Biodiversity Net Gain, grants and separate reports where necessary. | Tree Strategy January 2022. Tree planting plan end of 2022 | Opportunity audit completed and Tree Strategy adopted. | BOA identifies new planting opportunities, and is due to go to March committee
| Continue to support Conservation Volunteering on TRDC Open Space through Friends groups and volunteer work days. | Leisure and Landscapes | Countryside Management Service | N/A | Ongoing | Ongoing | Ongoing, Community Biodiversity Officer has been appointed to provide additional support to groups
| Review outcome of biodiversity audit and pilot reduced mows sites to inform the future mowing management regimes. | Leisure and Landscapes | Countryside Management Service, Grounds. | Outcome of pilot project will require a separate short report to identify potential resource requirements, and therefore inform the roll out programme. | Report by March 2022 | Biodiversity audit completed, autumn pilot mowing regime completed, draft Action Plan March 2022. | BOA Report is due to go to March committees
Assess how biodiversity can be enhanced across the District and on TRDC own land to provide climate mitigation benefits and community resilience to the effects of climate change. | Develop a Biodiversity Baseline across the District to quantify existing levels of biodiversity across Three Rivers. | Community Partnerships (via HCCSP) | HCCSP/CMS | £2,000 in Climate Change Budget | March 2022 | Partner appointed | Baseline audit reaching final stages and will be presented to HCCSP April 27th 2022 | Baseline work completed
| Produce a Three Rivers Biodiversity Strategy which will encompass a number of actions outlined here and the Local Nature Recovery Strategy requirements of the Environment Act. To be called Three Rivers Nature Recovery Strategy | Leisure and Landscapes | Leisure and Landscapes/ Community Partnerships | Manage within existing budgets. Delivery of the strategy to be managed by seeking grant funding, Biodiversity Net Gain and separate report if required. Environment Bill may require some officer funding through new burdens fund. | 2022-12-01 | Environment Bill enacted. Publication of regulation requirements and new burden funds availability- if any. Anticipated 2023 | New Community Biodiversity Officer has initiated a kick off meeting to scope themes and timing | commenced
| Raise awareness of light pollution amongst residents to lower emissions, and protect wildlife from light pollution, where this does not conflict with public safety. | Community Partnerships | Community Partnerships | N/A | Ongoing | Great Big Green Week pamphlet, to be launch September 2022, then will remain on website. | Article in Great Big Green Week arranged and in newsletter, identified in planning guidance document
| Review how to restrict / discourage the use of sky lanterns and balloon releases and require the clean-up of firework debris at licenced premises and regulated events. | Licensing | Licensing | N/A | March 2023 |  | Legal have advised the parameters available to the Council.
Encourage ecologically-resilient and varied landscapes to ensure habitats remain diverse and adaptable to the impacts of climate change, thereby safeguarding local flora and fauna. | Avoid tree monocultures and use mixed species plantings to ensure the resilience of Council’s tree stock against new pests and climatic changes. | Leisure and Landscapes | Leisure and Landscapes | In budget | Ongoing | Tree Strategy Complete Ongoing approach to tree management | , work currently taking place to remove non-native Larch from Carpenters wood, creating space for natural regeneration and replanting with a diversity of species
| Use Management Plans to provide flood alleviation and biodiversity benefits where possible. | Leisure and Landscapes | Countryside Management Service | Some projects are within existing budgets, others would need separate report. | Ongoing | Oxhey Wood Management produced | Oxhey Wood management plan in progress and should be available for comment after August 22 .
Upon enactment of the Environment Bill, require all new development in TRDC to result in a 10% net-gain for biodiversity (preferably within the District) and avoid the fragmentation, damage and isolation of existing habitats. | A report to be prepared to consider the resource requirement for a dedicated officer to ensure the requirements of the Environment Act (and Local Plan once adopted) can be implemented. | Development Management | Development Management / Leisure and Landscapes/ Community Partnerships |  | N/A | Publication of regulation requirements and new burden funds availability- if any | Consideration is being made to utilise a shared service via Herts LEADS provided by Herts County . SPD for site allocations will be required.JH 19/8/22
Support landowners in the District to enhance their land for biodiversity through rewilding, tree planting, improving soil health, and creating wildlife corridors. | Restore habitat along 350m of the River Gade to protect endangered water voles | Community Partnerships | Herts and Middlesex Wildlife Trust | £6,500 from 2019/2020 budget (HMWT sources additional funds) | work due to be completed November 2021 | contractor commences September 2021 | Almost Complete
Encourage local residents and householders in the District to improve their gardens and open spaces for biodiversity. | Facilitate community wildlife events, such as guided walks, open days and other events on TRDC open spaces. | Leisure and Landscapes | Park Ranger / Friends Groups Countryside Management Service / Park Rangers |  | Ongoing | New biodiversity officer appointed | Regular activities are taking place at Leavesden Country Park, and it is planned to extend this to more areas with the appointment of the new CBO
| Provide advice in communications plan to encourage residents to improve garden wildlife through suggestions such as wildlife corridors, pollinator friendly plants, and by sharing initiatives such as the Queens Green Canopy | Community Partnerships | Leisure and Landscapes/ Community Partnerships | Proposal made to CMT for a Community Biodiversity Officer Within existing headcount budget. | Part of a series of communication events | Great Big Green Week pamphlet and included in communication plan. Ongoing | Green Living Newsletter and website advice, events such as Rickmansworth Festival and, sustainability leaflet. Advice on biodiversity enhancing activities also features heavily in "Green Your Home" planning advice document. The "One Step Greener" Challenge has also encouraged a number of actions to improve gardens for nature (EN 17/01/22)

## Adaptation and Resilience
Theme: Adaptation and Resilience
Aim: Create communities, services, infrastructure and environments that are resilient to the unavoidable impacts of the Climate and Ecological crises.
We will / Objective: | Action: | Responsibility of [Department/Officer]: | Delivery Partners: | Completed By / Delivery Date: | Budget | Milestones: | Status and Comments: | Action Progress
Make council services adaptable to extreme weather events and the effects of a changing climate, including the emergence of new pests and diseases. | Ensure extreme weather events and the consequences of them are recorded on SWIMS (Severe Weather Impacts Monitoring System) to enable Hertfordshire County Council and Three Rivers District Council to have an evidence base for risk management. | Residential Environmental Protection |  |  | N/A | Start at next event | https://www.local.gov.uk/case-studies/severe-weather-impacts-monitoring-system-swims
| Identify suitable adaptation training course for heads of service. | Community Partnerships | Local Partnerships/HCCSP | Action complete |  | Training course for core adaptation team. | Key officers attended workshop.
| Each service area to incorporate climate risk adaptation and resilience in their service risk registers and any associated actions in exercise in their service and work plans. Adaptation to be addressed in each relevant committee report using the climate and sustainability impact assessment tool | Committees/Heads of Services |  | March '23 |  | Environment Assessment Tool projects, service risk registers completed | Assessment tool being considered by senior management. Community partnerships to do pilot risk assessment October '22, then review before extending to all services.
Reduce flood risk, and ensure sustainable water supply through engagement with key stakeholders | As described in the Water and Flooding section. 2 Suds installation projects | [5 empty] | See row 23 Water & Flooding
All proposals for development will be designed sensitively to build in resilience to extreme weather events and a changing climate. | As described in the Sustainable Design and Construction section.
Adapt landscapes to provide summer shading, mitigate the ‘urban heat island’ effect, and to slow heavy rainfall to reduce flooding. | As described in Biodiversity Section.
Protecting, improving, increasing, and connecting habitats to help nature thrive and withstand new pressures. | As described in Biodiversity Section.
Encourage local food production through the development of community gardens, allotments, orchards, and support of home grown food, with co-benefits for tackling eco-anxiety. | As described in Food and Agriculture Section. |  | Woodoaks Farm |  |  |  | TRDC actively support the work of Woodoaks Farm who are enjoying considerable success in connecting residents to the land and food production. https://woodoaksfarm.com
Encourage renewable energy generation within the District, working either independently or in partnership to encourage greater energy self-sufficiency. | As described in Energy Section. | [5 empty] | Solar Together campaign had over 1200 registers and 133 housholds accept installations
Reducing waste of edible excess food and alleviating food poverty by connecting retailers, the hospitality sector, and households in local food-sharing networks. | As described in Waste Section.
Engage with local businesses, council tenants, relevant corporates, schools, faith groups, youth groups, parish councils, highways, and campaign and conservation groups to inspire and support each other in adopting pro-environmental behaviours, for example water and energy conservation, waste reduction, and sustainable food consumption. | As described in Enable and Engage Section.

## Food and Agriculture
Theme: Food and Agriculture
Aim: Encourage sustainable food production and consumption in the district, and engage with farmers to improve habitat networks.
We will / Objective: | Action: | Responsibility of [Department/Officer]: | Delivery Partners: | Completed By / Delivery Date: | Budget | Milestones: | Status and Comments: | Action Progress
Identify sites for biodiversity enrichment and habitat networks with land owners and farmers to maximise opportunities for biodiversity gain and climate adaptation. | Biodiversity baseline procured to identify potential sites across the District which will benefit from biodiversity. | Leisure and Landscapes |  |  |  | See Row 9 biodiversity
Publicise local sustainable food producers to connect food retailers, the hospitality sector, and residents. | Develop a list of contacts in the Farming community in order to include support for local food production in our communications plan and identify opportunities to develop stronger links between local producers and local people. | Community Partnerships | Community Partnerships /Communications | Ongoing | N/A | Action closed | woodoaks Farm are driving this action forward, with no spcific resource at TRDC this action is closed. | Objective to be reviewed for Spring '23 update
Encourage local food production through the development of community gardens, allotments, and orchards, with co-benefits for mental health, and enable the creation of these sites in new developments and regeneration projects. | Asses if the DEEP DIG project could be delivered through additional providers and include a training course for growing and preparing fresh seasonal food. | Community Partnerships | Ascend, Hillside Hub, Herts Mind Network | 2023-03-01 | Existing budget |  | DEEP DIG involves teaching new skills to people in need through a community allotment.
Engage with local businesses, relevant corporates, schools, faith groups, and youth groups, to inspire and support each other in adopting sustainable food consumption | The Healthy Hubs deliver a healthy eating course, this will be explored to see how a sustainable approach to food can be included. | Community Partnerships | Healthy Hubs | 2023-03-01 | N/A | Meet with course provider to explore options.
Encourage and support community and school workshops on food growing, food waste, food-related carbon footprints, and cooking with locally-produced, seasonal foods. | Review with partners who work with schools to determine if there is an opportunity within their school work to develop a sustainable approach to food and food waste which could be developed. | Community Partnerships | Services for Young People / South West Herts Partnership | 2023-03-01 | N/A | Initial meeting with partners
| Work as part of the WasteAware sub-group to develop a new food waste reduction campaign to be piloted for 6 months in Three Rivers. The campaign will aim to reduce edible food waste through a social media campaign, in person enegement, and an online food waste challenge. | Environmental Protection/Community Partnerships | WasteAware/Sustainable Hertfordshire | 2023-04-01 | N/A |  | Campaign materials are being developed, campaign set to lunch October 2022
From Herts Climate Change and Sustainability Partnership Action Plan:
The Agricultural Act 2020 passed into law in November 2020. It sets out the new Environmental Land Management Scheme (ELMS)xliii, which will replace existing funding from government to the farming sector. The scheme makes provision for farmers and land managers to be rewarded with public money when they provide ‘public goods’. These goods could include better air or water quality, improved soil health, or thriving wildlife and biodiversity. The scheme is thus designed to help achieve the aims of the 25 Year Environment Plan and the net zero emissions by 2050 commitment.
Actions:
Engage with Hertfordshire’s farming community and other private landowners to explore opportunities to deliver improvements for biodiversity through management which synchronises with individual business models and working practices
Annual