SUSTAINABLE DEVELOPMENT, PLANNING AND TRANSPORT COMMITTEE -

20 JUNE 2017

PART I - DELEGATED

5.	GREEN EXPECTATIONS – SUSTAINABILITY AND CLIMATE CHANGE STRATEGY AND ACTION PLAN 2017-18

(DCES)

1.	Summary

1.1	The Green Expectations strategy for Three Rivers was published in March 2015 and set out aims and objectives for the authority on sustainability and climate change.  This report sets out progress against the Action Plan for 2016-17 to help achieve these aims and objectives and sets out actions for 2017-18.

2.	Details

2.1	In March 2015 Three Rivers District Council published a Sustainability and Climate Change Strategy, Green Expectations.  This set out the environmental and sustainability aims and objectives for the next 5 years.  In order to achieve these objectives an Action Plan is published each year to set and monitor targets to meet the aims and objectives.

2.2	The strategy and action plan was divided into 8 broad themes:

    - Energy and Climate Change;

    - Biodiversity;

    - Waste;

    - Reducing Water Use;

    - Flooding;

    - Sustainable Transport;

    - Sustainable Procurement and Fair Trade; and

    - Climate Change Adaptation.

It also considered the cross-cutting themes of economic development, partnerships, inclusion, education and promotion, and health.

2.3	Under each of the broad themes the strategy set out a key aim.  In order to achieve this aim the strategy outlined 3 objectives.

| For each theme: |  |
| --- | --- |
| First Objective | Direct - An objective which the Council has direct control over (such as the management of our buildings and operations). |
| Second Objective | Indirect - An objective related to our role as a Council. |
| Third Objective | Influence and Partnership - An objective related to our potential for wider influence such as providing information to residents on actions they could take or working in partnership with other organisations. |

2.4	The Action Plan 2017-18 (Appendix 1) brings together information from across the authority to monitor progress on sustainability.  Specifically the Action Plan updates on progress against actions set out for 2016-17 and sets actions for 2017-18 to help achieve the aims and objectives of the strategy. The first objective in each theme area has measurable actions as these are the areas in which the authority has direct control.  There are also actions associated with the second and third objectives which will be tracked over time.

2.5	Good progress has been made in most of the theme areas. Using a traffic light system 32 are green, 5 amber and 1 is red. Data is not yet available for one action.

2.6 	Action 1.1 ‘To improve Three Rivers House DEC rating’ did not reach the target and in fact the rating fell. This was unexpected as according to internal monitoring there was a slight decrease in electricity use and only a small increase in gas use. The building does have much lower gas use than is typical for a similar building. However, the electricity use is higher than typical, which is in part due to the electricity which is needed to operate the ground source heat pump. In addition the certificate covers the whole building including the areas occupied by the Police and CAB.  The police operate 24/7 and out of core office hours they use electricity for heating and in the summer due to security are unable to open their windows, so are more likely to use electricity for cooling. We are expecting continued reductions in electricity use as a result of improvements such as more efficient computers and printers and a full year of the solar panels operating. Unfortunately monitoring does show that there has been an increase in gas use for the building in the last winter period (2016/17), in part due to a faulty temperature sensor and also earlier heating times to ensure the building was warm at the start of the day. As such it is not expected that energy used can be reduced significantly before the DEC certificate is due for reissue on the 1 November 2017.  The Greenhouse Gas Emissions report will cover all of the emissions from the Council’s operations including all buildings and also fleet fuel and business mileage.  This will be available from July and will be reported in a Members Information Bulletin.

2.7 	The number of energy efficiency measures (funded by ECO) installed in the District were higher than expected; Green Flag status has been retained at Rickmansworth Aquadrome, Leavesden Country Park and for the Chorleywood House Estate; UK Woodland Assurance Scheme annual audit was passed; a new recycling system and monitoring process has been established for Three Rivers House and District recycling levels have remained high, although did just miss the target.

2.8	Water use across the Council is now monitored centrally and in 2016-17 provisional data indicates that 12,600m3 of water was used in our managed sites. The aim for next year will be to more closely monitor use and raise awareness with site managers to ensure any leaks are caught quickly and to aim to reduce water use year on year. Water efficiency for new homes is delivered through building regulations and the Council promotes water efficiency.

2.9 	Awareness raising for businesses has focussed on energy efficiency, with the promotion and hosting of Carbon Trust SME energy efficiency training and grants, and trade waste recycling. Water efficiency has concentrated on home rather than specific business water efficiency and as such the indicator is red this year and the action remains in place for 2017/18.

2.10	Actions set out for 2017-18 will generally look to be delivered within approved staffing and budgets but where new opportunities are identified through monitoring, which may require funding or resources, a fully costed report would be presented to the relevant committee for consideration.

3.	Options/Reasons for Recommendation

3.1	To note the Action Status reported for 2016/17 and approve the Actions set out for 2017/18 in the Green Expectations Action Plan (Appendix 1).

4.	Policy/Budget Reference and Implications

4.1	The recommendations in this report are within the Council’s agreed policy and budgets.  The Action Plan helps to achieve the Strategic Plan objective:

We want to maintain high quality neighbourhoods and reduce the eco-footprint of the district.

4.2	The purpose of this Action Plan is to monitor delivery of ‘Green Expectations’ the Council’s Sustainability and Climate Change Strategy, March 2015.

5.	Financial Implications

5.1	None specific.

5.2	It is expected that any costs will be met within current budgets.  In the case of a new opportunity being identified through monitoring which may require funding or resources, a fully costed report would be presented to the relevant committee for consideration.

6.	Legal Implications

6.1	None specific.

7.	Equal Opportunities Implications

7.1	None specific.

8.	Staffing Implications

8.1	The actions identified are within current workplans.

9.	Environmental Implications

9.1	The Action Plan sets out specific actions to directly maintain or improve the environment.  This includes the Council’s direct impact through our operations, indirect impact through our powers to influence local activity or by using our influence to encourage local residents and businesses to reduce their impact on the environment.

10.	Community Safety Implications

10.1	None specific.

11.	Public Health implications

11.1	The Action Plan includes actions to promote improvements in Home Energy Efficiency and to promote Safe and Well visits and the Herts Warmer Homes projects which have positive health and wellbeing as well as energy reduction outcomes.

12.	Customer Services Centre Implications

12.1	Improving information for local residents and businesses may from time to time require updated information to be provided to the CSC.

13.	Communications and Website Implications

13.1	Many of the actions require promotion of information to the public.  This will require the continuation of regular articles in Three Rivers Times, Environment News, and All Aboard, updates to the Three Rivers and Green our Herts websites.

14.	Risk Management and Health & Safety Implications

14.1	There are no risks to the Council in agreeing the recommendation.

15.	Recommendation

15.1	That the Green Expectations Action Plan 2017/18 (Appendix 1) is approved.

Report prepared by:	Katherine Frost, Sustainable Projects Officer.

# Data Quality

Data sources: N/A

Data checked by:  Katherine Frost, Sustainable Projects Officer.

Data rating:

| 1 | Poor |  |
| --- | --- | --- |
| 2 | Sufficient | ( |
| 3 | High |  |

Background Papers

Green Expectations, Three Rivers District Council’s Sustainability and Climate Change Strategy March 2015.

APPENDICES / ATTACHMENTS

Appendix 1 – Green Expectations Action Plan 2017/18